## Risk Register
Project : Spray Train
Project Manager : Nkululeko Mbendle
Facilitator: Simo Khanyi
Date Last Review: 04 August2025
Risk Number | Categoy | Risk Name | Risk Description | Category | DPE Category / Context | Transnet Strategic objectives | Divisional objectives | Causes | Impacts | Risk Owner | Risk Correlation | Risk Status | Control Name | Controls Description | Control Owners | Control Weight (Basket to add up to 100%) | Control Design Intent: Reactive (R)/ Preventative (P) | Control Route Cause | Control Owner | E-Mail Address | Consequence | Likelihood | Risk Rating | Consequence | Likelihood | Risk Rating | Current RCE | Desired RCE | Task/Actions Name | Task/Action Owner | Start Date | To be completed by when
1. | Financial | Lack of Funding | Lack of funding to adhere to committed quantities |  |  |  |  | Project execution delays | >Non compliace to RSR,National veld and Forest Fire Act.. > PFMA Violation for payments of fines to the regulators(FPA,Local authorities) | Regional Chief Engineers |  | Active | Approved allocated bugdet |  | Depot Engineers | 0% |  |  |  |  | 40 | 40% | 16 | 40 | 40% | 16 | 0% | 80% | 1. Vegetation Control budget to be ringfenced | Technical Officers | 2025-07-08 | 2025-08-31
[8 empty] | Budget cuts |  |  |  | Active | Budget reprioritization |  | Depot Engineers | 0% |  |  |  |  | 40 | 40% | 16 | 40 | 40% | 16 | 0% | 80%
[16 empty] | 0% |  |  |  |  | 80 | 30% | 24 | 80 | 30% | 24 | 0% | 80%
2. | Operational Risk | Poor vegetation Control | Vegetation not controlled to the required specification |  |  |  |  | >Not meeting required standard >Not monitoring the Project | >Adverse impact on the operations of TRIM railway safety > Poor workmanship >Inability to comply with relavant standards and regulations | Nkululeko Ndlembe |  | Active | Master Agreement |  | Thato Sebalane | 50% | P |  |  |  | 40 | 40% | 16 | 40 | 20% | 8 | 50% | 80% | 1.Contionous Monitoring of the contract | Technical Officers | Ongoing
[15 empty] | Technical Officres | 50% | P |  |  |  | 40 | 40% | 16 | 40 | 16% | 6.4 | 60% | 80%
[16 empty] | 100% |  |  |  |  | 80 | 30% | 24 | 80 | 30% | 24
3. | Technical | Non approval of RRV"s | RSR not approving the RRV"s |  |  |  |  | >Not meeting required standard | >TRIM will be forced to cancel /terminate the contract or agreement | Nkululeko Mbendle |  | Active | RSR Standards and SLA |  | Technical Officres | 60% | P |  |  |  | 50 | 70% | 35 | 50 | 35% | 17.5 | 50% | 80% | The project team to advise the supplier to ensure compliance to RSR Standards. | Technical Officers | 2025-08-05 | 2026-03-31
[16 empty] | 60% |  |  |  |  | 90 | 40% | 36 | 90 | 40% | 36 | 30% | 80%
|  | Failure to secure required wagons/RRVS | Contractor Fails to secure the required number of wagons or RRV's |  |  |  |  | Non-adherence to technical specifications | > >Failure to achieve the objectives of the project. >Project or contract cancelletion | Nkululeko Mbendle |  | Active | Technical specifications |  | SCS Officials and Technical Officers | 60% | P |  |  |  | 50 | 20% | 10 | 50 | 10% | 5 | 50% | 80% | Development of a clear and adequade Technical Specification as per the Transnet Group /TRIM Standards | Technical Officers | 2025-08-04 | 2025-09-30
[8 empty] | Inadequate evaluation criteria |  |  |  | Active |  |  |  | 20% | P |  |  |  | 50 | 20% | 10 | 50 | 10% | 5 | 50% | 80%
[8 empty] | Inadequate system functionality evaluation |  |  |  | Active |  |  |  | 20% | P |  |  |  | 50 | 20% | 10 | 50 | 10% | 5 | 50% | 80%
[16 empty] | 100% |  |  |  |  | 35 | 25% | 8.75 | 35 | 25% | 8.75
4 | People | PCO"s Employment Termination | PCO"s exit employment halfway through the project |  |  |  |  | Labour disputes | > Failure to derive optimal benefits from the Projetct > Delays in Completing the Project > Wasteful expenditure ( PFMA Violations ) | Nkululeko Mbendle |  | Active | Contractor BCP, |  | SCS Officials and Technical Officers | 0% |  |  |  |  | 40 | 80% | 32 | 40 | 80% | 32 | 0% | 80% | 1.Ensure contractor employs or recruit new PCO's(Agreement). 2. Contractor to implemente business continuity plan | Technical Officer | 2025-09-01 | 2025-12-31
[23 empty] | 0 | 0 | 0% | 0
[23 empty] | 0 | 0 | 0% | 0
[23 empty] | 0 | 0 | 0% | 0
[23 empty] | 0 | 0 | 0% | 0
[24 empty] | 0 | 0% | 0
[16 empty] | 0% | [6 empty] | 0 | 0 | 0% | 0
[16 empty] | 0% | [6 empty] | 0 | 0 | 0% | 0
5 | Supplier | Lack of Competition | Prices that are not market related as a result of lack of competition |  |  |  |  | Inability to attract potential supplies fit for the purpose | >Uncompetitive Pricing . | CPO and Regional Chief Engineers |  | Active | PPM Guidelines |  | SCS Officials and Depot Engineers | 0% |  |  |  |  | 45 | 70% | 31.5 | 45 | 70% | 31.5 | 0% | 80% | 1. The technical specifications to be generic and seek for a solution that can be supplied and integrated by more than one supplier in South Africa from the market. | Nkululeko Mbendle | 2025-08-04 | 2025-12-31
[8 empty] | Confinement of the procurement processes. | [7 empty] | 100% | P |  |  |  | 45 | 70% | 31.5 | 45 | 35% | 15.75 | 50% | 80% | 2. Issue the tender on an open tender process as per PPM guidelines. |  | 2025-08-04 | 2025-12-31
[16 empty] | 100% |  |  |  |  | 53 | 19% | 10.07 | 53 | 19% | 10.07 |  |  |  |  | 01/09/2022 | 31/03/2023
[21 empty] | 53 | 19% | 10.07 | 53 | 19% | 10.07 |  |  |  |  | 01/09/2023.01/03/2023 | 31/03/2024. 01/10/2023
[16 empty] | 20% | P |  |  |  | 53 | 47% | 24.91 | 53 | 47% | 24.91 |  |  |  |  | 01/04/2023 | 31/03/2024
[16 empty] | 100% | 0 | 0 | 0 | 0 |  | 0.54 | 25.82 | 75.5 | 36.5% | 17.945
|  | Project delays | Contractor falling behind the programme |  |  |  |  | Inexpirienced Project Managers | >project overrun > failure to deliver project on schedule time | Depot Engineers |  | Active | Service level agreement and master agreements |  | Technical Officres | 0% |  |  |  |  | 25 | 70% | 17.5 | 25 | 70% | 17.5 | 0% | 80% | 1. Request the service provider\supplier to place orders as soon as the Purchase Order is issued by Transnet 2. Conduct daily\weekly \monthly programmes to monitor project progress. NOTE: Ensure that the project delivery lead times are evaluated and include them in the SLA. | TRIM Contract Manager | 2025-12-01 | 2026-03-31
[16 empty] | 0% |  |  |  |  | 29 | 80% | 23.2 | 29 | 80% | 23.2 | 0% | 80% | 2. Project Management by an expirienced Project Manager . | TRIM Contract Manager | 2025-12-01 | 2026-03-31
[23 empty] | 0 | 0 | 0% | 0
[23 empty] | 0 | 0 | 0% | 0
[16 empty] | 0% | 0 | 0 | 0 | 0 |  | 75% | 20.35 | 27 | 75% | 20.35
6 | Safety | SHE incidents | Incidents and accidents by contractor employees |  |  |  |  | Non compliance to OHSA | > Injuries >Fatalities .>Damage of infrastructure and equipment | Nkululeko Mbendle |  | Active | Technical Specificificatios,SWP"s |  | Technical officers and Safety Specialsit | 0% |  |  |  |  | 40 | 40% | 16 | 40 | 40% | 16 | 0% | 80% | Tenderer SHE Management System and Proper methodology applied when handling / spraying herbicides according to SANS 10206-2020 | Safety Specialist & Technical Officers | 2025-08-04 | 2026-03-31
[16 empty] | 0% |  |  |  |  | 45 | 40% | 18 | 45 | 40% | 18 | 0% | 80% | Safety File to be checked for adherence
7 | Planning | Resource allocation | Failure to include or prioritise spray train on the ITP |  |  |  |  | > Operators pushing commodity trains | > Delays in completing the project on time > Loss of revenue | Nkululeko Mbendle |  | Active | Adherence to ITP |  | DE's and Techncial officers | 0% |  |  |  |  | 40 | 40% | 16 | 40 | 40% | 16 | 0% | 80% | 1. Engage TFR and train control offices regarding ITP. | Technical Officers | 2025-08-31 | 2026-03-31
Inherent Risk Level
Residual Risk Level

## Likeli & Cntrl rating
Likelihood rating:
Category |  | Criteria
E | ≥90% probability | · impact is occurring now, or
· could occur within “days to weeks”
D | ≥50%<90% probability | · balance of probability will occur, or
· could occur within “weeks to months”
C | ≥20%<50% probability | · may occur shortly but a distinct probability it won’t, or
· could occur within “months to years”
B | ≥1%<20% probability | · may occur but not anticipated, or
· could occur in “years to decades”
A | <1% probability | · occurrence requires exceptional circumstances
· exceptionally unlikely, even in the long term future
· only occur as a “100 year event”
Control effectiveness rating:
RCE | RCE Rating Scale | Guide
Rating
Satisfactory | ≥80% | Nothing more to be done except review and monitor the existing controls. To the extent that is reasonably achievable, controls are well designed for the risk, are largely preventative and address the root causes and Management believes that they are effective and reliable at all times.
Requires Improvement | ≥50%<80% | Most controls are designed correctly and are in place and effective. Some more work to be done to improve operating effectiveness or Management has doubts about operational effectiveness and reliability.
Unsatisfactory | ≥10%<50% | While the design of controls may be largely correct in that they treat most of the root causes of the risk, they are not currently very effective. There may be an over-reliance on reactive controls.
or
Some of the controls do not seem correctly designed in that they do not treat root causes, those that are correctly designed are operating effectively.
None | <10% | Virtually no credible control. Management has no confidence that any degree of control is being achieved due to poor control design and/or very limited operational effectiveness.

## Consequence 7 scale
Rating |  | Financial impact - Operating Profit R | Investment impact NPV R | Human Health and Safety | Environment and Community | Reputation and Brand | Compliance and Legal | Information Communication Technology
100 Points Rating
1 | ≥80 | > 1 billion | > 5 billion | - Multiple fatalities, and/or | - Irreversible long term environmental damage to a highly valued species or location | - Prolonged international condemnation | - Major litigation or prosecution with damages of R100m+ plus significant costs. | - Major loss of or nonavailability of critical ICT services and ICT enabled process across more than two ODs.
|  |  |  | - Very serious irreversible injury to >100 people | - Large-scale prolonged class action. | - Transnet CE and/or Business CEO departs and board is restructured | - Custodial sentence for company Executive | - Failure of a mission critical project that spans more than one OD.
[6 empty] | - Public reprimand from Government | - Long term closure of operations by authorities.
- Transnet loses operating licence for an extended period
2 | ≥60<80 | 100 million | 500 million | - Multiple fatalities, and/or | - Irreversible long term environmental damage. | - Prominent negative International and South African press reporting over many days | - Major litigation or prosecution with damages of R50m+ plus significant costs. | - Major loss of or nonavailability of critical ICT services and ICT enabled process across more one or two ODs.
|  | - 999 million | - 4,9 billion | - Significant irreversible injuries to up to 10 people | - Community outrage- potential for large-scale class action. | - Non-public reprimand by Government | - Custodial sentence for Manager | - Failure of a major project that spans more than one OD.
[6 empty] | - Senior executive departs and/or board is restructured. | - Medium term closure of operations by authorities.
- Operating licence is threatened
3 | ≥45<60 | 10 million | 50 million | - Single fatality and/or | - Prolonged environmental impact. | - National press reporting over several days. | - Major litigation costing R10m+. | - Major loss of or nonavailability of critical ICT services and ICT enabled process within one OD.
|  | – 99 million | - 499 million | - Severe irreversible effects to one or more people | - High-profile community concerns raised – requiring significant remediation measures and management attention | - Government caution | - Investigation by regulatory body resulting in long term interruption to operations. | - Failure of a mission critical project that affects one OD.
[6 empty] | - Pressure on Executives to leave. | - Possibility of custodial sentence.
- Implications for operating licence.
4 | ≥30<45 | 1million | 5 million – | - Moderate irreversible disability or impairment to one or more people. | - Major spill or release leading to off-site impact | - Local press reporting – over several days | - Major breach of regulation with punitive fine. | - IT functionality / availability seriously affected across more within one OD.
|  | – 9,9 million | 49 million |  | - Medium term recovery. | - Manager may be asked to leave. | - Significant litigation involving many weeks of management time. | - Failure of a non-critical project that affects one OD.
[5 empty] | - High potential for complaints from interested parties. | - Government may be interested
5 | ≥20<30 | 100000 | 500000 | - Objective but reversible disability requiring hospitalisation to several people. | - Medium term effect on environment/community | - Local press reporting | - Breach of regulation with investigation or report to authority with prosecution and/or moderate fine possible. | - IT functionality / availability moderately affected in one OD.
|  | -999000 | - 4,9 million |  | - Required to inform environmental agencies, (e.g.: noise, dust) | - Disciplinary action likely. |  | - Serious issues that could affect the successful delivery of a project within an OD regarding timeline, budget or functionality.
6 | ≥10<20 | 10000 | 50 000 – | - Objective but reversible disability requiring the medical treatment of one person. | - Small, unconfined spill or release | - No press reporting | - Minor legal issues, non-compliances and breaches of regulation. | - IT functionality / availability minimally affected
|  | – 99 000 | 499000 |  | - Short term transient environmental or community impact- remedial action needed. | - Disciplinary action may be taken
7 | <10 | < 10 000 | <50 000 | - Minor injury | - Minor impact | - No reputational impact | - Minor breach only | - IT functionality / availability effect negligible

## Heatmap
Cat | % | ENHANCED ERM METHODOLOGY (Heat Map using minimax point values)
E | 100% | 9 | 10 | 29 | 30 | 44 | 45 | 59 | 60 | 79 | 80 | 99
| 90% | 8.1 | 9 | 26.1 | 27 | 39.6 | 40.5 | 53.1 | 54 | 71.1 | 72 | 89.1
D | 80% | 7.2 | 8 | 23.2 | 24 | 35.2 | 36 | 47.2 | 48 | 63.2 | 64 | 79.2
| 70% | 6.3 | 7 | 20.3 | 21 | 30.8 | 31.5 | 41.3 | 42 | 55.3 | 56 | 69.3
| 60% | 5.4 | 6 | 17.4 | 18 | 26.4 | 27 | 35.4 | 36 | 47.4 | 48 | 59.4
| 50% | 4.5 | 5 | 14.5 | 15 | 22 | 22.5 | 29.5 | 30 | 39.5 | 40 | 49.5
C | 40% | 3.6 | 4 | 11.6 | 12 | 17.6 | 18 | 23.6 | 24 | 31.6 | 32 | 39.6
| 30% | 2.7 | 3 | 8.7 | 9 | 13.2 | 13.5 | 17.7 | 18 | 23.7 | 24 | 29.7
| 20% | 1.8 | 2 | 5.8 | 6 | 8.8 | 9 | 11.8 | 12 | 15.8 | 16 | 19.8
B | 10% | 0.9 | 1 | 2.9 | 3 | 4.4 | 4.5 | 5.9 | 6 | 7.9 | 8 | 9.9
A | 1% | 0.09 | 0.1 | 0.29 | 0.3 | 0.44 | 0.45 | 0.59 | 0.6 | 0.79 | 0.8 | 0.99
| MiniMax Points | 9 | 10 | 29 | 30 | 44 | 45 | 59 | 60 | 79 | 80 | 99
| Category | 7 | 6 | 5 | 4 |  | 3 |  | 2 |  | 1
|  | CURRENT METHODOLOGY | [7 empty] | Priority | From | Below
| E | III | III | II | II | I | I | I |  | V | 0.001 | 6
| D | IV | III | III | II | II | I | I |  | IV | 6 | 20
| C | IV | IV | III | III | II | II | I |  | III | 20 | 35
| B | V | IV | IV | III | III | II | II |  | II | 35 | 55
| A | V | V | IV | IV | III | III | II |  | I | 55 | 100
|  | 7 | 6 | 5 | 4 | 3 | 2 | 1