## Week1
TRANSNET NATIONAL PORTS AUTHORITY
ENQUIRY NUMBER: TNPA/2023/01/0014/20728
DESCRIPTION OF THE SERVICE: FEASIBILITY DESIGN FOR THE UPGRADE AND DEEPENING OF MAYDON WHARF BERTH 5-11 AND 15 IN THE PORT OF DURBAN
Question no. | Date | Organization | Email Address | Enquiries | Category | Responsible Person (Transnet) | Response
1 | 2023-04-04 | RHDV | Jaco Steyn <Jaco.Steyn@rhdhv.com | The tender calls for the Senior Design Engineer to be professionally registered through ECSA. Will a professional registration under the Washington Accord also be accepted, i.e. Chartered Engineer though ICE of similar. | Management and CV's | Vuyelwa Mabaso/ Masupha Letsie | Yes, it shall be accepted
2 | 2023-04-04 | RHDV | Jaco Steyn <Jaco.Steyn@rhdhv.com | In the briefing session, it was mentioned that all surveys, concept and prelim design reports will be share with the tenderers that attended. Please can I request that this be share as soon as possible as this will inform the tender strategy and we need some time to study and review the information. | Procurement | Mphoyakaomphile Ngwenya | One drive link is shared to all via One Drive link.
3 | 2023-04-04 | RHDV | Jaco Steyn <Jaco.Steyn@rhdhv.com | In the briefing session it was stated at no extension of time will be entertain. However, giving that we are approaching the easter holiday period with numerous people are on leave for religious reasons, I do not think it is unfair to grand the tenderers a two week extension on the submission date. I propose that the submission date be extended to 9 May 2023. | Project Manager/ Procurement | Mphoyakaomphile Ngwenya/Vuyelwa Mabaso | Closing date has been extended Monday 15 May 2023 at 17h00 on the etenders website.
4 | 2023-06-04 | WSP | Dawood.Chafeker@wsp.com | Based on the amount of information provided, we believe more time is needed to complete an holistic and competitive bid. Considering the sheer amount of forthcoming public holidays, we hereby request extension of time until 25th May 2023. | Project Manager/ Procurement | Mphoyakaomphile Ngwenya/Vuyelwa Mabaso | Closing date has been extended Monday 15 May 2023 at 17h00 on the etenders website. Based on our initial date the period had taken the public holidays into consideration.
6 | 2023-06-04 | PRDW | gneuhoff@prdw.com | Extension of time for submission We respectfully request Transnet to consider extending the closing date by 2 weeks from 25 April to 9 May. | Project Manager/ Procurement | Mphoyakaomphile Ngwenya/Vuyelwa Mabaso | Closing date has been extended Monday 15 May 2023 at 17h00 on the etenders website.
7 | 2023-06-04 | PRDW | gneuhoff@prdw.com | Request for the following reports to be shared with bidders: * Concept and Prefeasibility Study completed in 2021 * Concept Study for detailed technical condition assessment completed in 2021 * Historical reports and data These reports will provide key information and ensure consistency of understanding across all bidders that will allow Transnet to receive informed technical responses. | Project Manager | Vuyelwa Mabaso | The required information should be covered in the link sent

## Week 2
TRANSNET NATIONAL PORTS AUTHORITY
ENQUIRY NUMBER: TNPA/2023/01/0014/20728
DESCRIPTION OF THE SERVICE: FEASIBILITY DESIGN FOR THE UPGRADE AND DEEPENING OF MAYDON WHARF BERTH 5-11 AND 15 IN THE PORT OF DURBAN
Question no. | Date | Organization | Email Address | Enquiries | Category | Responsible Person (Transnet) | Response
1 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | CIDB certificates relate to contractors. The tender is understood to be aimed at consultants. Please confirm that CIDB certificates are not required. | Management and CV's | Vuyelwa Mabaso/ Masupha Letsie | This is a NEC PSC contract as included in the tender. There is no reference made to the CIDB and as such CIDB certificates are not required.
2 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | NEC3 PSC - clause X7: Please confirm the items that will be included in the delay damages list. | Procurement | Mphoyakaomphile Ngwenya | The Delay damages are the liquidated damages paid by the Consultant when he fails to complete the services by the Completion Date. The Consultant pays delay damages at the rate stated in the Task Order.
3 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | NEC3 PSC - clause X13: Performance Bond: 5% of the total of the Prices (Incl. VAT), will it be possible to remove this from the requirement. Performance bonds are normally intended for Construction projects. | Procurement | Mphoyakaomphile Ngwenya | X13 is included as a Secondary Clause in the NEC PSC Contract and is not only intended for Construction projects.
4 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | Reference is made to NEC3 engineering and construction contract level 3 programme being required. Please confirm that this is a requirement for the consultant's tender submission. | Project Manager/ Procurement/Lead Planner | Mphoyakaomphile Ngwenya/Vuyelwa Mabaso/Cliff Phakathi | An addendum will be issued to correct the NEC3 to reflect PSC3. However the level 3 programme is still required under the PSC3 31.2.
5 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | Please confirm that all references to the NEC ECC contract requirements are not applicable to the submission of the consultant's tender. | Procurement | Mphoyakaomphile Ngwenya | Confirmed, this is an NEC PSC Contract
6 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | T2.2-03 (Page 3-4): Section T2.2-03: Evaluation Schedule - Qualification & Experience of Key Personnel, the following requirement is stated "The environmental Manager shall be in possession of a bachelor’s degree in environmental management or Science or other closely related discipline. The environmental Manager must be registered with EAPASA with at least 10 years work experience in the marine construction projects." However, the scoring table on page 3 to 4 of Section T2.2-03 indicates a score of 100 for "Environmental Manager has more than 12 years of on-the-job Environmental Management experience, is in possession of a relevant master’s degree in Environmental Management/Science or equivalent and is registered with EAPASA. Please clarify this requirement. | Project Manager/ Procurement/ Environmental Manager | Mphoyakaomphile Ngwenya/Vuyelwa Mabaso/ Gugulethu Buthelezi | The intention is for the Bibbers to at least meet the minimum qualifying score of 60. You explained it correctly on your e-mail. However, due to the inconsistency with the number of years experience parameters, we will use the parameters set on page 3 of T2.2-03 scoring purposes. The bidders will score a 60 if they have ≥8 to =10 years work experience in marine construction. This means that if the bidder has 9 years work experience in the marine construction, they will still score a 60, similarly, if they have 8, 8.5 or 9.5 years work experience they will be allocated a score of 60. The parameters change as it progresses with the scoring levels. an independent EAP can either be from the same company or the independent EAP services be subcontracted. The term ‘independent’ was used because the EAP has to be independent of Transnet who is the Developer. The minimum qualifying score for functionality is 60 points. However, the tenderer will score up to 100 points if they have more experience than the prescribed.
7 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | Section 2.3(Page 191): Page 191, Section 2.3 Detailed engineering Consultant's scope of services, the following is stated " The Consultant will provide an independent EAP that will undertake all environmental processes". Is the Independent EAP required to be from a different company to the design engineer? | Project Manager/ Environmental Manager | Vuyelwa Mabaso/ Gugulethu Buthelezi | An independent EAP can either be from the same company or the independent EAP services be subcontracted. The term ‘independent’ was used because the EAP has to be independent of Transnet who is the Developer.
8 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | T2.2-05 (Page 1-3): If part of the scope of work is subcontracted, can the experience of the subcontracted entity be used as part of the Tenderer’s experience, or can this only be done if a Joint-Venture or Consortium is set up? | Project Manager/ Environmental Manager | Vuyelwa Mabaso/ Gugulethu Buthelezi | The subcontractors experience will be taken into consideration if part of the scope of work is subcontracted out. It is the Consultants responsibility to ensure they submit the subcontractors previous experience for evaluation with their tender and clearly state what portion of work they will be undertaking.
9 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | T2.2-05 (Page 1-3): If part of the scope of work is subcontracted, can the experience of the subcontracted entity be used as part of the Tenderer’s experience, or can this only be done if a Joint-Venture or Consortium is set up? | Procurement | Mphoyakaomphile Ngwenya | The subcontractors experience will be taken into consideration if part of the scope of work is subcontracted out. It is the Consultants responsibility to ensure they submit the subcontractors previous experience for evaluation with their tender and clearly state what portion of work they will be undertaking.
10 |  | WSP | Dawood.Chafeker@wsp.com | We have reviewed the provided data from the FEL 1 design study. We note that the Detailed Condition Assessment at Maydon Wharf conducted by WML Coast in 2021 is not included in the provided data. This report is references in the FEL 1 Concept and pre-feasibility study report. Under the Conditional Assessment folder provided, only the Diving Report, GRP Survey and the Bathy reports are provided. There is no overall summary report with details on the existing structures. Will this report be made available? | Project Manager | Vuyelwa Mabaso | Please see the report located in the link below. It is in the folder sent to the tenderers Condition assessment report >>Diving report >>Condition assessment, repair…

## Week 3
TRANSNET NATIONAL PORTS AUTHORITY
ENQUIRY NUMBER: TNPA/2023/01/0014/20728
DESCRIPTION OF THE SERVICE: FEASIBILITY DESIGN FOR THE UPGRADE AND DEEPENING OF MAYDON WHARF BERTH 5-11 AND 15 IN THE PORT OF DURBAN
Question no. | Date | Organization | Email Address | Enquiries | Category | Responsible Person (Transnet) | Response
1 | 17/4/2023 | Lodemann | <mmadiba@lodemann.co.za> | We intend bidding for this project but feel that the scoring criteria disadvantages young black firms as the few dominant players in this sector do not normally partner with black companies. At present we have limited exposure to coastal engineering works and we will not score maximum score. We however, do have a PrEng with a masters degree in Coastal Engineering in our employ. Further to this we are exploring a few international partnerships with entities with multiple international projects. We do not want to form JV’s with these entities but are looking at having them as named sub-consultant/s in this bid. We shall include a sub-consulting agreement if required. Our request is that TNPA scores the experience of our subbies as they will be fully involved in then project, should we be successful. Please confirm acceptability of this request | Management and CV's | Vuyelwa Mabaso/ Asanda Dube | The subconsultant experience will be taken into consideration if part of the scope of work is subconsulted out. It is the Consultants responsibility to ensure they submit the subcontractors previous experience for evaluation with their tender and clearly state what portion of work they will be undertaking. Please see point 6 on week 2 tab.
2 | 2023-11-04 | Zutari | Pravesh.Lognath@zutari.com | Section 2.8 (Page 195): The project does not include construction of the works, yet construction supervision is considered as an optional extension to the Scope of Work. Is it essential to include a CV for a Supervisor/Resident Engineer at bid stage? It is noted that this person is not rated in the bid assessment. |  | Vuyelwa Mabaso/ Gugulethu Buthelezi | With reference to 2.8.2 “The Consultant is required to provide as much evidence as possible to unequivocally demonstrate that the incumbent completely satisfies these requirements”. A CV should be one of the evidence for the requirements.

## Week 4
TRANSNET NATIONAL PORTS AUTHORITY
ENQUIRY NUMBER: TNPA/2023/01/0014/20728
DESCRIPTION OF THE SERVICE: FEASIBILITY DESIGN FOR THE UPGRADE AND DEEPENING OF MAYDON WHARF BERTH 5-11 AND 15 IN THE PORT OF DURBAN
Question no. | Date | Organization | Email Address | Enquiries | Category | Responsible Person (Transnet) | Response
1 | 24/04/2023 | Mmetlakitso | lebogang.setshedi@mmetlakitso.com | The requirements on the project planner or scheduler are not clear and confusing. Under T1.2 – Tender Data, p5 of 9. The requirement is for a planner with formal or vocational training. However, under T2.2-03 – Qualifications and Experience, you state that the planner should have prerequisite experience AND certified MS Projects and Primavera Practitioner. We think that this is an overkill as most planners with a formal qualification will have a National Diploma or a Bachelor’s degree. Most people with a formal qualification will be registered with a relevant body such as SACPMP or PMI. MS project or Primavera certification is more suited for vocational training candidates. Requesting a prerequisite qualification AND certification will limit competition to few companies, excluding others who have the necessary experience to provide the required project management services. | ManagementandCV's for Programme | Mphoyakaomphile Ngwenya | The tender requires the "Planner should have a minimum of 10 years’ experience working in structural and marine engineering projects undertaking the role of Planner as well as a background (educational or vocational) in one of the built environment disciplines. Must be a certified Microsoft Projects or Primavera Practitioner. In addition, experience working with the NEC3 (Professional Service Engineering Contract & Engineering and Construction Contract), is an added advantage"The returnable does not request for a planner requirements as per clarification question please refer to the page 5/9 read in conjunction to returnable T2.2-03 and the evaluation prompts.
2 | 24/04/2023 | Mmetlakitso | lebogang.setshedi@mmetlakitso.com | Pursuant to the query above, we also think that limiting the scheduling to MS Project or Primavera is tantamount to promoting specific software packages, which is against the competition commission rules. We suggest you change the requirements to MS Projects, Primavera or similar. Alternative scheduling software packages to be interoperable with MS Project or Primavera. | Programme | Cliff Phakathi | Primavera and Microsoft Projects are the only scheduling softwares utilised within TNPA, it is therefore the only formats that will be accepted. Tenderers are not limited to compile their schedules in other softwares if they choose to do so, however the final submission for tender purposes must be in Primavera and Microsoft Projects.
3 | 24/04/2023 | Mmetlakitso | lebogang.setshedi@mmetlakitso.com | Most of previous Transnet requirements did not place an emphasis on this requirement for Consultancy services but it is normally included in the Construction Contracts. As this is a new requirement and there is no guarantee that the works will not proceed to construction, we suggest that the requirement should be removed but allowance should be made that the Consultant will be required to be registered for ISO 45001 at the completion of this study, prior to commencement of the construction works (if the works will definitely go to construction). We also note that ISO 45001 has replaced ISO 18001 since 2021. Emerging entities cannot register for OHSAS 18001. | Health and Safety | Abram Motshegare | During this phase of the project the consultant will be expected to manage any sub-consultants or contractors appointed by the successful tenderer. We are assessing the capability to manage your own sub-consultants or contractors. This is a mega project specifical zooming into the next phase, should you be the successful tenderer there is high possibility of your organisation implementing or constructing your own designs, now by having an implemented, fit for purpose safety management system by organisation it means your organisation will be able to assess and manage risks associated with this project during this phase and possibly the next phase effectively and efficiently. It will also be evident that your organisation will be able to implement planned health and safety processes to manage the project safely and achieve the intended outcomes.
4 | 24/04/2023 | Mmetlakitso | lebogang.setshedi@mmetlakitso.com | Reading the preamble on the requirements for the programme, it is clear that these requirements are meant for Construction contracts, .e.g., “The Contractor indicates how he plans in achieving the following dates and clearly demonstrates them on the schedule by complying with Clause 31.2 of the NEC ECC – Initiates starting date, access dates, key dates, planned Completion, Sectional Completion Dates & Completion Date.”. Access dates, sectional completion and completion dates are mainly for construction contracts. Further down in the preamble, and the under the evaluation criteria, on p 2 of 8, of this section, it is mentioned that constraints will be one of the sub – criterion that will be evaluated. Programme constraints (hard or soft) are normally associated with construction contracts. Secondly, the Client should provide detailed information that will need to be considered when incorporating constraints into the programme. The Scope of Works and Site Information do not provide any details on the items that will force a constraint on the programme. | Contract Data | Mphyakaomphile Ngwenya | The reference to NEC ECC has been replaced by NEC PSC please refer to NEC PSC kindly refer to Addendum 01. point 3 and Annexure C
5 | 24/04/2023 | Mmetlakitso | lebogang.setshedi@mmetlakitso.com | T2.2 -4a – H & S Contractor Safety Questionnaire. Looking at the contents of the form, it is clear that the form is specifically for contractors and construction activities. We are of the opinion that the information required on this form, is for contractors and does not apply to Consultancy services, especially when the designs will be done remotely. Kindly consider removing this requirement. | Health and Safety | Abram Motshegare | During Tender clarification we clarified this requirement, as a consultant you are having your internal processes to manage contractors and your organisation will appoint contractors or sub-consultants to work on Transnet sites where there are other contractors working, your processes are very critical to ensure that this phase and the next phase are managed safely, your past experience will also outline the level of experience you have in managing projects of this magnitude, your organisation need to aslo be in Goodstanding COID, we cannot remove the requirement.
5 | 24/04/2023 | Mmetlakitso | lebogang.setshedi@mmetlakitso.com | Query 06: T2.2-20: Insurance. It is not clear what information is required under Premium on the form. Premium payable is confidential information between the service provider and Client. Providing such information will be in violation of the OPPI Act, aw we will need to get consent from the service provider to provide such information. Most insurers will provide the necessary details confirming but do not divulge information on the premium. Please consider revising. | Insurance returnable and Contract Data | Mphoyakaomphile Ngwenya | Clause 81.1 in NEC3 Professional Services Contract (June 2005)(amended June 2006 and April 2013) requires that the Consultant provides the insurance stated in the insurance table except any insurance which the Employer is to provide as stated in the Contract Data. Please provide the following details for insurance which the Consultant is still to provide. Notwithstanding this information all costs related to insurance are deemed included in the tenderer’s rates and prices.refer to PSC 81.1 that states " The consultance provides the insurance stated in the insurance Table excecpt any insurance which the employer is to provide as stated in the Contract Data. The Insurancs provide cover from the contract Date until the end of the periods stated in Contract Data" The returnable shoul be read in conjunction with 81.1 of the Contract Data. As this is still the tender stage the insurance will be required from the succesful tenderer. The documents are standards used and cannot be revised.
7 | 24/04/2023 | Mmetlakitso | lebogang.setshedi@mmetlakitso.com | Query 07: Clause 13.6 of Contract Data conflicts with optional clause X18.3. kindly explain the why the retention period will be three years but limitation of liability is two years? Suggest that the requirement for retention is removed and the limitation of liability to remain two years. | Contract Data | Mphoyakaomphile Ngwenya | The 2 clauses are independant of each other. Under the Professional Services Contract clause 13.6 defines how long should the consultant retain documentation? "The Consultant should retain all drawings, specifications, reports and other documents for the period for retention" X18.3 refers to risks and defects not found after the defects date.
8 | 24/04/2023 | Mmetlakitso | lebogang.setshedi@mmetlakitso.com | Query 08. Supervisor/Resident Engineer. Your response to query 2, dated 2023/04/11 contradicts with the requirements for this tender. Clause 2.8 of the Scope of Service, sub-clause 2.8.3, states that “The Supervisor/Resident Engineer will be provided with the construction monitoring team as deemed necessary y then for the project.” We interpreted this clause to read that the relevant CV will be required by then. Since most of these people do freelancing work, they refuse to provide CV’s unless if there’s confirmation that the work will go to Construction. We request that the CV for the Resident Engineer should be requested at the time the project is about to proceed to construction. | Management and CV's and Scope of Service | Vuyelwa Mabaso. | Employer requires evidence that the rate provided matches the experience and qualification of the candidate. It is upto the tenderer to ensure that such evidence is presented.
9 | 24/05/2023 | PRDW | gneuhoff@prdw.com | Please may you assist us with missing information on pages 43, 45 and 46 (pdf page numbers) of the Concept and Prefeasibility Study Report. We attach a copy for your information. | Extra Documents | Vuyelwa Mabaso. | The tenderers are to note that, the information is for internal use. That is why it is intentionally hidden.