## RFI 01
TENDER QUERIES / REQUEST FOR INFORMATION
|  | Date: | 2025-01-16
Query No. | Applicable section in tender documents | Page | Section / Item No | Details of Query / Information Required | TRANSNET Response
6.1 | Addendum No 5 |  |  | Please can you confirm the tender closing date
6.2 | C2.2 |  | BOQ | Please can we have a revised Bill of Quantity, PDF and Excel template | Provided
|  |  |  | In support of our request for a revised BoQ, we note the following items (there may be others) are not covered by the BoQ, and thus may give rise to ambiguity and misalignment in the proposals received. • 110mm dia Cable sleeves • Manholes complete by civil contractor • Excavation, backfill, dealing with services, layerworks, paving for 70mm2 core electrical cable. • Timber support details and gussets. • Earthing • Concrete cast in water • Blinding layer below anchor beam • 500mm deep river sand below anchor beam • 500mm deep aggregate below anchor beam • Tyre fender anchors • Retaining wall concrete, formwork and rebar. Shoring for construction of anchor beam/ retaining wall adjacent existing building | The items have been added and are now included in the new revised BOQ.
6.3 | T2.2-12 |  | Addenda | Please advise if Addendum No 4 was issued | Yes was issued and the last addenum is addendumn 8
6.4 | Contract Data |  |  | Please advise on revised Start Date per Contract Data to be able to adjust our Programme accordingly | That can be align with the closing date as communicated by Addendum Number 8.
7.1 | C1.2 - Contract Data | Page 133, 142 | Clause X18.1: Commercial and legal department: | We note clause X18.1 of the tender document calls for unlimited liability iro Indirect or consequential loss, we also note that in terms of clause 84.1 Public liability cover is to be provided by Transnet, would you kindly confirm the following 1.) What Indemnity limit is provided for in terms of the Public Liability cover provided for by Transnet 2.) Will the cover provided extend to cover Indirect or consequential losses envisioned in terms of clause X18.1 We look forward to receiving the response in this regard, and note that the clause X18.1 as currently set written poses significant risk for Contractors, and is not in line with what would be considered industry norm. | See attached Public Liability for Transnet.