TERMINAL OPERATOR AGREEMENT TO DESIGN, DEVELOP, FINANCE, CONSTRUCT, OPERATE AND, MAINTAIN A LIQUID BULK TERMINAL AT THE LIQUID BULK PRECINCT IN THE PORT OF NGQURA FOR A PERIOD OF 25 (TWENTY-FIVE YEARS).

between

TRANSNET NATIONAL PORTS AUTHORITY, an operating division of TRANSNET SOC LTD,

(Registration number 1990/000900/30)

(Hereinafter called “TNPA”)

and

[TERMINAL OPERATOR]

NOTE TO BIDDERS - All Bidders and to note the provisions of the RFP and are reminded to submit “marked up” versions of the negotiable clauses of this Terminal Operator Agreement. - As the Terminal Operator Agreement has been drafted in general terms, TNPA reserves the right to amend or vary any of the terms of this Terminal Operator Agreement to ensure alignment with the preferred Bidders Business Case and the commercial risk allocation between the TNPA and the Preferred Bidder. - The Financiers Direct Agreement will be negotiated and agreed between the TNPA, the Preferred Bidder and the Lenders of the Preferred Bidder should third party finance be provided to undertake the project. This Financiers Direct Finance Agreement and the negotiable clauses of the Terminal Operator Agreement will be revised to ensure consistency between Terminal Operator Agreement and the Financiers Direct Finance Agreement. - TNPA shall not in any way be bound to the terms and conditions provided for in this draft TOA and TNPA reserves the right to vary and negotiate the final terms with the Preferred Bidder.

TABLE OF CONTENTS

Clause number and description	Page

1.	Definitions and Interpretation	4

2.	Introduction	35

3.	Commencement, Duration and Concession Period	36

4.	Appointment of Terminal Operator and Grant of Rights	38

5.	Duration of the Concession Period	53

6.	Concession Fees	54

7.	Ownership and eventual handover of the Project Site and the Terminal Infrastructure	55

8.	Indemnity	56

9.	Terminal Operator's Warranties and Undertakings	58

10.	Compliance with D&C Specifications and Operational Plan	60

11.	Contracts	60

12.	Environmental Compliance	61

13.	Empowerment Obligations	66

14.	Access to documents, copyright, and related matters	69

15.	Performance Guarantees	72

16.	Project Insurance	74

17.	Port Users and Port Rules	76

18.	Changes in the Terminal Operator	77

19.	TNPA's Assistance and Rights and Limitations on Liability	77

20.	TNPA Step-in	78

PART II – PROVISION OF THE PROJECT SITE AND THE PORT	80

21.	Provision of the Port	80

22.	The Project Site	81

23.	Key Personnel and Removal of Personnel	84

24.	Health and Safety	84

25.	Security	86

PART III – DESIGN AND CONSTRUCTION, OPERATION AND MAINTENANCE	87

26.	Independent Certifier	87

27.	Demolish Existing Buildings	90

28.	Design and Construction	90

29.	Operations Commencement for the Project	96

30.	Operation and Maintenance	97

31.	Reporting Requirements	103

32.	Financial Accounts, Reports, inspection and reporting of changes	105

33.	Rights of Access	109

34.	Authority Changes	110

PART IV – FINANCIAL PROVISIONS	112

35.	Fees in respect of services	112

36.	Refinancing	113

37.	Foreign exchange risk	113

38.	Default Interest	114

PART V – RELIEF, AND FORCE MAJEURE EVENTS, CHANGE OF LAW	114

39.	Consequences of a Relief Event	114

41.	Force Majeure	118

42.	Unforeseeable Conduct	119

PART VI – TERMINATION	120

43.	Terminal Operator Default	120

44.	Notification	122

45.	TNPA Default	125

46.	Invalidation in terms of Section 67 of the Act	126

47.	Effects of Termination	126

48.	Termination Amount on Terminal Operator Default	132

49.	Termination Amount for TNPA Default	136

50.	Termination Amount for Invalidation in terms of section 67 of the Act	138

51.	Termination Amount for termination for Force Majeure	138

52.	Termination Amount for corrupt gifts and fraud	139

53.	Payment of Termination Amount	139

54.	Liability for Indirect and Consequential Losses and Damages	141

PART VIII – PROCEDURAL ISSUES	141

55.	Corrupt gifts and fraud	141

56.	Expert Determination	143

57.	Dispute Resolution	145

58.	Information and Audit Access	150

59.	Confidentiality and Non-Circumvention	151

60.	Miscellaneous Matters	153

PART I – GENERAL PROVISIONS

- Definitions and Interpretation

In this Agreement and its Schedules, the following terms shall, unless inconsistent with the context in which they appear, have the following meanings and cognate expressions shall bear corresponding meanings:

"Act" means the National Ports Act, 12 of 2005;

"Actual Operations Commencement Date" means the date of Operation Commencement as stated in the Provisional Operations Certificate issued by the Independent Certifier in accordance with clause 28.4 subject to all necessary and relevant, as may be applicable, NERSA authorisations being obtained;

"Adjusted Estimated Project Value" means the Estimated Project Value of this Agreement less the aggregate of:

the Calculation Costs; and

amounts that TNPA is entitled to set off or deduct under clause 60.11 (set-off),

plus, the aggregate of:

all credit balances on any bank accounts held by or on behalf of the Terminal Operator on the date that the Estimated Project Value of this Agreement is calculated; and

any insurance proceeds, and other undisputed amounts owing to the Terminal Operator (and which the Terminal Operator is entitled to retain), to the extent not included in clause 1.1.3.3;

to the extent that:

the amounts in clauses 1.1.3.3 and 1.1.3.4 have not been directly taken into account in calculating the Estimated Project Value; and

TNPA has received such amounts in accordance with this Agreement;

"Adjusted Highest Compliant Tender Price" means the Highest Compliant Tender Price as per clause 1 less, to the extent it is a positive amount, the aggregate of:

the Tender Costs;

amounts that TNPA is entitled to set off or deduct under clause 60.11 (set-off); and

the rental amounts that would have been due and remaining unpaid from the date of the Terminal Operator Default until the date of appointment of the other terminal operator;

plus, the aggregate of:

all credit balances on any bank accounts held by or on behalf of the Terminal Operator on the date that the highest-priced Tender is received; and

any insurance proceeds and other amounts owing to the Terminal Operator (and which the Terminal Operator is entitled to retain);

to the extent that:

the amounts in clauses 1.1.4.4 and 1.1.4.5 have not been directly taken into account in the Highest Compliant Tender Price; and

TNPA is entitled to such amounts in accordance with this Agreement;

"Agreement" means this Terminal Operator Agreement and its Schedules, as amended, extended, replaced and varied from time to time;

"Associated Agreements" means any agreements entered into by the Terminal Operator in respect of the Project, including agreements entered into with Subcontractors and any other Project related agreements that TNPA may designate as falling within this clause 1.1.6;

"Annual Report" means the annual report which is required to be prepared and submitted by the Terminal Operator in accordance with clause 31 (Reporting Requirements);

"Authority Change" has the meaning ascribed to it in clause 34 (Authority Changes);

"Base Case Financial Model" means the base case financial model for the Project, as set out in the Business Case, and any updates thereto and which are to be agreed to between the Parties and which shall be annexed to this Agreement prior to the commencement of the Construction Works as Schedule 4 (Base Case Financial Model) once so agreed;

"B-BBEE" means broad-based black economic empowerment;

"B-BBEE Act" means the Broad-Based Black Economic Empowerment Act 53 of 2003;

"B-BBEE Codes" means the amended B-BBEE Codes of Good Practice, published under Government Gazette No. 36928, on 10 October 2013, in terms of section 9(1) of the B-BBEE Act;

"Berths" means the envisaged new berth A100 to be developed by TNPA in the Port of Ngqura.

"Black People" means a generic term defined in the B-BBEE Act to mean natural persons who are Africans, Coloreds, and Indians –

who are citizens of the Republic of South Africa by birth or decent; or

who became citizens of the Republic of South Africa by naturalisation

before 27 April 1994; or

on or after 27 April 1994 and who would have been entitled to acquire citizenship by naturalization prior to that date;

"Black Ownership" means the effective ownership of shares by Black People, which shall be determined with reference to the B-BBEE Codes and evidenced by way of a B-BBEE Level verification certificate in any supplier of the Terminal Operator and/or third party to whom the Terminal Operator may want to cede and/or assign the rights it holds in this Agreement in terms thereof;

"Business Day" means any Day other than a Saturday, Sunday or gazetted national public holiday in South Africa;

"Business Case" means the business case relating to the financing, design and construction, operation and maintenance of the Terminal in the Port of Ngqura, any revisions and amendments thereto in terms of this Agreement and which shall be annexed to this Agreement prior to the commencement of the Construction Works as Schedule 4 (Base Case Financial Model);

"Calculation Costs" means the total of all costs forecast to be incurred by TNPA as a result of termination, which shall be calculated and discounted at the Termination Date Discount Rate, such costs to include (without double counting):

a reasonable risk assessment of any cost overruns that will arise, whether or not forecast in the relevant base case;

the costs of the services forecast to be incurred by TNPA to the standard required;

any Rectification Costs required to deliver the services to the standard required (including any costs forecast to be incurred by TNPA to complete construction or development work and additional operating costs required to restore operating services standards); and

in each case such costs to be forecast at a level that will deliver the services in accordance with the output specifications;

"Cargo" shall mean but not be limited to any liquid bulk commodities proposed to be handled by the Bidders at the envisaged new berth A100 to be developed by TNPA in the Port of Ngqura, which may include hydrocarbon and chemical products, such as petrol, diesel, jet fuel, fuel oil, carbon black feedstock, paraffin, Liquified Petroleum Gas (LPG), Biofuel & Petrol & Diesel additives, Green Fuels (ammonia/hydrogen and/or any other green fuels but excluding liquified natural gas (LNG).

"Certifications" means the following certifications or certifications that are equivalent to the certifications listed below:

ISO 14001;

BS OHSAS 18001;

ISO 9001; and

NOSA 1 – 2 Star or Equivalent;

"Change in Control" means:

any change in the control of the Terminal Operator where the Terminal Operator is no longer able to make any decisions in respect of the management and operation of the Terminal provided that, without limitation to the generality of TNPA’s right to refuse consent, TNPA  shall be entitled to withhold its consents if it considers, in its reasonable opinion, that the proposed change in Control, constitutes a deviation from the objectives of the Directive and has or is reasonably likely to have a material adverse effect on the basis upon which the Terminal Operator was appointed  to design, construct, equip, operate and maintain the Terminal or undertake the Construction Works, and carry out the Operation and Maintenance of the Terminal;

any change in Control of the Terminal Operator or any change in the way in which the Terminal Operator is managed which results in or is reasonably likely to result in non-compliance with Schedule 10 (Terminal Operator’s Supplier Development Plan) at any time prior to the expiry of the Operations Period;

any change whatsoever in Control of the Terminal Operator, whether effected directly or indirectly.

"Change in Law" means the coming into effect, after the Effective Date, of any Law, or any amendment or variation to any Law, other than any Law that on or before the Effective Date, has been published:

in a bill in a form substantially similar to the Law enacted pursuant to such publication; or

as an act but has not been brought into effect;

"Companies Act" means the Companies Act, 71 of 2008, as amended;

"Compensation Date" means either:

if clause 47.2 (Retendering Procedure) applies, the earlier of:

the date that the New Terminal Operator Agreement is entered into; and

the date on which TNPA pays the Highest Compliant Tender Price, as the case may be, to the Terminal Operator; or

if clause 48.3 (No Retendering Procedure) applies, the date that the Adjusted Estimated Project Value of this Agreement has been agreed or determined;

if clause 46 (Invalidation in terms of section 67 of the Act) applies, the date on which TNPA stipulates this Terminal Operator Agreement to be invalid;

"Completion Certificate" means the certificate to be issued by the Independent Certifier in terms of clause 28.4 (Completion of Construction Works) upon the completion of the Construction Works;

“Concession” means the concession rights granted by TNPA to the Terminal Operator.

"Concession Period" means 25 years from the Operations Commencement date, unless otherwise extended within the context of clause 5 of this Agreement;

"Confidential Information" means any and all:

information relating to the design of the Terminal or to any Intellectual Property Rights of the Terminal Operator;

information in respect of or relating to the Base Case Financial Model as well as such model and each Updated Financial Model; and

other information which relates to the undertaking or finances of any of the Parties and which is identified by the Party releasing such information as being confidential and the release of which is made in connection with this Agreement;

"Consents" means any consent, registration, clearance, filing, agreement, notarisation, certificate, licence, approval, ruling, permit, authority, or any exemption from the aforesaid, by, with or from any Relevant Authority in terms of the Laws, which is required from time to time in respect of the Project, or to be held by the Terminal Operator or which has any impact (whether direct or indirect) on the Project or the Terminal Operator, including the Environmental Authorisations and the Safety Authorisations; `

"Constitutional Documents" means the Terminal Operator's memorandum of incorporation and registration certificate, as well as the shareholders' agreement, equity subscription agreements and equity guarantees entered into and provided in respect of the Terminal Operator and any documents or agreements in respect of any debentures issued by the Terminal Operator, all of which are attached to this Agreement as per Schedule 20 (Constitutional Documents);

"Construction Agreement" means each and every written agreement to be entered into between the Terminal Operator or its authorised agent and the Construction Contractor or ceded and/or transferred to the Terminal Operator in respect of any of the Construction Works, which agreement shall be annexed hereto as Schedule 6 (Construction Agreement);

"Construction Completion" means the execution of the Construction Works that are required for the operation of the Terminal;

"Construction Contractor" means the Person who is appointed as the construction contractor by the Terminal Operator or its authorised agent in the Construction Agreement in force at the relevant time and any replacement or successor-in-title of such Person;

"Construction Documents" means all documents, drawings, data, reports, specifications, and other information (whether in printed form or in electronic form) produced in respect of the Construction Works;

"Contract Period" means the Planning Period, the Concession Period and if applicable, the Decommissioning Period;

"Construction Period" means the period commencing at the end of the Planning Period, on the Effective Date and terminating on the issue of the Completion Certificate, which period shall not be longer than 24 (twenty-four) months, unless otherwise extended in writing, with the TNPA’s consent and which consent shall not be unreasonably withheld;

"Construction Performance Guarantee" means the performance guarantee to be issued by a financial institution, on behalf of the Construction Contractor in respect of the Construction Works in favour of the Terminal Operator, which shall be annexed to this Agreement as Schedule [   ] (Construction Performance Guarantee);

"Construction Works" means the construction, installation, equipping, testing and commissioning of the Terminal Infrastructure and the Terminal Equipment required to operate the Terminal in accordance with the D&C Specifications and the Detailed Design;

"Construction Works Programme" means the programme for the Construction Works which shall be annexed to this Agreement as Schedule [      ] (Construction Agreement);

"Contract Year" means a period of 12 (twelve) consecutive calendar months, commencing on 1 April, provided that the 1st (first) contract year shall commence on the Effective Date and shall end on the 31st (thirty first ) of March following the year in which the Effective Date occurs;

"Contributor Status Level" means the B-BBEE Contributor Status Level as determined by Terminal Operator’s compliance with the applicable B-BBEE score - card in terms of the B-BBEE Codes;

"Control" means in relation to any entity, the ability, directly or indirectly, to direct or cause the direction of the votes attaching to the majority of its issued shares or interest carrying voting rights, or to appoint or remove or cause the appointment or removal of the majority of the board of directors;

"Corrupt Act" means any conduct that constitutes an offence under the Prevention and Combatting of Corrupt Activities Act 12 of 2004, including but not limited to:

offering, giving, or agreeing to give TNPA or any other organ of state or to any Person employed by or on behalf of TNPA or any other organ of state any gift or consideration of any kind as an inducement or reward;

doing or not doing (or for having done or not having done) any act in relation to the obtaining or performance of this Agreement or any other contract with TNPA or any other organ of state; or

showing or not showing favour or disfavour to any Person in relation to this Agreement or any other contract with TNPA or any other organ of state;

entering into this Agreement or any other contract with TNPA or any other organ of state in connection with which commission has been paid or has been agreed to be paid by the Terminal Operator or on its behalf, or to its knowledge, unless before this Agreement is entered into particulars of any such commission and of the terms and conditions of any such contract for the payment of such commission have been disclosed in writing to TNPA;

committing any offence in connection with this Agreement:

under any Law from time to time dealing with bribery, corruption, or extortion; or

under any Law creating offences in respect of fraudulent acts; or

at common law, in respect of fraudulent acts in relation to this Agreement or any other contract with TNPA or any other public body; or

defrauding or attempting to defraud or conspiring to defraud TNPA or any other public body in relation to this Agreement;

"CPI" means the consumer price index excluding interest on mortgage bonds, for metropolitan and other urban areas (Base 2000=100) published from time to time by Statistics SA in Statistical Release P0141.1, provided that if, after the Signature Date:

such index ceases to be published; or

the Terminal Operator and TNPA agree or, failing agreement, if it is determined pursuant to clause 57.7 (fast-track dispute resolution) that, due to a change in circumstances, the index is no longer representative;

then, from the date that the index was last published, the Parties shall use such other index as agreed between them or, failing agreement, as determined pursuant to clause 57.7 (fast-track dispute resolution) as being a fair and reasonable replacement index;

"Day" means any period of 24 (twenty-four) hours that starts at 00h01 and ends at 24h00;

"D&C Specifications" means the design and construction specifications submitted and approved in terms of clause 28 (Design and Construction) and which will be annexed hereto as Schedule 5 (D&C Specifications) on approval thereof by the Parties;

"Decommissioning Period" means a maximum period of 6 (six) months commencing on the Business Day following the expiry of the Operations Period;

"Deemed New Terminal Operator Agreement" means a contract on the same terms and conditions as this Agreement, as at the Termination Date, but with the following amendments:

if this Agreement is terminated prior to the Operations Commencement Date, then the Scheduled Operations Commencement Date shall be extended by a period to allow a Suitable Substitute New Terminal Operator to achieve Operation Commencement;

any penalties accrued in terms of Schedule [     ] (Penalties) shall be cancelled; and

the term of such contract shall be determined by TNPA;

"Detailed Design" means the detailed design for the Construction Works, which is to be submitted by the Terminal Operator after the Signature Date and approved by the Independent Certifier, in accordance with clause 28.1 (Performance of the Detailed Design);

"Distributions" means whether in cash or in kind, any:

dividend or other distribution of share capital;

reduction of share capital, stated capital, any capital redemption fund or any share premium account;

cancellation, conversion, redemption or re-purchase of shares or any other variation whatsoever in share capital;

payment in respect of the shareholder loans (whether of principal, interest, breakage costs or otherwise);

payment, loan or other financial assistance, transfer of rights or other assets or receipt of any other benefit to the extent put in place after the Signature Date and not in the ordinary course of business, on an arm’s-length basis or otherwise on reasonable commercial terms to any shareholders or their Related Parties in respect of the Project; or

any release of any contingent liability of any of the Terminal Operator's shareholders or their Related Parties in respect of their financial obligations to the Terminal Operator;

"Economic Development Plan" means the Terminal Operator’s Development Plan as set forth in Schedule [      ] hereto;

"Economic Development Construction Value Summary" means the Terminal Operator’s Economic Development for construction phase Value Summary as set forth in Schedule 10 hereto;

"Economic Development Operation Value Summary" means the Terminal Operator’s Economic Development for operational phase Value Summary as set forth in Schedule [      ].

"Effective Date" means the date of fulfilment, or waiver where applicable, of the last of the Suspensive Conditions;

"Environment" means the surroundings within which humans exist and that are made up of:

the land, water and atmosphere of the earth;

micro-organisms, plant and animal life;

any part or combination of clauses 1.1.56.1 and 1.1.56.2 and the interrelationships among and between them; and

the physical, chemical, aesthetic and cultural properties and conditions of the foregoing that influence human health and well-being;

"Encumbrance" means any encumbrance, lien, charge, hypothec, pledge, mortgage, title retention agreement, security interest of any nature, adverse claim, exception, reservation, easement, right of occupation, any matter capable of registration against title, option, right of pre-emption, right of first refusal, privilege or contract to create any of the foregoing; and variations of the word, including "Encumber" and “Encumbered", shall have corresponding meanings;

"Environmental Authorisations" means any authorisations, licenses, permissions or consents to be obtained from the Relevant Authority in compliance with the Environmental Laws in order to undertake the Project;

"Environmental Laws" means all applicable Laws (including general remedies and duties of care), statutes, regulations, statutory guidance notes and final and binding court and other tribunal decisions of any relevant jurisdiction in force and binding on the Terminal Operator at the date of this Agreement whose purpose is:

to protect, or prevent pollution of, or to remedy damage to the Environment;

to protect or prevent or compensate harm to human health and safety; or

to regulate emissions, discharges, or releases of Hazardous Substances into the Environment, or

to regulate the use, treatment, storage, burial, disposal, transport or handling of Hazardous Substances,

and all by-laws, codes, regulations, decrees or orders issued or promulgated or approved thereunder for such purposes to the extent that the same have force of law and are binding either or on both of TNPA and the Terminal Operator at the date of this Agreement;

"Environmental Management Plan" means the environmental management plan and system prepared in respect of the Project for the monitoring and management of environmental issues raised as a result of the environmental impact assessment undertaken by or on behalf of, the Terminal Operator and based on TNPA's environmental policy and any Environmental Authorisations issued in respect of the Project and in terms of the Environmental Laws;

"Equity" means any shares issued in the authorised share capital of the Terminal Operator, any share premium on such issued shares, any debentures issued by the Terminal Operator and any loans to the Terminal Operator by its shareholders or debenture-holders;

"Equity IRR" means the projected blended rate of return to the Terminal Operator's shareholders and their Related Parties over the full Operations Period, having regard to Distributions made and forecast to be made and as detailed in the Base Case Financial Model;

"Estimated Project Value" means the amount determined in accordance with clause 48.3 (No Retendering Procedure) that a third party would pay to TNPA as the market value of the Deemed New Terminal Operator Agreement;

"Existing Buildings" means the existing buildings, including warehouses and sheds, located within the Project Site and depicted in Schedule 2 (Project Site);

"Expert" has the meaning ascribed to it in clause 56 (Expert Determination) of this Agreement;

"Expiry Date" means the last day of the Concession Period, unless the Minister of Transport, in terms of Section 79, directs otherwise, irrespective of whether the Terminal Operator is required to decommission and demolish the Terminal Infrastructure or not and unless otherwise extended within the context of Clause 3;

"Final Maintenance Guarantee" means the final maintenance guarantee to be issued on behalf of the Terminal Operator, which shall be substantially in the form of the guarantee annexed to this Agreement as Schedule 15 (Final Maintenance Guarantee) and shall be on terms to TNPA's satisfaction, which satisfaction may not be unreasonably withheld nor delayed;

"Force Majeure" has the meaning ascribed to it in clause 41 (Force Majeure);

"Force Majeure Event" means any event of Force Majeure;

"Hazardous Substances" means:

any petroleum or petroleum products, radioactive materials, asbestos in any form, urea formaldehyde foam insulation, transformers or other equipment that contain dielectric fluid containing regulated levels of polychlorinated biphenyls (PCBs) and radon gas; and

any pollutants, contaminants, pesticides, chemicals, materials or other substances (including any special, dangerous or toxic wastes) defined as or included in the definition of "pollutant," "hazardous substances," "hazardous wastes," "hazardous materials," "extremely hazardous wastes," "restricted hazardous wastes," "toxic substances," "toxic pollutants," or other words of similar import, by any Relevant Authority or in terms of any Environmental Laws;

"Highest Compliant Tender Price" means, as per clause 48.1 the price offered by the Tenderer (if any) with the highest tender price and, if no Tenders are received, zero;

"IMDG Code" means the International Maritime Dangerous Goods Code, published by the International Maritime Organisation as amended from time to time;

"IAS 18" means an International Accounting Standard 18 (revenue), applicable as at the Signature Date;

"Independent Certifier" means the person appointed from time to time jointly by TNPA and the Terminal Operator as the independent certifier in respect of the Project, and whose duties are specified in this Agreement under clause 26 (Independent Certifier);

"Independent Expert" shall mean:

an accountant of not less than 10 (ten) years professional experience or investment banker agreed to between the Parties, and failing agreement nominated (at the request of either Party) by the President for the time being of the South African Institute of Chartered Accountants: Eastern Cape Region, if the matter relates primarily to a financial matter; or

an attorney or advocate of not less than 10 (ten) years professional experience agreed to between the Parties, and failing agreement nominated (at the request of either Party) by the Chairperson for the time being of the Legal Practice Council or its successor, if the matter relates primarily to a legal matter; or

an engineer of not less than 10 (ten) years professional experience agreed to between the Parties and failing agreement nominated (at the request of either Party) by the President for the time being of the Engineering Council of South Africa, if the matter relates primarily to an engineering matter; or

a relevant Terminal manager of not less than 10 (ten) years professional experience agreed to between the Parties and failing agreement nominated (at the request of either Party) by the secretariat for the time being of the International Association of Ports and Harbours, if the matter relates primarily to a port facilities management matter;

"Intellectual Property Rights" means all registered or unregistered trademarks, service marks, patents, design rights (whether the aforementioned rights are registered, unregistered or formed pending applications), utility models, applications for any of the aforegoing, copyrights (including copyright in any software programmes, data and documents), database rights, the sui generis rights of extraction relating to databases and any similar or analogous rights to any of the above, whether arising or granted under the Laws or any other jurisdiction;

"Insurance" means the project insurance that the Terminal Operator is required to purchase and maintain in terms of clause 16 (Project Insurance);

"International Best Practice" means, in relation to the design, construction, equipping and commissioning of the Terminal, and in relation to the provision of the Operation and Maintenance activities, a reasonable and prudent operator that exercises that degree of skill, diligence, prudence, foresight and operating practice that would reasonably and ordinarily be expected from a skilled and experienced Person engaged in providing a Terminal similar to the Terminal or the same type of business as that of the Terminal Operator  (irrespective of whether or not that Terminal or that business is conducted by or on behalf of any organ of State), under the same or similar circumstances;

"ISPS Code" means the International Ship and Port Terminal Security Code, as referred to in the Merchant shipping (Maritime Security) Regulations, 2004, published under Government Notice R751 in Government Gazette 26488 of 21 June 2004;

"IPMS" means TNPA’s Integrated Port Management System, which is TNPA’s online internet terminal where Port Users can execute certain instructions to TNPA, such as vessel management, vessel arrival notification, changes to estimated times of arrival, marine services requests, berth planning, vessel traffic services, dry dock, change of agent requests, supplementary services, security permit application and incident reporting;

"Laws" means the Constitution of the Republic of South Africa Act, 108 of 1996, the common law, all applicable statutes, statutory instruments, by-laws, regulations, orders, rules, directives, decrees, decisions, determinations, executive orders and other secondary, provincial or local legislation, treaties, directives and codes of practice having the force of law in South Africa including the Environmental Laws and the Port Regulations made in terms section 80(1) of the Act, and all judicial decisions, judgements, order of any competent court or the Government and any notifications, instrument or other similar directives made pursuant thereto that have the force of law in the Republic of South Africa, issued by any executive, legislative, judicial or administrative entity in South Africa or by TNPA or the municipality in which the Port is located, and “Law" shall have a corresponding meaning;

"Long Stop Date" means the last Business Day on the 6th (sixth) month after the Scheduled Operations Commencement Date  (as that day may be amended from time to time in terms of this Agreement) being the date by which Operations of Project , must have commenced, failing which TNPA shall be entitled to terminate this Agreement in accordance with the provisions of clause 43 (Terminal Operator Default);

"Losses" means losses, damages, liabilities, claims, actions, proceedings, demands, costs, charges or expenses of any nature in respect of the Project;

"NEMA" means the National Environmental Management Act, 107 of 1998;

"NERSA" means the National Energy Regulator of South Africa;

"New Terminal Operator Agreement" means a contract on substantially the same terms and conditions as this Agreement at the Termination Date,

- however, with, inter alia, the following amendments:

if this Agreement is terminated prior to the Operations Commencement Date, then the Scheduled Operations Commencement Date shall be extended by a period to allow the Successor Terminal Operator to achieve Operation Commencement on or before the extended Scheduled Operations Commencement Date;

any penalties accrued in terms of Schedule [        ] (Penalties) and/or warning notices shall be cancelled;

the term of such contract shall be a period equal to the period from the Termination Date until the Expiry Date; and

any other amendments, which do not adversely affect the Terminal Operator;

"Operation Commencement Date" means the 1st (first) Business Day following the date on which the Completion Certificate in respect of the Project is issued, from which date the Terminal Operator shall commence the operation of the Terminal;

"Operation and Maintenance" means all operation and maintenance activities and obligations of the Terminal Operator in respect of the Terminal, that are required in order to operate the Terminal and for the operation and maintenance of the Terminal Infrastructure and Terminal Equipment in good order and condition including where applicable, in accordance with OEM (original equipment manufacturer) requirements, in accordance with the requirements of this Agreement, the Operational Plan and International Best Practice and the terms "Operate" and "Maintain" shall have corresponding meanings;

"Operating Performance Guarantee" means the irrevocable, on-demand performance guarantee to be issued by such entity as approved by the TNPA on behalf of the Terminal Operator, substantially in the form of the guarantee annexed to this Agreement as per Schedule [        ](Operating Performance Guarantee) for an amount that shall be set on agreement being reached on the relevant Terminal Operator Performance Standards between the TNPA and the Terminal Operator;

"Operational Plan" means the operational plan, specifications and standards in accordance with which the Terminal is to be operated are to be provided and the Operation and Maintenance activities conducted, and the Terminal is to be maintained and upgraded, all of which are detailed in Schedule [     ] (Terminal Operator’s Operational Plan);

"Operating Rights" means all the rights and obligations conferred and imposed on the Terminal Operator in terms of and pursuant to this Agreement in respect of and for the purposes of carrying out the Project;

"Parties" means TNPA and the Terminal Operator and "Party" shall mean either of them as the context may require;

“Payment Expert” means a chartered accountant of not less than 10 (ten) years professional experience or investment banker as agreed to between the Parties, and failing agreement, nominated (at the request of either Party) by the Regional Executive for the time being of the South African Institute of Chartered Accountants: Eastern Region, if the matter relates primarily to a financial matter or financial management matter;

"Performance Guarantees" means the Construction Performance Guarantee, the Operating Performance Guarantee and the Final Maintenance Guarantee;

“Performance Penalties and Incentives” means penalties payable by the Terminal Operator to TNPA for failure to meet or comply with the minimum performance standards and incentives payable to the Terminal Operator by TNPA for achieving performance better than last performance with reference to Schedule 17 (Terminal Operator Performance Standards) and Schedule [  ] (Terminal Operator’s Operating Specifications).”

"Port" means the Port of Ngqura, as promulgated in terms of the Act, and situated at Gqeberha, in the province of the Eastern Cape, Republic of South Africa;

"Port Terminal Security Officer" means a security officer appointed by the Terminal Operator in accordance with the provisions of the ISPS Code and the certificate issued in terms of the ISPS Code in respect of the Terminal;

"Port Infrastructure" means the basic common use structures of the Port of Ngqura, including the Berths, breakwaters, seawalls, channels, basins, quay walls, jetties, roads, railways and infrastructure used for the provision of water, lights, power, sewage and similar services, other than the Terminal Infrastructure;

"Port Regulations" means the regulations made in terms of section 80(1) of the Act;

"Port Rules" means the rules made in terms of section 80(2) of the Act;

"Port Users" means any other Person, other than the Terminal Operator, organisation and/or agency utilizing the facilities of the Port and/or conducting business within the Port limits, including shipping lines, vessel agents, licenced operators, operators of other terminals within the Port and any Subcontractor and/or any third parties authorised to conduct business on behalf of any such Port User;

"Project" means the design, development, financing, construction, operation and maintenance of a liquid bulk terminal at the liquid bulk precinct in the Port of Ngqura for a period of 25 years (twenty-five years);

"Project Documents" means all drawings, data, books, reports, documents, software, source codes and manuals, the Construction Documents and other information, which the Terminal Operator has or have been using and which are necessary for the Construction Works and/or continuing Operation and Maintenance;

"Project Site" means the land described as depicted in Schedule [      ] (Project Site).

"Provisional Operations Certificate" means the certificate to be issued by the Independent Certifier prior to Construction Completion when, in the reasonable opinion of the Independent Certifier, Construction Completion is likely to be achieved by the Construction Contractor by the date specified in the certificate;

"Quarter" or "Quarterly" means a three-month period commencing on 1 April annually and occurring every three months thereafter;

"Rand" or "R" or "ZAR" means the lawful currency of South Africa;

"Real Base Case Project IRR" means the real pre-Tax Project internal rate of return as set out in the Base Case Financial Model;

"Rectification Costs" means for the purposes of any Termination Date that occurs during the Operations Period, an amount equal to the reasonable and proper costs incurred by TNPA in ensuring that the services are available;

"Related Party" means a Person who:

directly, or indirectly through one or more intermediaries, controls, or is controlled by, a person who acquires and holds Equity in the Terminal Operator;

is under common control with any person who acquires or holds Equity in the Terminal Operator; or

any person who acquires or holds  Equity in the Terminal Operator,

where "control" in respect of any person means the power to direct the management and policies of such person, whether through the holding of voting rights or the ability to nominate and/or appoint a majority of the directors or through any contractual arrangement (whether at Law or pursuant to a contractual arrangement) and the term "controlled" has a cognitive meaning;

"Related Party Transaction" means any transaction relating in any way directly or indirectly to the Project in which the Terminal Operator or any Subcontractor of the Terminal Operator leases, transfers or otherwise disposes of any of its properties or assets to, or purchases any property or assets from, or enters into any contract, agreement, understanding, loan, advance or guarantee with, or for the benefit of, a Related Party (other than the Terminal Operator);

"Relevant Authority" means National and/or Provincial legislature, any agency, local authority, department, inspectorate, minister, ministry, official or public or statutory person (whether autonomous or not) having jurisdiction over any or all of the Parties or the subject matter of this Agreement.  A Relevant Authority shall not include any Utility operator or provider;

"Relief Event" means any of the following:

any fire, explosion, tempest, flood, ionising radiation (to the extent it does not constitute an event of Force Majeure), earthquakes, riot and civil commotion, or pressure waves caused by devices travelling at supersonic speed;

(without limiting the obligations of the Private Party regarding service level specifications) any failure by the Institution or any Responsible Authority, utility or other like body to carry out works or provide services;

any accidental loss or damage to the Works and/or the Facilities;

any off-site failure or shortage of power, fuel or transport;

any blockade or embargo which does not constitute an event of Force Majeure;

the discovery of any heritage objects or resources or conditions at the Terminal that could not reasonably have been discovered by proper due diligence, by the Terminal Operator;

any delay in obtaining any Consent; or

any official or unofficial strike, lockout, go slow or other such labour disputes generally affecting the Liquid bulk industry or a significant sector of it,

any breach by the TNPA of any of its obligations under this Agreement (save for any breach that constitutes TNPA Default), and provided that the breach is not caused or contributed to a material extent by the contributory negligence or wilful misconduct of the Terminal Operator or any of its Subcontractors, and any other event that is designated in this Agreement to be dealt with in accordance with clause 39 (Consequences of a Relief Event);

unless any of the events listed in Clauses (a) to (i) inclusive arises (directly or indirectly) as a result of any negligence, wilful conduct or default of the Private Party or any Subcontractor

"Rental" means the rental payable by the Terminal Operator to the TNPA in respect of the grant of the Concession as provided for in Clause 5 (Rental);

"Safety Authorisations" means any consents, license, authorisations, permissions or approvals required to be obtained by the Terminal Operator from any Relevant Authority required in terms of any health and safety Law for the Project;

"SAMSA" means the South African Maritime Safety Authority duly established in terms of South African Maritime Authority Act of 1998;

"Schedules" means the schedules to this Agreement, as amended, replaced and varied from time to time;

"Scheduled Operations Commencement Date" means the date which is specified in the Construction Works Programme as the Day after the date on which the Completion Certificate in respect of the Project is scheduled to be issued and the Terminal operations are due to commence;

"Shareholder" means the holder of Equity in the Terminal Operator;

"Signature Date" means the date on which this Agreement has been signed by both Parties and, if signed on different dates, the last of such dates;

"South Africa" means the Republic of South Africa;

"Subcontractors" means any subcontractor of the Terminal Operator, who has contracted directly with the Terminal Operator in respect of the Project including the Contractor/s;

" Substitute Terminal Operator" means a person duly and properly appointed and approved by TNPA to be the new operator of the Terminal (including, as applicable, the construction and/or Operation and Maintenance of the Terminal) in the place and stead of the Terminal Operator in terms of this Agreement and which:

has the appropriate technical and financial ability to perform the rights and obligations of the Terminal Operator under this Agreement;

employs persons having the appropriate qualifications, experience and technical competence;

has sufficient resources available to it (including financial resources and Subcontracts) to perform the obligations of the Terminal Operator under this Agreement; and

has the same, or more favourable policies to ensure that there is no reduction in BBBEE;

"Supplier Development Plan" means the Terminal Operator's supplier development plan to be annexed to this Agreement as Schedule 10 (Terminal Operator’s Supplier Development Plan) hereto;

"Target Completion Date" means the date by which Construction Completion is, at the Signature Date, intended to occur, which date is specified in the Construction Works Programme;

"Tax" means VAT, any tax, levy, impost, duty or other charge or withholding of a similar nature (including any related penalty or interest);

"Tender" means any tender submitted by a Tenderer that meets the qualification criteria notified under clause 48.2  (Retendering Procedure);

"Tenderer" means a tenderer who is a Suitable Substitute Terminal Operator having submitted a Tender that complies with the requirements of the Request for Proposal issued by TNPA in relation to the New Terminal Operator Agreement;

"Tender Costs" means the reasonable and proper costs of TNPA incurred in carrying out the Tender Process;

"Tender Process" means the process by which TNPA requests tenders from any parties interested in entering into a New Terminal Operator Agreement, evaluates the responses from those interested parties and negotiates the conclusion of a New Terminal Operator Agreement with a Successor Terminal Operator, in accordance with clause 48.2(Retendering Procedure);

"Tender Process Monitor" means a third party appointed by the Terminal Operator under clause 48.2 (Retendering Procedure);

"Terminal" means the land area situated at the Port of Ngqura liquid bulk  Precinct measuring 100 000 m2, including Terminal Infrastructure and Terminal Equipment, from which the Terminal Operator will undertake the Project;

"Terminal Equipment" means the movable assets, including equipment and machinery (whether affixed to the Project Site or not) that are required in order to operate the Terminal as is more fully described in Schedule 7A of this Agreement;

"Terminal Infrastructure" means the land based structures, including storage facilities, loading facilities, Terminal buildings, sheds, surfacing, and all other fixed and movable improvements to the Project Site or adjacent to the Project Site, that are required in order to operate the Terminal operate the Terminal as well as the internal network for the provision of water, lights, power, sewerage and similar services within the Project Site boundaries, all of which shall be designed and Constructed in accordance with the Detailed Design and the D&C Specifications;

"Terminal Operator" means {PREFFERED BIDDER}

"Terminal Operator Financial Year" means the financial year of {PREFERRD BIDDER}, which runs from 1 April to 31 March annually;

"Terminal Operator Performance Standards" means the minimum performance standards specified in Schedule [     ] (Terminal Operator Performance Standards) which shall take account of and be based upon the Business Case, and which shall include performance targets in respect of the operation of the Terminal at the Terminal expressed as volume throughout targets;

"Termination Amount" means the amount payable on termination of this Agreement in terms of Part VII;

"Termination Calculation Expert" means an accountant of not less than 10 (ten) years professional experience or investment banker agreed to between the Parties, and failing agreement, nominated (at the request of either Party) by the President for the time being of the South African Institute of Chartered Accountants: Eastern Cape, if the matter relates primarily to a financial matter;

"Termination Date" means the date on which this Agreement is terminated in accordance with its terms, other than by way of effluxion of time;

"Termination Date Discount Rate" means a discount rate expressed as:

(1+ Real Base Case Project Internal Rate of Return + Bond B – Bond A)* (1+ i) – 1,

where:

"i" is the agreed assumed forecast rate of increase in the South African Reserve Bank’s prevailing long-term inflation target;

"Bond A" is the real yield to maturity on a benchmark government bond instrument of the same or closest possible maturity as the average life of the Debt as at the Commencement Date; and

"Bond B" is the real yield to maturity on a benchmark government bond instrument of the same or closest possible maturity as the average life of the Debt as at the Termination Date;

"TNPA" means the Transnet National Ports Authority, an operating division of Transnet, established in terms of the Act, and/or its successor/s in title;

"TNPA Policies" means TNPA policies, operating manuals, operating conditions and rules as set out in Schedule [       ] (TNPA Policies, Manuals and Operating Conditions);

"TNPA Approval Date" means the date on which the TNPA accepts and approves the Terminal Operator’s feasibility studies, technical reports and associated business and operational plans as provided for in clause 3;

"TNPA Financial Year" means the financial year of TNPA, which runs from 1 April to 31 March annually;

"Transnet" means Transnet SOC Ltd, registration number 1990/000900/30, as incorporated pursuant to the Legal Succession to the South African Transport Services Act, 9 of 1980;

"Unforeseeable Conduct" means such conduct that shall occur if, after the Signature Date, TNPA or any Relevant Authority takes any action (including the introduction, application, or Change in Law, regulation, by-law or order having the force of Law) or fails to carry out its obligations as prescribed by Law:

the principal effect of which is directly borne by:

the Project and no other similar transactions;

the Terminal Operator and no other persons;

parties undertaking port facility operations and no other persons;

in respect of which the Terminal Operator is not entitled to any other relief pursuant to any other provisions of this Agreement;

which was not foreseen by the Terminal Operator on or before the Signature Date; and

which could not reasonably have been foreseen by any person in the position of the Terminal Operator on or before the Signature Date;

- provided that:

Unforeseeable Conduct shall be deemed not to have occurred in circumstances where any action or omission of TNPA or Relevant Authority is in direct response to any act or omission of the Terminal Operator which is illegal (other than an act or omission rendered illegal by virtue of such conduct of TNPA or Relevant Authority) or in violation of agreements to which the Terminal Operator is a party;

an increase in Taxes of general application which does not discriminate against TNPA or against TNPA and other parties undertaking similar transactions shall be deemed not to be Unforeseeable Conduct;

Unforeseeable Conduct shall be deemed not to have occurred if such conduct by TNPA or any Relevant Authority is required as a result of an event of Force Majeure and is reasonably proportionate thereto; and

Unforeseeable Conduct shall be deemed not to have occurred in the circumstances where the principal effect of any action or omission of a Relevant Authority is directly borne by both TNPA and the Terminal Operator;

"Uninsurable" means in relation to a risk, either that:

the required insurance is no longer available in the worldwide insurance market from reputable insurers; or

if the required insurance is available, the insurance premium payable for insuring that risk has increased to such a level that the risk is not generally being insured against in the South African insurance market on commercially acceptable terms;

"Updated Financial Model” means the Base Case Financial Model as amended and updated from time to time;

"Utilities" means all port infrastructure serving the public and Port Users such as water, electricity, sewage, gas and telecommunications and where appropriate includes the relevant provider thereof;

"Valuer" means a Property Valuer registered with the South African Council for the Property Valuers;

"VAT" means the value-added tax levied in terms of the Value Added Tax Act No.89 of 1999.

In this Agreement, unless inconsistent with the context, words referring to:

one gender includes a reference to the other genders;

the singular includes the plural and vice versa;

natural persons include juristic persons and vice versa.

When a number of Days is prescribed in this Agreement, such number shall be calculated including the first and excluding the last Day, unless the last Day falls on a Day that is not a Business Day, in which case, the last Day shall be the first succeeding Day which is a Business Day.

Any Schedules to this Agreement shall be deemed to form part of this Agreement. Those Schedules that are not available as at Signature Date shall be annexed to this Agreement as soon as they have been signed by the delegated representatives of the Parties and will form an integral part of this Agreement. If there is a conflict between the provisions of a Schedule and the provisions of this Agreement, the provisions of this Agreement shall prevail.

Any reference to legislation, a statute, a statutory instrument, or a standard in this Agreement shall be a reference to such legislation, statute, statutory instrument or standard as amended, replaced, varied or re-enacted from time to time.

Words and expressions defined in any sub-clause shall, for the purpose of the clause of which that sub-clause forms part, bear the meaning assigned to such words and expressions in that sub-clause.

If any provision in a definition is a substantive provision conferring rights or imposing obligations on any party, effect shall be given to it as if it were a substantive clause in the body of the agreement, notwithstanding that it is only contained in the interpretation clause.

Any reference in this Agreement to another agreement shall be to such agreement as amended, supplemented, varied, novated, or replaced from time to time in accordance with its terms and conditions.

Titles of clauses and Schedules of and to this Agreement are inserted for the sake of convenience only and shall not be used in respect of or in any way affect the interpretation of any provision of this Agreement.

A reference in this Agreement to any Person shall be a reference to such Person's permitted successor, transferee, cessionary and/or delegatee.

Any reference in this Agreement to the Updated Financial Model shall, unless the context requires otherwise, be a reference to such document as most recently updated, amended, or replaced and approved by TNPA, in accordance with the terms of this Agreement.

Where this Agreement requires that the waiver, consent, approval, or permission of TNPA is to be obtained:

such waiver, consent, approval, or permission shall at all times be required to be obtained by the Terminal Operator prior to undertaking or failing to undertake the course of action to which such waiver, consent, approval or permission pertains; and

the granting or withholding of such waiver, consent, approval or permission shall not be valid unless it is issued in writing by TNPA.

The terms "holding company" and "subsidiary" shall have the meanings ascribed to them in the Companies Act.

The term "Person" shall mean a natural person, partnership, firm, corporation, joint stock company, trust, unincorporated association, joint venture, government body, limited liability company, close corporation, any sphere of government (including national, provincial, regional and local government, or organ of state) or any other legal entity which is considered a legal entity under the laws of South Africa or the country in which such an entity has been formed.

References in this Agreement to TNPA, the Terminal Operator, the Independent Certifier, shall include their respective authorised agents and representatives.

Any provision of this Agreement that contemplates or provides for performance of an obligation or compliance with a provision of this Agreement subsequent to any termination of this Agreement shall survive termination of this Agreement and shall continue in force and effect for the period contemplated in said provision.

Termination of this Agreement shall not affect and shall be without prejudice to the accrued rights, obligations, claims, duties, and liabilities of either Party which such accrued rights, obligations, claims, duties and liabilities arose prior to such termination.  For the avoidance of doubt, such rights, claims and liabilities shall include any rights of a Party in respect of an antecedent breach or non-performance by either Party of any of the terms or conditions of this Agreement.

The eiusdem generis rule and the contra proferentem rule shall not be applicable to this Agreement.

- Introduction

In terms of the Act, TNPA exercises authority, power, control, and responsibility in respect of commercial Ports of South Africa, including the Port of Ngqura. In addition, certain powers, capacity, and Authority have been conferred on TNPA, as a division of Transnet, in respect of the Port by the Act.

The Terminal Operator has been authorised to enter into this Agreement with the TNPA, for the Port, following the conclusion of an open, fair, transparent, and competitive bid process in accordance with the provisions of Section 56 of the  Act 12 of 2005;

In terms of this Agreement, the TNPA appoints the Terminal Operator who shall design, develop, finance, construct, operate and, maintain a liquid bulk terminal within the liquid bulk precinct at the Port for a period of 25 (twenty-five years).TNPA requires the said project  to be designed, constructed, equipped, operated and maintained, in accordance with the standard of a Reasonable and Prudent Operator and International Best Practice.

- Commencement, Duration and Concession Period

Save for the provisions of this clause  and clause 1,8, 9, 12,14, 14.3, 15, 47.6, 52, 55, 56, 57, 58 and 59,which shall come into effect immediately upon signing of this Agreement ("Immediately Operative Provisions") , this Agreement shall not come into force and effect until the suspensive conditions set out below are fulfilled or waived as the case may be, within a period of  24 (Twenty Four)  months from the Signature Date, or such later date as the Parties may agree to in writing prior to the expiry of the said period of 24 (Twenty Four) months  ("the Fulfilment Date"):

the Terminal Operator obtains all necessary Consents for the Works and the Operations and Maintenance of the Terminal, including but not limited to an Environmental Authorisations and consents required in terms of NERSA Legislation (other than a tariff determination by NERSA);

the Terminal Operator has concluded the Construction Agreement, and such agreement has become unconditional in accordance with its terms except to the extent that any conditions contained therein relating to the effectiveness of this Agreement;

the Construction Agreement, the Works Programme, the Detailed Design and D&C Specifications have been approved by the Independent Certifier in accordance with the provisions of clause 28.1(Performance of the Detailed Design) where applicable;

the Terminal Operator has undertaken an insurance due diligence assessment and has obtained (i) an insurance report which confirms that the Project Insurance is appropriate for the Terminal as well as the obligations of the Terminal Operator and (ii) a letter of undertaking from an insurance broker confirming that the Project Insurances are available in the market and that the Terminal Operator qualifies for such Project Insurances; and

the Parties have agreed to Schedule [     ](Business Case Financial Model), Schedule [  ] (Terminal Operator’s Operating Specifications), Schedule [     ] (D&C Specifications) where applicable, Schedule [   ] (Base Case Financial Model), Schedule [   ] (Penalties), Schedule [    ] (Project Insurance), and Schedule [      ] (Annual Reporting).

The Parties shall co-operate and shall use all reasonable endeavours to procure the fulfilment of the suspensive conditions in this clause. Each Party shall promptly inform the other Party, in writing, when the suspensive conditions for which it is responsible have been satisfied.

Unless the suspensive conditions contained in this clause, are fulfilled or where applicable, waived, as the case may be, on or before the Fulfilment Date, the provisions of the Immediately Operative Provisions shall continue to be of full force and effect, but the remainder of this Agreement shall not become operative or effective and shall have no force or effect whatsoever.

No Party shall have any claim, unless explicitly set out in this Agreement, against any other Party pursuant to the non-fulfilment of the suspensive conditions in this clause, save where a Party (the "Guilty Party") has breached the terms of this clause and/or has deliberately frustrated the fulfilment of such condition or intentionally caused that condition not to be fulfilled, in which event the Guilty Party shall be liable to the other Party for such damages as such other Party may have suffered thereby.

Commencement and Duration

This Agreement shall commence on the Signature Date and shall endure for the Concession Period until the earlier of the Termination Date or the Expiry Date.

Notwithstanding the provisions of clause 3.5.1 above, it is expressly recorded that the Terminal Operator may only commence with any part of the Project on the first business day following the TNPA Approval Date and for the avoidance of doubt, by which time the Terminal Operator shall have completed and submitted to the reasonable satisfaction of the TNPA the following information, including but not limited to:

SHE Risk Assessment and Plans;

Civil and Bulk Services Studies;

Navigation and Mooring Study;

HAZOP Studies;

Environmental Impact Assessment and related environmental authorisation;

The Terminal Operator obtaining and submitting to the TNPA a resolution from its Board of Directors and/or the Shareholder (if applicable) approving and accepting the terms of this Agreement.

- Appointment of Terminal Operator and Grant of Rights

Grant of Rights

TNPA hereby grants the Concession in favour of the Terminal Operator to undertake the Project on the Project Site, on the terms and conditions contained in this Agreement. The Terminal Operator accepts such appointment on the terms and conditions contained in this Agreement.

Subject to the provisions of this Agreement and with effect from the Effective Date, the Terminal Operator is hereby granted an exclusive right to undertake the Project on the Project Site until the expiry or earlier termination of this Agreement in accordance with its terms.

The Terminal Operator shall be entitled to use the Port Infrastructure that is within the Project Site and the quay that serves the Project Site including the land on which the Terminal Operator operates a pipeline. In the event that the pipeline shall traverse a portion of port land that lies outside the Project Site, then the provisions of a separate wayleave agreement shall apply.

Terminal Operator's Obligations

The Terminal Operator shall undertake the Project at its own cost and risk in accordance with the terms of this Agreement. TNPA shall not provide any guarantee, subsidy, grant or any financial support of any nature to the Terminal Operator or in respect of the Project, the Terminal or this Agreement.

The Terminal Operator shall at its own cost maintain the Certifications, if applicable, for the duration of the Concession Period.

This Agreement shall not be interpreted as granting the Terminal Operator any rights or imposing any obligations or duties on TNPA or any Relevant Authority, except as expressly and specifically stated in this Agreement.

No instructions or approvals given by TNPA or any Relevant Authority in accordance with the Law and this Agreement in respect of any aspect of the Project or the Terminal will affect, alleviate, excuse, or provide relief from the Terminal Operator's duties, obligations, liabilities and responsibilities under this Agreement and in respect of the Project.

Subcontracting

Regardless of the fact that this Agreement permits or requires the Terminal Operator to appoint third parties to perform part of the Project, such appointment shall not relieve or excuse the Terminal Operator of any duty, obligation, liability or responsibility under this Agreement and in respect of the Project. Accordingly, for the avoidance of doubt,  the cession and transfer of Operating Rights shall not be permitted.

The Terminal Operator shall be responsible for the management and supervision of any third parties appointed by it to perform any part of the Project.  The Terminal Operator shall be and shall remain, at all times, fully responsible and liable for the actions and omissions (whether negligent, wilful or intentional) of all such third parties and of the agents, representatives and employees of such third parties, whether such third parties are employed directly or indirectly by the Terminal Operator.

Nothing in this Agreement is intended to create or should be interpreted as creating any privity of contract between TNPA and any third parties appointed by the Terminal Operator to perform any part of the Project. The Terminal Operator shall ensure that a provision to this effect is inserted into every contract entered into by it with such a third party.

General Rights and Obligations of the Terminal Operator

Use of Terminal and Project Site, No Alienation or Encumbrance and Site Condition

      - In accordance with the terms of this Agreement, the Terminal shall be used solely, for undertaking the Project, at the Terminal Operator’s own cost and risk and for no other purpose whatsoever.

TNPA shall not, provide any guarantee, subsidy, grant or any financial support of any nature to the Terminal Operator or in respect of the Project, the Terminal or this Agreement.

      - The Terminal Operator shall be entitled to carry out tasks and activities that are reasonably necessary for and incidental to undertaking the Project.

      - In the event that the Terminal Operator wishes to make use of the Terminal for any other purpose, other than liquid bulk terminal operations, it shall not do so, unless the prior written consent of TNPA has been obtained and if deemed necessary by the TNPA.

      - The Terminal Operator shall not lease, sell, dispose of, or otherwise alienate or encumber the whole or any portion of the Project Site or the Terminal in any manner whatsoever.

      - The Terminal Operator shall not use the Terminal for residential purposes or as sleeping quarters, except if the Terminal Operator elects to provide accommodation facilities or if TNPA authorises (in writing) the use of a portion of the Terminal as sleeping quarters for operational or security purposes, which authority shall not be unreasonably withheld.

      - The Terminal Operator shall not do or cause anything to be done that may cause a nuisance to TNPA or to any other Port User or the occupants of adjoining properties.

      - The Terminal Operator shall not do anything that materially detracts from the appearance or safe Operation and Maintenance of the Terminal, the Terminal Infrastructure, or the Terminal Equipment.

      - The Terminal Operator acknowledges and agrees that the Terminal Operator has inspected the Project Site and has satisfied itself fully as to the location, condition, geotechnical characteristics and features, zoning, ownership, existing Encumbrances, nature and extent of the Project Site as well as any and all Consents already granted to or held by TNPA in respect of the Project Site and the Terminal Operator expressly records and agrees that TNPA does not warrant the suitability or otherwise of the Project Site for purposes undertaking the construction, Operation and/or Maintenance of the Terminal or for purposes of operating the Terminal and that the Terminal Operator shall have no claims whatsoever against TNPA in respect of the location, condition, geotechnical characteristics and features, zoning, ownership, existing Encumbrances, nature and extent of the Project Site as well as any and all Consents already granted to or held by TNPA in respect of the Project Site.

Construction of  Terminal Infrastructure and Equipment

The Terminal Operator shall undertake the Construction Works (including the design, procurement, construction, installation, commissioning and testing of the Terminal Infrastructure and the Terminal Equipment) in respect of the Terminal, which shall include the following:

the Construction and installation of all Terminal 	Infrastructure in accordance with the Detailed 	Design, the D&C Specifications, International 	Best Practice and the terms and conditions of this 	Agreement, including but not limited to:

all infrastructure required to operate the Terminal excluding Port Infrastructure;

basic services infrastructure within the Project Site in respect of water, electricity, sewerage, and storm water 	reticulation;

hard surfacing;

restrooms;

roads and parking areas;

lighting (i.e., high mast) enabling 24/7 operations;

perimeter fencing and entrance gate/s;

security kiosk/s;

firefighting capability as required (based on the type and volume of products handled at the Terminal);

electrical sub-station/s linked to maximum demand;

appropriate signage;

The procurement, installation, testing, and commissioning of all Terminal Equipment in accordance 	with the Detailed Design, the D&C Specifications, 	International Best Practice and the terms and conditions 	of this Agreement;

subject to obtaining the prior written approval of TNPA, the construction and alterations to the quayside for the 	installation of the Terminal Infrastructure;

any other construction activities necessary in 	accordance with the Detailed Design and the D&C 	Specifications.

Without limiting the other obligations of the Terminal Operator in this Agreement or which are imposed on it by Law, the Terminal Operator shall:

        - bear full responsibility to comply with conditions of the Environmental Authorisation;

        - bear full responsibility to apply for and obtain the required Consents which may be required to enable it to undertake the Construction Works (including the design, finance, procurement, construction, installation, commissioning and testing of the Terminal Infrastructure and the Maintenance of the Terminal, and the operation of the Terminal (as envisaged above); and

        - ensure that if any of its Contractors, or other Subcontractors, agents and service providers require a licence in terms of the Act or any applicable law, such persons shall be duly licensed at all times.

Operation of the Terminal

      - The Terminal shall, be used, managed and operated on a common-user basis and on an equal footing, meaning that:

The Terminal Operator shall have the right to operate the Terminal and shall provide reasonable equality of access to the Terminal in respect of uncommitted capacity to Terminal users and potential Terminal users wishing to utilise the services of the Terminal;

The Terminal Operator shall not unreasonably discriminate, in its tariff structure or in its trading conditions (including but not limited to all commercial terms and conditions) between various users or potential users of the Terminal and the Loading Facilities; and

Port Users have on a first come, use it or lose it basis, open access to the Terminal and the Loading Facilities available and uncommitted in accordance with any relevant and applicable legislation;

Without limiting the other obligations of the Terminal Operator, as specified in this Agreement, or imposed by Law, the Terminal Operator shall be obliged to manage and operate the Terminal for the purpose of:

providing reliable, secure and efficient services and facilities to Port Users;

receiving Cargo at the Project Site via Berth.

storage of Cargo in storage tanks;

transferring Cargo from the Terminal via Pipelines on Pipeline racks  to the storage tanks;

transferring Cargo from the vessel into the storage tanks for distribution and/ or transfer of Cargoes from the storage tanks into the vessel;

preparation of all necessary documentation associated with the shipment of Cargoes, and their inland transport	to/from the Port;

submit reports in respect of all cargo exported, landed and shipped by the Terminal Operator on a per vessel basis, 72 (seventy-two) hours subsequent to the vessel having entered the Port;

performing maintenance related activities within the Terminal that the Terminal Operator may deem necessary;

obtaining, maintaining and renewing all documents, permits or other authorisations necessary to operate the Terminal and render the services and perform the activities referred to in this clause;

ensuring that if any sub-contractors, Agents and service providers used by it that require a document in terms of the Act, such persons are duly licensed at all times;

providing, maintaining or replacing, according to International Best Practice, all operating and other equipment necessary for the efficient operation of the Terminal;

procuring, installing and operating communication, control and administrative systems necessary for the efficient operation of the Terminal;

complying with all applicable provisions of the Act, the Port Rules, the Regulations and any directives issued in terms of the Act;

complying with "SAMSA", including any applicable Legislation and codes relating to safe working practices;

complying with the ISPS Code and the IMDG Code in relation to security and dangerous goods, respectively;

complying with all other applicable Legislation and generally conduct its activities and operations in accordance with the Law; and

anything reasonably necessary or incidental thereto.

- 4.4.3.3.	For the avoidance of doubt, all the obligations of the Terminal Operator set out in this clause 4.4 and under this Agreement in its entirety, shall be in compliance with the IMDG Code as the context requires. In the event that the Terminal Operator contravenes the applicable IMDG Code, such contravention shall constitute a breach of this Agreement by the Terminal Operator. The Terminal Operator shall be fully conversant with the requirements of the IMDG Code in respect of the handling of Cargo and should in particular take note of the classification applied in the regulation of the handling practices required for the duration of this Agreement.

      - The Terminal Operator may not:

- 4.4.3.4.2.	permit the growth upon the Terminal of noxious weeds;

- 4.4.3.4.3.	do or cause anything to be done that may cause a nuisance to TNPA or to any other Port User or the occupants of adjoining properties;

- 4.4.3.4.4.	do anything that materially detracts from the appearance of the Terminal; or

- 4.4.3.4.5.	load vehicles in any area within the Port, other than in the 		Terminal, unless with TNPA's prior written consent or with 		permission from another person legally in control of the area 		which shall not be unreasonably withheld.

The Terminal Operator shall take all reasonable steps to prevent the spilling of Cargo and/or any other matter into the Port’s water. The Terminal Operator shall:

immediately notify TNPA if any Cargo and/or any other matter is spilled in the water as a result of its operation of the Terminal or the conduct of its employees, Agents, service providers, sub-contractors or persons responsible for the vessels calling at the Terminal; and

immediately take steps to recover such cargo or any other matter.

If the Terminal Operator fails to recover any spilled cargo or any other matter as envisaged above, TNPA may take whatever steps are necessary to recover the cargo or any other matter and to claim the costs of taking such steps from the Terminal Operator.

The Terminal shall be used solely for the services and activities described in this Agreement for purposes incidental to the provision of those services and activities, and for the exercise of the rights and the fulfilment of the obligations set out under this Agreement, and for no other purpose whatsoever unless the prior written consent of TNPA which consent shall not be unreasonably withheld has been obtained, in terms of this Agreement, for such other purpose.

Terminal Operator’s Replacement, Repair, Operation and Maintenance Obligations

The Terminal, the Terminal Infrastructure, the Terminal Equipment as well as the surface of the quay within the Project Site and any other equipment that is necessary for the safe and efficient Operation and Maintenance of the Terminal, shall be Operated and Maintained by the Terminal Operator at its own cost, and kept in good working order and condition and in a safe operating condition and  in accordance with the Terminal Operator’s Operational Plan, agreed Terminal Operator Performance Standards, International Best Practice and  all relevant and applicable Laws as well as any applicable national standards, specifications and codes of practice which are generally applied in South Africa in relation to such Operation and Maintenance.

The Terminal Operator shall be responsible for repairs, renewals and replacement of the Terminal Infrastructure and the Terminal Equipment as is necessary for the continued and efficient operation of the Terminal.

The Terminal Operator shall procure, install, commission, test, Operate and Maintain appropriate communications, safety, control and administrative systems and equipment as are necessary for the safe and proper use, Operation and Maintenance of the Terminal in accordance with Detailed Design, the Operational Plan, and the Terminal Operator Performance Standards, the IPMS and International Best Practice.

The Terminal Operator shall provide TNPA with an annual maintenance programme for the Terminal Infrastructure and a replacement programme for the Equipment, at least 2 (two) months prior to the start of each of the Terminal Operator’s Financial Years.

The Terminal Operator shall to the extent that the relevant service, at the Terminal is not provided by the relevant local authority in the ordinary course as envisaged in clause 22.6, the Terminal Operator shall be responsible, at its own cost, for the disposal of garbage and waste, including garbage and waste generated by vessels visiting the Terminal and by the Terminal itself.

The Terminal Operator shall keep the Terminal and the Project Site in a clean, orderly and sanitary condition.

The Terminal Operator shall attend to removal of intrusive vegetation including regular control and removal of grass, noxious and other weeds, and other plants and vegetation on the Project Site (save for any landscaped gardens which may be provided for in the Detailed Design).

The Terminal Operator shall, in the Operation and Maintenance of the Terminal comply with all other applicable Laws (including all labour related Laws) the Port Rules, the Port Regulations, TNPA Policies, any directives issued in terms of the Act, and generally, conduct its activities and operations at the Terminal in accordance with all applicable Laws.

The Terminal Operator shall conduct annual inspections of the Terminal and must incorporate the outcome of each such annual inspection in the Annual Report as provided for in clause 31 (Reporting Requirements) hereof. The Terminal Operator shall provide TNPA with a maintenance and replacement programme for the Terminal Infrastructure and Terminal Equipment, in accordance with the clause 31 (Reporting Requirements).

Erection of Improvements and Extensions of Terminal Infrastructure

The Terminal Operator shall be entitled to make, or cause to be made in the Terminal or in respect of the Terminal Infrastructure such improvements, alterations, additions and/or extensions as may be necessary or appropriate for the operation of the Terminal, the Operation and Maintenance of the Terminal upon the Project Site, provided that any improvements, alterations, additions and/or extensions which are not envisaged or provided for in the Detailed Design and/or the Construction Works Programme shall only be undertaken by or on behalf of the Terminal Operator after it has first submitted the plans, designs and specifications thereof to TNPA and has obtained the prior written approval of TNPA which approval shall not be unreasonably withheld.

Unless otherwise agreed in writing by the Parties or otherwise expressly provided for in this Agreement, all improvements, alterations, additions and/or extensions envisaged in clause 4.6.1 shall be undertaken by the Terminal Operator at its own cost and TNPA shall not be liable to compensate the Terminal Operator for improvements, alterations, additions and/or extensions which are effected to the Terminal (including the Terminal Infrastructure) whether or not such  improvements, alterations, additions and/or extensions are effected pursuant to and with the prior approval of TNPA in terms of clause 4.6.1 and the value of such any and all such improvements, alterations, additions and/or extensions  shall not be deducted from or set-off by the Terminal Operator against, or otherwise form the substance of counterclaim by the Terminal Operator or in other manner whatsoever affect or detract from any amounts which are or may become payable by  the Terminal Operator to TNPA in terms of this Agreement.

Roadways, Surfaces and Access to and Egress from the Terminal

The Terminal Operator shall not load vehicles (including a car or truck or tracked or wheeled equipment) in any area within the Port, other than in the Terminal, unless with the TNPA's prior written consent or with permission from another person legally in control of the area which consent shall not be unreasonably withheld.

The Terminal Operator shall, at its own cost, Operate and Maintain in good order and condition, all existing roads within the Project Site and shall construct Operate and Maintain in good order and condition all roadways and surfaces as may be required within the Terminal for the operation of the Terminal and the performance of the activities and obligations contemplated in this Agreement. Such roadways and surfaces shall be constructed Operated and Maintained in accordance with all applicable Laws, the Detailed Design and the Operational Plan and in accordance with a standard that complies with the permissible axle loads for the types and volumes of Cargo and traffic which will use the roads which is envisaged in the Business Case, Operational Plan and the Detailed Design, and in the absence of the provision of such standards at such standard as is stipulated by TNPA and communicated to the Terminal Operator in writing.

The Terminal Operator shall ensure that all vehicles entering and exiting the Terminal shall be organised to minimise traffic congestion, the parking of vehicles and any queuing outside the Project Site. To the extent that the weighing of vehicles entering and exiting a port Terminal in order to load or unload cargo is required by any Law, the Terminal Operator must check the weight of vehicles entering and exiting the Terminal.

TNPA’s duly authorised agents, employees and contractors shall have the right of access to the Terminal for purposes of performing TNPA's functions, provided that TNPA ensures that its agents, employees and contractors comply with all reasonable safety and security stipulations, environmental and Project Site rules of the Terminal Operator whilst in the Terminal.

All other persons, vehicles and equipment shall have access to the Terminal and may use the roadways and the surfaces in the Terminal in the manner reasonably determined by the Terminal Operator in order to conduct normal legal business related to the Operation of the Terminal, provided that in the use of such roadways such persons, vehicles and equipment shall not unnecessarily interfere with or impede the activities of the Terminal Operator and shall comply with all the safety and security stipulations, environmental and Project Site rules of the Terminal Operator.

The Terminal Operator may not impose any fee for admission to the Terminal.

Spillage

The Terminal Operator shall take all reasonable steps to prevent the spilling or dropping of Cargo and/or any other matter into the Port’s water. The Terminal Operator shall:

immediately notify TNPA if any Cargo and/or any other matter is spilled or dropped in the water as a result of its operation of the Terminal or the conduct of its employees, agents, service providers, Contractors, Subcontractors or persons responsible for the vessels calling at the Terminal; and

immediately take steps to recover such Cargo or any other matter.

If the Terminal Operator fails to recover any spilled Cargo or any other matter as envisaged above, TNPA may take whatever steps are necessary to recover the Cargo or any other matter and to claim the reasonable costs of taking such steps from the Terminal Operator.

General Safety and Security in the Terminal

- Without detracting from the provisions of clauses 24 (Health and Safety) and 25 (Security), the Terminal Operator shall be responsible for the safety and security of the Terminal and for all persons and movables therein, including Cargoes, and for the implementation of and adherence to the ISPS Code, and accordingly the Terminal Operator shall:

ensure that the perimeter of the Terminal is fenced with security fencing of a standard reasonably acceptable to TNPA and which is in compliance with the ISPS Code and that such fencing is maintained at that standard (and repaired as necessary) during the term of this Agreement;

as part of the security plan envisaged in clause 25 (Security), monitor and control all Cargo, vehicles and people entering and leaving the Terminal as part of the Terminal security plan, and ensure that security communications are always readily available;

comply with all applicable provisions of the Act, the Regulations, the Port Rules, prevailing security and safety requirements of the TNPA (including requirements relating to access to and exit from the Project Site), and any directives that may be issued in terms of the Act, from time to time;

comply with the requirements of the Port Regulator (established in terms of the Act);

comply with the provisions and requirements of the South African Maritime Safety Authority ("SAMSA"), including any applicable legislation and codes relating to safe working practices;

comply in all material respects with the provisions of the International Maritime Organisation Convention of Safety and Security at Sea, the ISPS Code and the Maritime Security Regulations 2004, adopted under the Merchant Shipping Act No 57 of 1951; and

comply with the IMDG Code in relation to security and dangerous goods.

Personnel, Contractors, and other Subcontractors - Generally

The Terminal Operator as well as its Contractors and other Subcontractors shall comply with all relevant labour Laws.

The Terminal Operator as well as its Contractors and other Subcontractors shall at all times employ or engage sufficient and suitably qualified and competent personnel to enable it to efficiently operate the Terminal and Operate and Maintain the Terminal, all envisaged in the Terminal Operator Agreement.

The Terminal Operator shall implement all measures as are required by the relevant applicable Laws and/or as may be reasonably necessary to ensure the safety of its employees and that of its Contractors and other Subcontractors, and shall provide them or ensure they are provided, free of charge, with any necessary personal protective clothing and equipment and shall ensure that its Contractors and other Subcontractors do likewise.

The Terminal Operator accepts full responsibility for the training of staff and shall ensure that all its employees are properly trained for the work they are undertaking and are familiar with safety and security requirements that apply to the Terminal and shall ensure that its Contractors and other Subcontractors do likewise.

TNPA may require the Terminal Operator to remove any employee, agent, representative,  Contractor/s or other Subcontractor, or any of their respective employees, agents or representatives, from the Terminal or to prevent such employees, agents or representatives, Contractors or other Subcontractors from entering the Terminal, if any such employees, agents or representatives, Contractors or other Subcontractors engage in any conduct which might threaten public health, or the safety or security of the Port or other Port User.

- Duration of the Concession Period

The Concession shall endure for an initial operating period of 25 (twenty-five) years with a non-automatic option to renew up to a maximum period of a further 25 years as may be negotiated and agreed to between the Terminal Operator and the TNPA.

The Terminal Operator shall be obliged to give written notice by no later than the 20th year of the initial operating period of the Terminal Operator Agreement, of its intent to seek a renewal of the Terminal Operator Agreement.

The Development Period shall commence on the first Business day following the Effective Date and shall expire 24 months from the first Business day following the Effective date.

The Construction Period shall commence on the Effective Date and shall terminate on the issue of the Completion Certificate.

The Operations Period shall commence on the Actual Operations Commencement Date.

- Concession Fees

The Terminal Operator shall pay to TNPA, in consideration of the right to use the Terminal for the purpose set out in this Agreement :

the sum of [                     ]per square meter, per month for [        ] [                            ] square meters,  during the Construction Period;

the sum of R[                     ] per square meter, per month for [              ] square meters, being that portion of the Project Site where buildings are situated, during the Operations Period;

The amounts payable by the Terminal Operator in terms of clauses 6.1.1  and 6.1.2, shall be paid monthly in advance, by no later than the 7th (seventh) Day of each month.

For the period commencing on signature date of the Terminal Operator Agreement, the monthly Rental amount shall be escalated by TNPA on each anniversary of such date at an escalation rate of              (           percent).,

Except if TNPA otherwise agrees in writing, all payments shall be made in South African Rands;

All payments to be made in terms of this Agreement by the Terminal Operator to TNPA shall be made in full without set-off or counterclaim in immediately available funds, free of bank exchange or any other charges or deductions, electronically into the following bank account: RMB Corporate Bank, A Division of FirstRand Bank Limited , Account name: Transnet National Ports Authority, Type: CORPORATE CASHMAN ACCOUNT, Account Number 62875771315:  branch Code: 255005;

TNPA shall be entitled in its sole and absolute discretion to appropriate or re-appropriate any amounts received from the Terminal Operator towards the payment of any other amounts owing by the Terminal Operator to it;

TNPA shall have the right to apply the whole or portion of the rental towards the payment of any amounts owing by the Terminal Operator, when any such amount has not been paid within 15 (fifteen) Business Days of written notice requesting such payment that is due and payable.

- Ownership and eventual handover of the Project Site and the Terminal Infrastructure

The Terminal Operator agrees and acknowledges that the ownership of the Project Site shall at all times vest in TNPA and nothing in this Agreement shall be construed as transferring ownership to the Terminal Operator.

The Parties agree that ownership of the Terminal Infrastructure and Terminal Equipment shall remain vested in the Terminal Operator, save where expressly stated to the contrary.

The Terminal Operator hereby grants to TNPA the first option to purchase the Terminal Equipment on the following terms and conditions:

the option shall be exercisable by written notice given by the Terminal Operator to the TNPA at any time between the date on which notice of termination of this Agreement is given by either Party to the other in terms of this Agreement and the Termination Date and at least two (2) years prior to the Expiry Date;

the purchase price for the Terminal Equipment shall be its fair value as agreed by the Terminal Operator and TNPA as at the Termination Date;

the Parties shall use their reasonable endeavours to agree the purchase price and complete the transfer of the Terminal Equipment to the TNPA within 30 days after the Termination Date and/or Expiry Date, failing which the TNPA shall be deemed not to have exercised the option, and the option shall no longer be capable of being exercised.

At least 2 (two) Contract Years prior to the expiry of the Operations Period, TNPA shall notify the Terminal Operator whether it is required to demolish and remove all or some of the Terminal Infrastructure. Should TNPA notify the Terminal Operator to demolish and remove all or some of the Terminal Infrastructure, the Terminal Operator shall decommission, demolish and remove all or the selected Terminal Infrastructure during the Decommissioning Period.

Upon the termination for any reason or expiry of the Operations Period or subject to clause  7.4, (the “Decommissioning Period”), the Terminal Operator will be required to:

give free and vacant possession of the Terminal, the Project Site, the Terminal Infrastructure and subject to clause 7.3, the Terminal Equipment to TNPA;

hand over all associated manuals, certificates and documents in respect of the Terminal Infrastructure and the Terminal Equipment, if applicable;

leave the Project Site in a safe, clean and orderly condition in accordance with the terms and conditions contained in this Agreement.

Subject to clause 7.3, the Terminal Operator shall not be entitled to payment of any monies in connection with such delivery referred to in clause 7.5.

- Indemnity

Subject to clauses 8.2 and 8.4, the Terminal Operator shall fully and effectively indemnify and hold TNPA or any Port User harmless in respect of all Losses suffered or incurred by TNPA, or any Port User or person which arise in connection with the breach of this Agreement or the applicable Laws by the Terminal Operator, or which the Terminal Operator is legally liable for, including, without limitation to the generality of the foregoing, any Losses which may be incurred or suffered by TNPA  and/or any Port User, or any Person in respect of personal injury (including injury resulting in death).

This clause 8 shall not apply to:

any Losses to the extent that they arise directly from the wilful default and/or negligence of TNPA or the relevant Port User or relevant Person; and

Losses to the extent that TNPA or the relevant Port User or relevant Person is reasonably able to mitigate such Losses.

If the Terminal Operator pays to TNPA an amount in respect of Losses and TNPA subsequently recovers (whether by payment, discount, credit, saving, relief or other benefit or otherwise howsoever) a sum which is directly referable to the fact, matter, event or circumstances giving rise to the Losses, TNPA shall forthwith repay to the Terminal Operator:

an amount equal to the sum recovered or the value of the savings or benefit obtained, less any reasonable costs and expenses incurred by TNPA in recovering the same; or

if the figure resulting under clause 8.3.1 above is greater than the amount paid by the Terminal Operator to TNPA in respect of the Losses, such lesser amount that has been paid by the Terminal Operator to TNPA.

The Terminal Operator shall indemnify TNPA in respect of all Losses relating to the use or infringement or alleged use or infringement by the Terminal Operator of TNPA’s Intellectual Property Rights.

Except as expressly provided in this Agreement, the Terminal Operator shall not make any claim against TNPA or any Port User in respect of any Losses sustained by the Terminal Operator by reason of or arising out of and/or in any way connected with the performance of this Agreement.

For the avoidance of doubt, this clause 8 (Indemnity) shall take effect without prejudice to the Terminal Operator's obligations under the other provisions of this Agreement.

TNPA agrees that it will forthwith notify the Terminal Operator of any claim or any matter or thing which comes to its attention, and which may give rise to a claim by TNPA against the Terminal Operator under this Agreement pursuant to this clause 8 (Indemnity), as follows:

TNPA shall at all times after such notification, disclose in writing to the Terminal Operator all information and documents relating to such claim and the matter giving rise thereto and will allow the Terminal Operator to see appropriate files and records relating to same and take copies of all relevant documents; and

TNPA will take such action as the Terminal Operator may reasonably request at the Terminal Operator’s expense to avoid disputes, settle, compromise, defend or appeal against such claim and TNPA will take no steps to avoid disputes, settle, compromise, defend or appeal against such claim without the Terminal Operator's consent, which consent shall not be unreasonably withheld or delayed. The Terminal Operator shall procure that its Subcontractors shall provide identical undertakings to TNPA.

- Terminal Operator's Warranties and Undertakings

Registration

The Terminal Operator is, incorporated in South Africa in accordance with the provisions of the Companies Act. The Terminal Operator shall remain validly incorporated and registered in accordance with the provisions of the Companies Act for the entire duration of this Agreement.

The Terminal Operator shall maintain such incorporation and its Constitutional Documents and if any intended amendment, restatement, and supplement or any other modification thereof, has the effect of transferring any of the Operating Rights to another entity, the Terminal Operator shall obtain consent and authorisation of the Department of Transport and the consent of the TNPA, which consent shall not be unreasonably withheld.

Compliance with Laws

The Terminal Operator shall comply with the Laws applicable to it and the Project in all respects and shall obtain all Consents that are required in respect of it and all and any aspects or parts of the Project, in accordance with Laws.

TNPA shall use its reasonable endeavours to assist the Terminal Operator to obtain such Consents as may be required to enable the Terminal Operator to execute the Project, provided that TNPA shall bear no liability or responsibility for any failure of the Terminal Operator to obtain such Consents save as provided in this Agreement.

Related Party Transactions

Unless otherwise agreed to by TNPA and without prejudice to the provisions of clause 9.4 (Limitation on Financial Indebtedness), the Terminal Operator shall not enter into any Related Party Transactions, other than Related Party Transactions which are no less favourable to the Terminal Operator than those that could have been obtained in a comparable arm’s length transaction by the Terminal Operator with a Person who is not a Related Party.

TNPA shall have the right to review the basis for all costs charged, directly or indirectly, to the Terminal Operator under a Related Party Transaction. The Terminal Operator shall give prior notice to TNPA of any Related Party Transaction, together with all relevant details relating thereto.

Limitation on Financial Indebtedness

The Terminal Operator shall not incur, assume, or permit to exist any indebtedness including guarantees issued to third parties, the creation of charges, pledges or other encumbrances over the Terminal Equipment and, in general, any claims and rights in respect of the Terminal otherwise than:

in accordance with the Associated Agreements, the financing plan included in the Business Case; or

in the ordinary and normal course of business; or

with the prior consent of TNPA.

- Compliance with D&C Specifications and Operational Plan

The Terminal Operator shall comply with, and shall ensure that its Subcontractors comply with, the D&C Specifications and the Detailed Design in respect of the Construction Works and the Operational Plan in respect of the Operation and Maintenance at all times.

The Terminal Operator warrants that the Project shall be carried out in conformity with the Construction Works Programme, the D&C Specifications, the Detailed Design and the Operational Plan using equipment and materials, which are of suitable quality for the purposes and uses intended and are free of defects and deficiencies. All such Construction Works shall be completed and undertaken in accordance with the Construction Works Programme, the D&C Specifications and the Operational Plan to the reasonable satisfaction of the Independent Certifier.

The Terminal Operator shall ensure that any decision, determination, instruction, inspection, examination, testing, consent, approval, expression of satisfaction, acceptance, agreement, exercise of discretion (whether sole or otherwise) or similar act by any Relevant Authority or the Independent Certifier in respect of this Agreement shall be facilitated, carried out, applied for or requested promptly by the Terminal Operator.

- Contracts

The Terminal Operator shall enter into the Associated Agreements, and such other contracts as are necessary to ensure the timeous and proper completion and undertaking of the Project  in accordance with the D&C Specifications, the Detailed Design and the Operational Plan. The Terminal Operator shall satisfy itself that the terms of such agreements fully describe the rights, obligations, risk allocation and protection of the Terminal Operator’s rights. None of TNPA, any other Relevant Authority or their respective officers, employees, agents and/or representatives, shall have any liability whatsoever to the Terminal Operator arising from the Associated Agreements and/or the Finance Agreements except as provided in or arising from this Agreement.

The Terminal Operator shall not:

amend, replace or cancel any term of the Associated Agreements;

terminate any of the Associated Agreements;

replace the Construction Contractor;

enter into a new Construction Agreement; or

consent to the cession, delegation, or novation of any Associated Agreement, without the prior written consent of TNPA, which shall not be unreasonably withheld.

- Environmental Compliance

The Terminal Operator shall comply with the Environmental Authorisations issued in terms of the National Environmental Management Act, 107 of 1998 (NEMA) and environmental impact assessment ("EIA") for the duration of the Concession Period. The Terminal Operator indemnifies TNPA in respect of all Losses incurred by it because of a failure to comply with the Environmental Authorisations or Environmental Laws.

The Terminal Operator shall, if applicable, comply with any existing EIA and the Environmental Authorisations and any existing environmental authorisation granted to TNPA in respect of the Project Site (the "Existing TNPA Environmental Authorisation") for the Concession Period. The Terminal Operator undertakes to indemnify TNPA in respect of all Losses for any failure to comply with the Environmental Authorisations and the Existing TNPA Environmental Authorisation during the Contract Period.

The Terminal Operator is responsible for and shall obtain all Consents (excluding Environmental Authorisations) that are required in respect of the Project and shall comply with all such Consents. TNPA shall use its reasonable endeavours to assist the Terminal Operator to obtain such Consents as may be required to enable the Terminal Operator to execute the Project, provided that TNPA shall bear no liability or responsibility for any failure of the Terminal Operator to obtain such Consents save as provided in this Agreement. For the avoidance of doubt, the Terminal Operator shall be required to undertake, at its own costs, any further studies as may be required to obtain further Environmental Authorisations for scope of works not covered in the Existing TNPA Environmental Authorisation.

The Terminal Operator shall take all necessary steps to ensure that appropriate pollution control and other environmental protection measures are taken in accordance with the Environmental Laws. The Terminal Operator shall comply with all Environmental Consents obtained by it in respect of the Project Site and the Terminal including the Environmental Authorisations and the Existing TNPA Environmental Authorisation and shall comply with the Environmental Management Plan in respect of the Project Site and the Terminal at all times.

The Terminal Operator shall conduct an environmental site assessment, at the Terminal Operator's expense and within the period specified by TNPA, in respect of all the works, activities and operations conducted by or on its behalf on Project Site or if applicable, elsewhere in the Port as required by the provisions of the NEMA.

Such environmental site assessment shall:

include a systematic identification and evaluation of any potential impacts of any current or proposed work on the environment, this includes biophysical, biological, social, cultural, economic, aesthetic and technological aspects, to such an extent that those aspects are relevant to the works, activities and operations conducted on Project Site or if applicable, elsewhere in the Port;

be conducted by an independent environmental assessment practitioner;

form part of the Terminal Operator's Environmental Management Plan (the "EMP"); and inform the Terminal Operator’s Environmental Management System (the "EMS"); and

comply with any other reasonable requirements stipulated for such an assessment by TNPA.

Within a period of 3 (three) months of the Target Completion Date, the Terminal Operator shall submit, for the approval of TNPA, the EMP which shall comply with NEMA and TNPA's written requirements (which requirements shall be provided to the Terminal Operator). The EMP and EMS shall be developed, updated and implemented by the Terminal Operator for the Construction Period of this Agreement. On or before the Operations Commencement Date, the Terminal Operator must develop a further EMP that will be implemented during the Operations Period. The EMP and EMS shall be binding on the Terminal Operator.

TNPA shall have the right at all times to conduct audits of the Terminal Operator's compliance with the EMP and EMS. If, and where TNPA is of a reasonable belief that there is non-compliance, inefficiency or inadequacy, then TNPA may require that the Terminal Operator rectify such non-compliancy, inefficiency or inadequacy, without any delays, to the reasonable satisfaction of TNPA or provide TNPA with proof that such non-compliance, inefficiency or inadequacy does not exist.

The Terminal Operator, as required by Law, shall comply with:

all the requirements of SAMSA in relation to the environment;

all the conditions in respect of the Project Site, if the Project Site is declared as a protected natural environment or a special nature reserve;

all the conditions in any authorisations or exemptions from the Relevant Authority in respect of the Project Site or the Terminal;

TNPA's requirements for the regular waste removal, including waste originating from cleaning or loading of vehicles or wagons;

all the conditions in environmental permits, consents, licences, certificates, authorisations, orders and exemptions from the Relevant Authority in respect of the Terminal; and

all applicable statutory requirements related to the environment including NEMA, the National Water Act, 36 of 1998, the Air Quality Act, 39 of 2004 and the Biodiversity Act, 10 of 2004, and any other environmental legislation enacted or promulgated before or after the Effective Date.

In the event that the Terminal Operator contravenes the provisions of this clause and/or fails to remedy such contravention in accordance with the terms agreed to, the TNPA shall be entitled to appoint, at the Terminal Operator’s reasonable cost, and with the prior approval of the Terminal Operator, which shall not be unreasonably withheld, an independent environmental monitor who shall be responsible for:

ensuring that the Construction Works and Operation and Maintenance are performed in accordance with the D&C Specifications, the Operational Plan, the Business Case and the Environmental Laws; and

monitoring and ensuring the implementation and effectiveness of mitigation measures and other requirements and targets set forth in the D&C Specifications, Operational Plan, the Business Case and the Environmental Laws.

The conditional authorisations and/or environmental requirements to be fulfilled by the Parties during the Construction Period in terms of the EMP, and during the Operations Period the further EMP, are set out in Schedule 8 (Environmental Management Plan) of this Agreement.

The Parties shall review the EMP at the start of each Contract Year in order to ascertain whether that plan needs to be amended or replaced.  If the Parties are unable to agree whether the EMP should be amended or replaced or on the contents of such amendment or replacement, then such dispute shall be referred to the monitor detailed in clause 12.10 for determination in terms of clause  56 (Expert Determination).  The decision of such monitor shall, in the absence of manifest error or fraud, be final and binding on the Parties.

The Terminal Operator shall, upon the request of TNPA and within a reasonable period of such request, provide TNPA with certified copies of:

all Environmental Authorisations obtained regarding the Construction Works and services it provides at the Port, and, where the permissions are renewable, in each instance a certified copy of a new or updated permission;

any measurements undertaken of emissions, effluent, storm water quality and material safety data sheet for hazardous substances, which it is, obliged to submit to a Relevant Authority; and

prepare and submit quarterly reports in respect of any environmental matters as may arise or require attention.

The Terminal Operator may, as required by Law, not by any means cause significant pollution or degradation of the environment and shall:

provide TNPA within a reasonable period with certified copies of any notices and directives issued by a Relevant Authority to the Terminal Operator to take steps to address pollution or negative impact on the environment;

provide TNPA with certified copies of any report, including an emergency report, submitted by the Terminal Operator to a Relevant Authority regarding pollution or negative impacts on the environment;

take all reasonable measures as envisaged by applicable Environmental Laws, including NEMA and the National Water Act, 36 of 1998, to investigate, assess and evaluate the impact of its activities on the environment of the Port and on the water resources on or below the Port;

if the Construction Works or services directly or indirectly cause any pollution, environmental degradation or negative impact on the Environment, the Terminal Operator shall, at its own costs, undertake efficient and effective means of combating, mitigating, cleaning, collecting and/or disposing of all pollutants, or of otherwise addressing the environmental damages or other negative impact with the appropriate remedial and/or rehabilitative measures, to the satisfaction of any Relevant Authority; and

take every reasonable precaution to prevent the spillage of Cargos and/or other material (including fuel and waste) from vessels, vehicles, Cargo handling equipment and Terminal Infrastructure and Terminal Equipment, and take immediate steps to mitigate and remedy any spillage to the satisfaction of SAMSA, TNPA and any other Relevant Authority, at the Terminal Operator's expense.

If the Terminal Operator fails to comply promptly with any of the obligations imposed under this clause, TNPA shall be entitled to immediately take whatever steps necessary to combat, mitigate and remedy any such pollution, environmental degradation or other impact on the environment, and to recover all reasonable costs incurred by TNPA from the Terminal Operator.

Should TNPA, in writing, determine that the Terminal Infrastructure shall be decommissioned upon the earlier of the cancellation or termination of this Agreement or the termination of the Operations Period, the Terminal Operator shall develop and submit a Decommissioning EMP to TNPA and the Relevant Authority for implementation during the Decommissioning Period in terms of the Decommissioning EMP guidelines, which guidelines shall be provided to the Terminal Operator by TNPA or any requirements that may be stipulated by a Relevant Authority. The Decommissioning EMP shall be required to be approved by TNPA and all applicable Relevant Authorities in order for the duly approved Decommissioning EMP to be submitted to TNPA at least 12 (twelve) months prior to the end of the Operations Period.

Upon the cancellation or termination of this Agreement, the Terminal Operator shall be obliged, at its own cost, to clean-up, remove and rehabilitate any pollution, environmental degradation or environmental impact that may have occurred during its operation of the Terminal in accordance with the provisions of the Law and the Authority’s requirements.

The Terminal Operator shall procure that its employees, agents and sub-contractors comply fully at all times with all of the Terminal Operator’s obligations as specified in this clause 12 (Environmental Compliance) and the Terminal Operator shall be responsible for any breach or non-compliance by its agents or sub-contractors of any such obligations.

- Empowerment Obligations

The Terminal Operator shall comply with its obligations and commitments as set out in the B-BBEE Commitment Schedule (Schedule 12), and the Economic Development Plan (Schedule 24), including the Economic Development Value Summary Worksheets incorporated therein, for the duration of this Agreement.

The Terminal Operator shall, ensure that it achieves and holds a level 4 B-BBBEE Contributor Status Level or its equivalent in terms of the prevailing sector code for the maritime transport and service sector and/or petroleum and liquid fuels sector codes published in terms of section 9 of the B-BBEE Act and shall further maintain such Contributor Status Level for the duration of the Operations Period.

The Terminal Operator shall on an annual basis, before the end of each Financial Year, or on such other date as determined by TNPA, provide TNPA with a certificate of accreditation from an accredited verification agency verifying the Terminal Operator’s B-BBEE Contributor Status Level.

The Terminal Operator further undertakes to:

promote job creation, job retention, skills development and undertake such further supplier development initiatives as set out in its Supplier Development Plan, which is to be annexed hereto as in Schedule 10 (Supplier Development Plan and Supplier Development Value Summary Worksheet) of this Agreement;

improve its Contributor Status Level as set out in its B-BBEE Improvement Plan which is annexed hereto as Schedule 12 (B-BBEE Improvement Plan).

The actual performance of the Terminal Operator against its targets and commitments in the B-BBEE Improvement Plan and the Supplier Development Plan, will be reviewed annually by TNPA, following the completion of each Contract Year. TNPA shall provide the Terminal Operator with a list of all the information which it reasonably requires the Terminal Operator to provide in respect of for each Contract Year by no later than 40 (forty) Business Days before the end of each Contract Year.

Subject to the rights of TNPA to terminate this Agreement under clause 43 (Termination for Terminal Operator Default), following receipt of the Annual Report, TNPA shall review compliance by the Terminal Operator with the targets and commitments in, the B-BBEE Improvement Plan and the Supplier Development Plan in respect of the preceding Contract Year.

In order to conduct the annual review, the information requested by TNPA in terms of clause 13.5 shall be submitted by the Terminal Operator in writing in terms of clause 31.1.2 and shall form part of the Annual Report.

TNPA shall communicate its initial comments and any requests for additional information within 15 (fifteen) Business Days after the information has been supplied by the Terminal Operator in terms of clause 13.6 read with clause 31.1.2, and will take into consideration any response by the Terminal Operator to these initial comments, provided that such response is submitted within 10 (ten) Business Days of the initial comments and/or requests envisaged above. If TNPA intends to make a negative finding regarding any aspect of the performance of the Terminal Operator, it shall give reasonable notice of its intention to do so to the Terminal Operator and representatives of TNPA and the Terminal Operator shall meet to discuss the proposed finding before a final decision is made.

When, in the opinion of the Terminal Operator, events or circumstances occur which may impact negatively on its achievement of its targets and commitments in the B-BBEE Improvement Plan and/or the Supplier Development Plan, the Terminal Operator shall notify TNPA in writing within 10 (ten) Business Days of the occurrence and both the Terminal Operator and TNPA shall document the details of the occurrence of such events or circumstances.  The targets and commitments in the B-BBEE Improvement Plan and/or the Supplier Development Plan, as applicable, may be adjusted or reduced in accordance with such terms as the Parties may agree, should the Terminal Operator be prevented or delayed in performing its obligations by reason of a Force Majeure event.  Furthermore, the targets and commitments in the B-BBEE Improvement Plan and/or the Supplier Development Plan, as applicable may be reviewed and amended, by agreement between the Parties, in the case of any other event or circumstance demonstrably beyond the reasonable control of the Terminal Operator, which had a material, negative impact on the achievement of the targets or commitments by the Terminal Operator.

If the Terminal Operator fails to achieve compliance with the targets and commitments in the B-BBEE Improvement Plan and the Supplier Development Plan in respect of any Contract Year (the “Penalty Period"), as determined in accordance with Schedule 11 (Penalties) and such failure is not attributable to any action, inaction or breach by TNPA of its obligations under this Agreement or due to Force Majeure (a "Failure") TNPA shall be entitled to impose the penalties envisaged in Schedule 11 (Penalties) in respect of such Failure.

Such penalties shall be calculated from the completion of the first Contract Year onwards but shall only be imposed on the Terminal Operator in respect of any Penalty Period, with effect from the completion of the 4th Contract Year onwards.

In relation to any Penalty Period in respect of which a Failure occurs the Terminal Operator shall as part of the Annual Report envisaged in clause 31,  submit a written remedial plan to TNPA, which shall detail the remedial steps that the Terminal Operator will take during the Penalty Period immediately following the Penalty Period in respect of which such Failure arose, in order to remedy the Failure and to achieve compliance with the Supplier Development Scoring Target referred to in Schedule 11 (Penalties).

If the Terminal Operator: (i) fails to comply with clause 13.2; and/or (ii) incurs a Failure and associated penalties in respect of any Penalty Period following completion of the 4th Contract Year; and/or (iii) fails to submit a remedial plan in terms of clause 13.12; and/or (iv) fails to comply with a remedial plan submitted in terms of clause 13.12 in respect of any Penalty Period following completion of the 4th Contract Year; (v) fails to comply with the targets in the BB-BEE Level Commitment Schedule, TNPA shall be entitled to exercise its rights in accordance with the provisions of clause 43 (Terminal Operator Default).

The provisions of clauses 30.5.10 and 30.5.11 shall apply equally to the imposition and recovery of penalties by TNPA in terms of this clause 13 (Empowerment Obligations).

The Parties agree that in the event that any penalties incurred in terms of this clause 13 (Empowerment Obligations) are determined to be a penalty in terms of the Conventional Penalties Act, 1962, TNPA shall be entitled to claim liquidated damages from the Terminal Operator in lieu of the relevant penalty, in an amount equal to such penalty.

The Terminal Operator shall incorporate the "Increased Competitiveness, Capability and Capacity Supplier Development Classification Matrix in Schedule 24 (Economic Development Plan) into its supply chain and procurement practices and shall at the request of the TNPA submit such reports as may be requested and required in respect of the extent of the Terminal Operator’s compliance thereto from time to time.

- Access to documents, copyright, and related matters

The Terminal Operator shall, at no cost to TNPA or any other Relevant Authority, at any time make available to TNPA and/or such Relevant Authority, as the case may be, upon request by any of them, all documents which are or were acquired or brought into existence by the Terminal Operator for the purpose of or in connection with the Project or supplied to the Terminal Operator from other parties to the Associated Agreements.

The Terminal Operator shall use its best endeavours to procure that all software, source codes and manuals, programmes and documentation shall be provided to the Terminal Operator by its suppliers upon termination of such a supplier contract. The Terminal Operator shall procure and be granted a perpetual non-exclusive royalty-free licence to use same for the continued Operation and Maintenance of the Terminal, which licence shall be transferred to a Substitute Entity or to a third party for continuing the Operation, Maintenance and/or upgrade of the Terminal in accordance with the provisions of the Operations Agreement in force at that time.

Copyright owned by the Terminal Operator, Construction Contractor or Operator in all Project Documents shall be transferred free of any cost to TNPA on termination of this Agreement or expiry of the Operating Term, whichever is earlier.

To the extent that the Terminal Operator is the owner of the copyright in the D&C Specifications, the Operating Specifications and other documents issued by TNPA or the Terminal Operator, such copyright shall be the property of TNPA. To the extent necessary, any copyright in terms thereof shall be ceded, assigned and made over to TNPA.  The Terminal Operator may at its cost (and shall allow other parties to the Associated Agreements at their cost to), copy, use and communicate any such document for the purposes of the respective Associated Agreements. The Terminal Operator shall not (and shall ensure that other parties to the Associated Agreements shall not), without TNPA’s consent, use, copy or communicate to a third party such documents, except as strictly necessary for the purposes of the Associated Agreements.  In addition to and without limiting the foregoing, the Terminal Operator shall deliver the Construction Documents and Operating Documents, and to the extent that the Terminal Operator is the owner of the copyright in any such documents, or the Terminal Operator is otherwise lawfully able or entitled to do so, transfer the copyright in such documents to TNPA on the earlier of:

the termination of this Agreement; or

the termination of the Construction Contract; or

the termination of the Operations Agreement; or

the appointment of a Substitute Entity and provided that such documents have, or such copyright has not already been delivered or transferred to TNPA, as the case may be, upon the appointment of such Substitute Entity.

Upon termination of this Agreement due to Terminal Operator Default, the Terminal Operator shall upon request by TNPA provide copies of or access to TNPA in respect of or to any other Relevant Authority designated by TNPA, the Project Documents, which access and copies shall be at no cost to TNPA or such Relevant Authority, and shall be for their use in relation to the Construction works and/or Operation and Maintenance before the appointment of a Substitute Entity, if any.  The Terminal Operator further agrees, upon expiry of the Project Term or termination of this Agreement for whatsoever cause, to ensure the transfer of ownership of the Project Document (to the extent owned by the Terminal Operator, Construction Contractor or Operator) to TNPA.  The Terminal Operator shall procure that TNPA is legally entitled to use such Project Documentation and any other information which is not owned by the Terminal Operator, Construction Contractor or Operator and which is necessary for the Construction works and/or continued Operation and Maintenance.

Save in the course of the proper discharge of its duties hereunder, the Terminal Operator shall not and shall ensure that other parties to the Associated Agreements shall not, during the Construction Period and Operating Term or at any time thereafter, disclose to any person  or otherwise make use of any information relating to the Project, TNPA or the Terminal Operator (including, but without limitation, information relating to the Construction works, Operation and Maintenance, the contents of any documents, including any legal agreements, prepared by or on behalf of the Terminal Operator or to which the Terminal Operator is a party), save for such information that is or comes into the public domain (other than through the default of the Terminal Operator or other parties to the Associated Agreements), other than with the prior approval of TNPA.  Nothing contained in this clause shall preclude the Terminal Operator from using such information in enforcing its rights against TNPA or any other person.

Unless otherwise agreed to by TNPA, and except as provided for in this Agreement or the Associated Agreements, the Terminal Operator and other parties to the Associated Agreements shall have no other interest or benefit in or to receive any other remuneration in connection with the Project or any part thereof.  The Terminal Operator shall not (and shall ensure that other parties, to the Associated Agreements shall not) be engaged in any activity which might conflict with the interests of TNPA under this Agreement or the Associated Agreements, unless such activity is carried out pursuant to the enforcement of its rights thereunder.  Nothing in this clause shall prevent the Terminal Operator from enforcing their rights under this Agreement and any Associated Agreements.

- Performance Guarantees

Delivery of Performance Guarantees

The Terminal Operator shall obtain, at its own cost, the on-demand Performance Guarantees referred to below in this clause 15 (Performance Guarantees), in such a form as per the relevant schedules hereto and to the satisfaction of the TNPA.

Concession Fee Guarantee

The Terminal Operator shall, no later than the commencement of the Construction Period,  provide an irrevocable bank guarantee in the sum equal to [                     ] Concession Fee as payable during the first year, excluding VAT thereon, as security for the payment of any and all amounts payable by the Terminal Operator in terms of this Agreement.

Construction Performance Guarantee

The Terminal Operator shall, no later than 30 (thirty) days before the Effective Date  obtain the Construction Performance Guarantee, which shall be an unconditional, irrevocable, on demand guarantee in favour of the Terminal Operator, from the Construction Contractor as at the Effective Date to the value as may be agreed to with the Construction Contractor and which shall remain in place until and upon the issue of the Completion Certificate upon completion of the Construction Works as contemplated in clause 28.4 (Completion of Construction Works) to secure the performance by the Construction Contractor of its obligations in terms of the Construction Agreement, as at the Effective Date.

The Construction Performance Guarantee shall be substantially in the form of the guarantee annexed to this Agreement as Schedule 13 (Construction Performance Guarantee).

The Construction Performance Guarantee shall be valid from the Effective Date until the expiry of the Completion Defects Rectification Period (as this latter term is defined in the Construction Agreement) and shall be returned to the Terminal Operator within 14 (fourteen) Days after the expiry of the Completion Defects Rectification Period.

Final Maintenance Guarantee

The Terminal Operator shall obtain a Final Maintenance Guarantee in favour of TNPA in an amount equal to 10% (ten per centum) of the value of the Terminal as provided for in the Base Case Financial Model.

The Final Maintenance Guarantee shall be an unconditional, irrevocable, on demand bank guarantee which is substantially in the form of the guarantee annexed to this Agreement as per Schedule 15 (Final Maintenance Guarantee).

The Final Maintenance Guarantee shall be submitted by no later than 12 (twelve) months prior to the expiry of the Operations Period and remain valid until the expiry of the Operations Period. The Final Maintenance Guarantee shall be released to the Terminal Operator once the Terminal Operator has satisfied TNPA that it has attended to the refurbishment of the Terminal, the Terminal Infrastructure and the Terminal Equipment, if applicable, so as to render the Terminal fully operational following the Operations Period and that the Terminal Operator has complied with its maintenance obligations in respect of the Terminal as detailed in the Operational Plan.

In the event that TNPA is satisfied that the Terminal Operator is maintaining the Terminal in accordance with its annual maintenance plans and in accordance with TNPA’s asset maintenance plans to the extent applicable, it shall be entitled to waive its right to call for the submission of such a Maintenance Guarantee.

Terminal Operator’s Obligations incorporated into Associated Agreements

The Terminal Operator shall ensure, where possible, that the Construction Contractor incurs the same obligations to the Terminal Operator under the Construction Agreement, as the Terminal Operator has imposed upon it in terms of this Agreement in respect of the Construction Works and Operation and Maintenance.

The Performance Guarantee shall also secure the obligations of the Construction Contractor under the Associated Agreements in favour of the Terminal Operator.

Enforcement Action

The Performance Guarantees shall secure the Terminal Operator’s performance of its obligations to TNPA  in respect of the Construction Works, Operations and Maintenance, and may be called on by TNPA to the extent of any Losses, costs, damages or expenses suffered or incurred by TNPA as a result of a breach by the Terminal Operator of the aforesaid obligations including, but not limited to, compensation to TNPA  for any actions taken by TNPA  as a result of such breach by the Terminal Operator of its obligations.

Prior to enforcing any such Performance Guarantee as aforesaid, TNPA shall give notice to the Terminal Operator, informing the Terminal Operator of the breach giving rise to the right, on the part of TNPA, to enforce the Performance Guarantee.  If such breach is not remedied within the stipulated remedy period as contemplated in clause 43.2 (Remedy Provisions), and subject to the terms and conditions contained in the relevant or applicable Performance Guarantee, TNPA may enforce the applicable Performance Guarantee for an amount equal to any cost, Losses, damages or expenses incurred by TNPA in respect of any such breach by the Terminal Operator.

- Project Insurance

General obligations

The Terminal Operator shall, in accordance with this clause 16 (Project Insurance), obtain and maintain in effect, at its own cost and expense, with a reputable insurance company such insurance coverage as is required by:

any Laws;  and

the standards of a Reasonable and Prudent Operator.

The Terminal Operator shall take reasonable steps to ensure that its Subcontractors obtain and maintain in effect at all times such insurance cover as is appropriate for a reasonable and prudent contractor.

Application of insurance proceeds

Unless the TNPA (acting reasonably) otherwise agrees in writing, the Terminal Operator shall apply all proceeds of any insurance claim made due to loss or damage to the Project or any part of the LNG Terminal (other than claims under any loss of revenue policies) towards reinstatement, reconstruction, replacement, repair or renewal of such loss or damage in the first instance.

Uninsurable Risks

If a risk usually covered by the Project Insurances  becomes Uninsurable, then the Terminal Operator shall notify TNPA within 3 (three) Days of that risk becoming Uninsurable.

If both Parties agree, or it is determined in accordance with clause 57.7 (fast-track dispute resolution), that:

such risk is Uninsurable;

such risk being Uninsurable is not caused by the actions or omissions of the Terminal Operator or a Subcontractor; and

other service providers carrying on businesses similar to the Project would cease to operate their business as a result of such event being uninsurable, then the Parties shall meet to discuss the means by which such risk should be managed (including by way of self-insurance by either Party).

The Terminal Operator shall bear the onus of proving the circumstances in clauses 16.1.4.3 and 16.1.4.5.

If the requirements of clauses 16.2.2.1 and 16.2.2.2 are satisfied, then the Agreement shall continue in full force and effect.

On the materialization of such risk, but only if such risk is still Uninsurable, TNPA  and the Terminal Operator shall enter into negotiations to reach agreement on the most appropriate remedial action, failing which such dispute shall be determined in accordance with clause 57.7 (fast-track dispute resolution). TNPA shall, at TNPA ’s option, either pay to the Terminal Operator:

an amount equal to the insurance proceeds that would have been payable had the relevant risk continued to be insurable and this Agreement will continue; or

an amount equal to the amount set out in clause 50 (Termination amount for invalidation in terms of Section 67 of the Act) and this Agreement will terminate.

- Port Users and Port Rules

The Terminal Operator shall fulfil its obligations, duties and responsibilities under this Agreement and in particular (without limitation) its duties in respect of the provision of the Construction Works, the Operation and Maintenance and the services:

so as not to interfere with the use of the Port, its facilities and the Port Infrastructure by other Port Users;

in compliance at all times with the Act, all other applicable legislation and the Port Rules; and

the TNPA’s the Liquid Bulk Terminals Mandatory Requirements for Safety Health, Environment, process safety, civil, structural, mechanical and electrical marked Schedule 19.

- Changes in the Terminal Operator

The Terminal Operator shall notify TNPA forthwith on becoming aware of any change in the legal or beneficial ownership from time to time of the Terminal Operator. In the event that such change constitutes a Change in Control as defined in clause 1.1.21 and entails the transfer, cession or assignment of the Terminal Operator’s rights granted in terms of  this Agreement,  the Terminal Operator shall  provide TNPA with any information which TNPA may reasonably require (and which the Terminal Operator is reasonably able to provide) relating thereto and the Terminal Operator shall be obliged to obtain, TNPA’s written consent prior to effecting such a Change in Control.

The Terminal Operator shall obtain TNPA’s written consent (which consent shall not be unreasonably withheld or delayed) prior to any Change in Control. TNPA shall notify the Terminal Operator whether it consents to the Terminal Operator within 20 (twenty) Business Days, or such extended time as may be agreed to in writing by the parties.

TNPA shall not unreasonably refuse its consent to any change in control of the Terminal Operator which is intended to produce compliance with the B-BBEE Improvement Plan. Any dispute as to whether TNPA is acting unreasonably in refusing its consent to such transfer shall be resolved in accordance with the fast-track dispute resolution procedure.

- TNPA's Assistance and Rights and Limitations on Liability

Except as otherwise provided in this Agreement, TNPA shall:

assist the Terminal Operator in its dealings with any Relevant Authority in connection with implementing the Project in accordance with the terms and conditions set forth herein; and

make every reasonable effort to assist the Terminal Operator to obtain those Consents necessary for the Construction Works and Operation and Maintenance of the Terminal, provided that TNPA shall not be liable or responsible for any failure of the Terminal Operator to obtain any such Consents.  If the Terminal Operator fails to obtain any such Consents, the Terminal Operator and TNPA shall agree, in good faith, on a mutually acceptable solution within a reasonable time period of the Terminal Operator failing to obtain such Consents, failing which the matter shall be dealt with in accordance with clause 57 (Dispute Resolution).

Nothing in this Agreement shall preclude or in any manner limit the rights of TNPA or any other Relevant Authority from granting such further or other concessions as it in its sole discretion deems fit, nor shall the Terminal Operator have any claim against TNPA or any other Relevant Authority arising from the grant of such further or other concessions, in any other port in South Africa.

TNPA shall not be liable to the Terminal Operator for the volume of demand for the services of the Terminal Operator and it shall be the responsibility of the Terminal Operator to adequately market the Terminal and the services of the Terminal Operator.

No warranties, representations or undertakings are given as to the accuracy or completeness of any information provided by TNPA and/or its advisors. None of TNPA nor its advisors shall be liable for any error, misrepresentation or omission in any such information.

Notwithstanding anything else contained in this Agreement, the Terminal Operator shall not in any way be relieved from any obligation under this Agreement nor shall it be entitled to claim against TNPA  or any other Relevant Authority and/or their respective officers, employees, agents and/or representatives on grounds that any information, whether obtained from or made available by TNPA  or any such other Relevant Authority and/or their respective officers, employees, agents and/or representatives or otherwise is incorrect or insufficient and shall make its own enquiries as to the accuracy and adequacy of that information.

Where in this Agreement any power, duty, function or discretion is given or is to be carried out or exercised by TNPA, such power, duty, function or discretion may be carried out or exercised by any Person nominated by TNPA.

- TNPA Step-in

TNPA may be authorised by the Minister of Transport, with the concurrence with the shareholding Minister to take any action in connection with the Operation and Maintenance and Construction Works, and/or the operation or the Terminal in  the Port because a serious and urgent risk arises to the health or safety of persons or property, or to the environment, or to national and public safety and/or to discharge a statutory duty, then TNPA  shall be entitled to take action in accordance with the provisions of this clause.

If pursuant to this clause 20 (TNPA Step-in), TNPA wishes to take action, it shall as soon as possible after reaching its determination to do so notify the Terminal Operator in writing of:

the action it wishes to take;

its reasons for taking such actions;

the date when it wishes to commence such action;

the time period (the "TNPA Step-in Period") which it reasonably believes will be necessary for such action and which must be a fixed period; and

to the extent practicable, the effect of such action on the Terminal Operator on its obligations to perform the Operation and Maintenance and Construction Works, and/or services of the Terminal Operator during TNPA Step-in Period.

Following the service of such notice, TNPA shall take such action as notified under clause 20.2 and any ancillary action as it reasonably believes is necessary (the "Required Action") and the Terminal Operator shall give all reasonable assistance to TNPA  in the conduct of such Required Action.

If the Terminal Operator is not in breach of its obligations in terms of this Agreement in respect of which the Required Action is proposed to be taken, then for so long as and to the extent that the Required Action is taken, and this prevents the Terminal Operator from providing any part of the Project:

the Terminal Operator shall be relieved from such obligations; and

in respect of the time period over which such Required Action is conducted, and provided that the Terminal Operator provides the TNPA with such reasonable assistance as the TNPA may need in the conduct of such Required Action (such assistance, however, to be at the expense of the TNPA to the extent of any incremental costs):

the TNPA shall pay to the Terminal Operator an amount of monies that is equal to the revenue that the Financial Model projects to have been earned by the Terminal Operator at the time of and during the period of the Required Action if the Terminal Operator was fulfilling all its obligations in respect of the Project that are affected by the Required Action over such period; and

the Term of the Operating Period, alternatively the Construction Period, as applicable, shall be extended for the length of the time over which such Required Action is conducted.

  - If the Required Action is taken as a result of a breach by the Terminal Operator of any of its obligations under this Agreement, then for so long as and to the extent that such Required Action is taken, and this prevents the Terminal Operator from providing any part of the Project:

the Terminal Operator shall be relieved of its obligations in respect of such;

the Terminal Operator shall owe TNPA an amount equal to TNPA’s costs of taking such Required Action,

provided that, if by the expiry of the Step-in Period, the breach still subsists and if it constitutes a Terminal Operator Default, then TNPA  will be entitled to serve a notice in terms of clause 44.1 (TNPA's option) requiring the Terminal Operator to remedy the Terminal Operator Default or to put forward a remedial programme.

# PART II – PROVISION OF THE PROJECT SITE AND THE PORT

- Provision of the Port

TNPA shall provide, manage, and maintain the Port, in accordance with the Act and any other Laws that are applicable to such provision, management and maintenance from time to time and in accordance with the Act and other applicable Laws.

- The Project Site

As provided for in clause 6.1 TNPA, shall remain the owner of the Project Site for the duration of this Agreement. The Terminal Operator acknowledges the ownership rights of TNPA in respect of the Project Site on which the Port is constructed and shall not in any way challenge or procure that any Person challenges or assists any other Person to challenge, such ownership rights and title of TNPA.

The Terminal Operator acknowledges that it does not have and shall not have any rights of title, ownership, lien, leasehold or any other rights in respect of the Project Site, other than the rights of occupation and use as detailed in this Agreement.

The Terminal Operator shall bear all risks and costs with regard to the physical conditions or obstructions on the Project Site (both above ground and subsurface and whether artificial or not) whether foreseen or unforeseen which are encountered during Construction Works or otherwise. The Terminal Operator shall be deemed as at the date of this Agreement to have satisfied itself in all respects as to the properties, nature, condition and extent of the Project Site.

The Terminal Operator shall, for the duration of this Agreement, have the right to use and occupy the Project Site, commencing on the Effective Date.

The Terminal Operator shall, in respect of its rights of use of the Project Site, pay to the TNPA the Rental amount in accordance with the provisions of clause 6 (Rental) of this Agreement.

In addition to the payment of Rental in terms of clause 6 (Rental), the Terminal Operator accepts responsibility for the payment of all municipal services and Utilities provided in respect of the Project Site, Rates, Taxes, charges, levies, assessments or any equivalent taxation which may at any time be levied by a Relevant Authority upon or in connection with the Project Site, in respect of the period covered by this Agreement, other than any Taxes imposed in relation to the receipt by TNPA of the payment detailed in clause  6.1 or in connection with its disposal of its interest in the Project Site used by the Terminal Operator or in relation to any other amounts received by or accrued to TNPA  as a result of or in connection with this Agreement or the Project Site used by the Terminal Operator. All amounts payable by the Terminal Operator in terms of this clause 22.6, shall be paid monthly within 30 (thirty) days of been issued with an invoice from TNPA.

The Terminal Operator may object to any rates valuation made by any Relevant Authority of the Project Site used by the Terminal Operator or the Project Site of which they form part. The Terminal Operator shall be liable for all costs in prosecuting any such objection and the Terminal Operator shall be entitled to any benefit accruing as a result of a successful objection.

If TNPA is obliged by the Relevant Authority to make payments referred to in clause 22.6, as a result of which TNPA makes such payments on behalf of the Terminal Operator, TNPA  shall notify the Terminal Operator in writing about such payments and following such notice the Terminal Operator shall, within 30 (thirty) Days after being called upon to do so, refund to TNPA such payments as TNPA may have made in respect of the rates, Taxes, charges, levies, assessments or equivalent Taxes levied.

TNPA shall use its reasonable endeavors to ensure that no other Port Users negatively affect the use by the Terminal Operator of the Project Site. The Terminal Operator shall not negatively affect the use of the Port by TNPA and the other Port Users, other than the Project Site and then only to the extent detailed in this Agreement.

TNPA shall have the right to enter and inspect the Project Site and the Terminal at reasonable times and on reasonable notice so as to enable it to inspect the Project Site and the Terminal, to fulfil its obligations of maintenance in respect of the Port and to fulfil its obligations as the port authority of South Africa.

The Terminal Operator shall use the Project Site solely for the uses and purposes contemplated in this Agreement in respect of the Project.

The Terminal Operator shall be responsible for maintaining the Project Site in good condition, fair wear and tear excepted, at no cost to TNPA or any other Port User. TNPA shall maintain or shall use its reasonable endeavors to procure that other Port Users maintain the Port, other than the Project Site, in good condition, fair wear and tear excepted, at the cost of TNPA or the relevant Port User. The Parties shall meet and discuss any intended maintenance or repair activities so as to ensure that such activities are conducted in a manner that minimises any interference with the operations of the other Party.

The Terminal Operator shall not be able to transfer any of its rights in respect of the Project Site or the use thereof to any other Person without the prior written consent of TNPA.

The Terminal Operator shall, subject to TNPA ’s approval, provide for:

the clearance of the Project Site;

any diversions to and re-routing of roads not forming part of the Project Site; and

the clearance, relocation and diversion of all Utilities on the Project Site,

from the date the Project Site is delivered to the Terminal Operator and

which are necessary for the execution of the Project.

The Terminal Operator shall, at its cost, apply for all Consents required for the clearance of the Project Site.

The Terminal Operator shall continue to be bound by and shall honour any existing agreements between TNPA and any person, which grant access or wayleaves to the Project Site. The Terminal Operator may, however, apply to TNPA for any necessary modifications or cancellations of such agreements, such application to be made timeously in order to avoid any delay or additional cost. To the extent that TNPA has the right to modify or cancel such agreements, it shall comply timeously with the Terminal Operator’s reasonable request to modify and/or cancel any such agreements.

TNPA shall make available to the Terminal Operator to the extent that it is able to do so, all of agreements referred to in clause 22.16.

- Key Personnel and Removal of Personnel

The Terminal Operator shall at all times ensure that it and its Subcontractors have sufficient suitable and appropriately qualified and experienced personnel to undertake the Project and that such personnel shall be located in South Africa.  Without limiting the generality of the foregoing, the Terminal Operator shall ensure that the key personnel positions are always filled as soon as reasonably possible.

The Terminal Operator shall implement all measures as are required by Law and/or as may be reasonably necessary to ensure the safety of its employees or Subcontractors and shall provide them or ensure that they are provided, free of charge, with any necessary personal protective clothing and equipment.

The Terminal Operator accepts full responsibility for the training of staff and shall ensure that all its employees and Subcontractors are properly trained for the work they are undertaking and are familiar with safety and security requirements that apply to the Terminal.

TNPA may require the Terminal Operator to remove any employee or other personnel of the Terminal Operator or any Subcontractor from the Project Site and the Terminal Operator shall do so (subject to applicable Law) if in the reasonable opinion of TNPA  such employee or personnel engages in any conduct which might reasonably result in a breach of any provision of this Agreement or threaten public health, safety or security, and the Terminal Operator shall immediately comply and replace such employee or personnel with suitable appropriately qualified and experienced replacements, subject to applicable Law.

- Health and Safety

Within 30 (thirty) Days of the Commencement Date, the Terminal Operator shall, at its cost, complete a comprehensive risk assessment of its business, in respect of all areas of the Project Site, and the services or processes it intends to undertake, in accordance with the requirements of the Occupational Health and Safety Act No 85 of 1993, and shall provide TNPA with a full report on its risk assessment so undertaken within 1 (one) month of completing the assessment.

The Terminal Operator shall be responsible for:

the implementation of and adherence to the IMDG Code and its regulations;

compliance with the Occupational Health and Safety Act No 85 of 1993 and regulations promulgated in terms of that Act;

procuring and implementing systems and services for the prevention, monitoring, detection and extinguishment of fires or explosions; and

maintaining a working environment which is safe and designed to minimise the risk of injury or illness to any Person present on the Project Site and to minimise the risk of Loss or damage to cargoes, vessels or other moveable and immoveable property in accordance with Law and the further written requirements of TNPA.

The Terminal Operator may not keep or store any hazardous or flammable substances unless:

it reasonably requires such hazardous or flammable substances to be kept or stored to enable it to conduct its business on the Project Site;

it has obtained the prior written approval of TNPA; and

it complies with the applicable Law in respect of hazardous substances in general and that specific hazardous substance, in particular.

In addition to the general Port water network provided by TNPA, the Terminal Operator shall provide, at its own cost, such fire water network, facilities or equipment, or other protective measures, that are, in TNPA ’s reasonable opinion, necessary in order to provide effective fire protection installations and water supply to the Project Site.

TNPA may, from time to time, require the Terminal Operator, by notice in writing, to provide and install, at the Terminal Operator’s cost, such further devices, appliances and installations as TNPA may reasonably consider necessary to minimise the risk of any fire occurring or to prevent the spread of any fire which may occur. The Terminal Operator shall, when so required, comply with the requirements set forth in such notice within the time period specified in the notice.

The Terminal Operator shall be required to ensure that it avails and/or procures appropriate and suitably qualified emergency response personnel to manage emergencies in the Terminal and shall submit, at the request of TNPA, all and any emergency response plans it has prepared in respect of the Terminal.

The Terminal Operator shall be obliged to submit a written report to TNPA in respect of any incident which occurs in the Terminal where any employee of the Terminal Operator or its Subcontractors has been injured, within 24 hours of the occurrence of such incident.

- Security

The Terminal Operator must ensure that the perimeter of the Project Site is fenced with security fencing of the standard set by the Department Of Transport and required to ensure compliance with the ISPS Code, and that such fencing is maintained at that standard (and repaired as necessary) during the term of this Agreement.

The Terminal Operator shall comply in all material respects with the provisions of the International Maritime Organisation Convention of Safety and Security at Sea, the ISPS Code, and the Terminal Operator shall be responsible for the security of the Project Site and for all persons and movables therein, including cargoes, and for the implementation of and adherence to the ISPS Code.

The Terminal Operator shall submit to TNPA, within 1 (one) month of the Commencement Date, a Project Site security assessment and develop a Project Site security plan for security levels 1, 2 and 3, corresponding with normal, medium and high threat situations. The plan shall indicate the operational and physical security measures the Terminal Operator will take to ensure that it normally operates at security level 1. The plan shall also indicate the additional, or intensified, security measures the Terminal Operator will take when instructed to do so by TNPA, to move to and operate at security level 2 (two), and to operate at security level 3 (three). The Terminal Operator will nominate a Port Terminal Security Officer, organise regular security drills and at all times provide the necessary security equipment on the Project Site.

As part of the Project Site security plan the Terminal Operator shall monitor and control all Cargo, vehicles and people entering and leaving the Project Site and ensure that security communications are always readily available.

# PART III – DESIGN AND CONSTRUCTION, OPERATION AND MAINTENANCE

- Independent Certifier

Appointment of Independent Certifier

TNPA and the Terminal Operator, acting jointly, shall appoint the Independent Certifier for a period which shall include the Development  and Construction Period as may be agreed to between the Parties and notified to the Independent Certifiers in terms of the Independent Certifier Agreement. In this regard, it is recorded that TNPA, the Terminal Operator and the Independent Certifier shall enter into the Independent Certifier Agreement as soon as reasonably practicable after the Signature Date, but not later than the Effective Date. The Independent Certifier Agreement shall be substantially in the form of the agreement attached to this Agreement as Schedule 23 (Independent Certifier Agreement).

TNPA shall propose a person for appointment as the Independent Certifier, for approval by the Terminal Operator.

If TNPA and the Terminal Operator are unable to agree on the person to be appointed as the Independent Certifier:

TNPA and the Terminal Operator shall each nominate 2 (two) persons ("Nominees") for the position of Independent Certifier;

TNPA shall submit the names of the Nominees together with their resumes to the chairperson for the time being of the Consulting Engineers South Africa ("CESA") or its successors in title;

the said chairperson of the CESA shall appoint the Independent Certifier from amongst the Nominees; and

such decision of the chairperson of the CESA shall be final and binding on the Parties.

The Independent Certifier will report directly to TNPA and the Terminal Operator, and the fees and disbursements of the Independent Certifier incurred in connection with the Project shall be paid by the Terminal Operator.

In appointing a person to act as the Independent Certifier in the future, the Parties shall comply with TNPA’s B-BBEE Policy and requirements in respect hereof.

Performance of duties of Independent Certifier

The Terminal Operator shall provide the Independent Certifier with a copy of this Agreement and shall, to the extent available to the Terminal Operator, provide the Independent Certifier with the requisite information and documentation in order to enable the Independent Certifier to discharge its duties and/or obligations.  Such information and documentation includes, but is not limited to, the following:

copies of working drawings, schedules and specifications prepared by the Terminal Operator and its Contractors and/or other Subcontractors (as applicable), sufficient to demonstrate compliance of the Terminal Operator and its Contractors and/or other Subcontractors (as applicable) with the requirements of this Agreement;

copies of the Terminal Operator's correspondence relating to the Terminal or building control matters;

copies of the Terminal Operator's commissioning reports;

if applicable, copies of the Annual Reports submitted by the Terminal Operator in terms of this Agreement;

copies of the Construction Agreement, the Construction Works Programme, the draft Detailed Design and the D&C Specifications;

copies of the Terminal Operator’s operating and maintenance manuals as well as the Operational Plan;

a copy of the health and safety plan of the Terminal Operator; and

any other information that the Independent Certifier reasonably requires in order to fulfil its duties and responsibilities.

The Independent Certifier shall be required to perform the duties set forth in this Agreement and as may be specified in the Independent Certifier Agreement.

TNPA and the Terminal Operator shall be entitled to consult with the Independent Certifier on any matter relating to the Project, the Construction Agreement, the Construction Works Programme, the Detailed Design and the D&C Specifications.  TNPA and/or the Terminal Operator may request the Independent Certifier to deliver and issue an opinion, instruction, certificate or valuation, or other determination as applicable with respect to all technical matters relating to the Project, the Construction Agreement, the Construction Works Programme, the draft Detailed Design and/or the D&C Specifications, in accordance with the provisions of and as contemplated in this Agreement.  The Parties agree to comply with such decisions of the Independent Certifier until and unless otherwise determined pursuant to clause 57 (Dispute Resolution).

The Independent Certifier’s duties shall include, but shall not be limited to, the review, inspection, testing, accepting and recommending certification   of the Construction Contractor’s work to ensure proper performance and completion of the Construction works in accordance with this Agreement, the Construction Agreement and the Independent Certifier Agreement.  The Independent Certifier’s duties may also include the review, analysis, audit, inspection and testing of the Operator's work to ensure proper Operation and Maintenance in accordance with the terms of this Agreement, the Operations Agreement and the Independent Certifier Agreement. Nothing in this clause 26 shall alter the rights and obligations of the Parties under this Agreement nor, unless otherwise provided in this Agreement, prevent the Parties from challenging any opinion, instruction, determination, certification or valuation of the Independent Certifier in accordance with clause 57 (Dispute Resolution), provided that the Parties shall comply with such decisions by the Independent Certifier until and unless otherwise determined pursuant to clause 57 (Dispute Resolution).

If any determination which the Independent Certifier is required to make in terms of this Agreement or the Independent Certifier Agreement involves an evaluation or assessment of any matter outside the Independent Certifier's field of expertise as Independent Certifier, the Independent Certifier shall with, the express written approval of the Terminal Operator and TNPA, appoint and rely on an independent expert advice in making such evaluation or assessment.

- Demolish Existing Buildings

The Terminal Operator shall be entitled to demolish at its own cost all of the Existing Buildings , if any, situated on the Project Site but shall not commence such demolition until it has received prior written approval from TNPA and the Relevant Authority to do so.

- Design and Construction

Performance of the Detailed Design

The Terminal Operator shall submit Detailed Design and D&C Specifications, Construction Agreement and Construction Works Programme in respect of the Construction Works for the Terminal to the TNPA and the Independent Certifier within 5 (five) months of the Signature Date. The Detailed Design Specifications in respect of the Terminal must comprise all the aspects as detailed in this clause 28  (Design & Construction) and show evidence of compliance with the requirements set out in Schedule 24.

The Detailed Design and D&C Specification, Construction Agreement and Construction Works Programme shall be reviewed prior to commencement of Construction Works, by the Independent Certifier in accordance with the Rules of Conduct for Registered Persons: Engineering Profession Act, 2000 (Act No. 46 of 2000).  If the Independent Certifier, acting reasonably, is of the opinion that the Detailed Designs and the D&C Specifications Construction Agreement and Construction Works Programme comply with the requirements of this Agreement and industry norms and standards, the Independent Certifier shall accept the Detailed Design and D & C Specifications, Construction Agreement and Construction Works Programme in writing.

If the Independent Certifier, acting reasonably, is not satisfied with the Detailed Designs and D&C Specifications, Construction Agreement and Construction Works Programme, the Independent Certifier shall notify the Terminal Operator and TNPA of the reasons for its dissatisfaction within 5 (five) Business Days after the review referred to in clause 28.1.2, specifying those elements of the Detailed Design and with which the Independent Certifier, acting reasonably, is dissatisfied.

Within 14 (fourteen) Business Days of the Independent Certifier having expressed dissatisfaction with the Detailed Design, D&C Specifications, Construction Agreement and Construction Works Programme, TNPA and Terminal Operator shall attend to such areas of concern raised by the Independent Certifier and re-submit the amended Detailed Design, D&C Specifications, Construction Agreement and Construction Works Programme, as applicable for review by the Independent Certifier (the "Second Review").

If, after the Second Review, the Independent Certifier, acting reasonably, is still not satisfied with the Detailed Design, D&C Specifications, Construction Agreement and Construction Works Programme, the Independent Certifier shall notify the Terminal Operator and TNPA  of the reasons for its dissatisfaction within 5 (five) Business Days after the Second Review, specifying those elements of Detailed Design, D&C Specifications, Construction Agreement and Construction Works Programme, as applicable, with which the Independent Certifier, acting reasonably, is still dissatisfied.  The Independent Certifier and the Parties shall arrange a meeting that includes the Designer and endeavor to reach mutual agreement on the correction of the the areas of concern raised by the Independent Certifier.

Once the Detailed Design, D&C Specifications, Construction Agreement and Construction Works Programme have been accepted in writing by the Independent Certifier, they shall be deemed to have been approved by TNPA.

The Terminal Operator shall perform or procure the performance of the Construction Works in accordance with Detailed Design, D&C Specifications, Construction Agreement and Construction Works Programme the Construction Agreement, the Construction Works Programme, accepted in writing by the Independent Certifier.

All reviews undertaken in this clause 28.1  as a result of the Independent Certifier dissatisfaction as contemplated from clause 28.1.4 above shall be undertaken at the Terminal Operator’s cost and shall not constitute any form of a variation or change in scope.

Execution of Construction Works

The Terminal Operator remains accountable for and shall perform or procure the performance of the Construction Works in accordance with the provisions of this Agreement, Construction Agreement, the Construction Works Programme, the D&C Specifications and the Detailed Design.

The Terminal Operator shall bear sole responsibility for the procurement of all construction materials in accordance with the approved Detailed Design, the adequacy of the design and compliance with the D&C Specifications and the Detailed Design.

The Terminal Operator may submit to the Independent Certifier for review, acceptance and recording of proposals for modifications by the Terminal Operator to the design, which, in the Terminal Operator’s opinion, would improve the quality or safety of the Terminal provided that any such modifications and any related amendments to the Construction Agreement, the Construction Works Programme, the Detailed Design and/or the D&C Specifications, shall only be effected if approved in writing by the Independent Certifier and TNPA.

The location, design and construction of any points of access to and/or egress from the Project Site both during construction and afterwards shall be in accordance with the D&C Specifications and the Detailed Design or otherwise be subject to the prior consent of TNPA and the Terminal Operator.

Commencement of Construction Works

The Terminal Operator shall be obliged to commence construction of the Construction Works on the date as specified in Construction Works Programme and/or by no later than 90 days after the Effective Date or any such date as may be agreed between the Parties in writing.

Completion of Construction Works

Completion of the Construction Works shall be effected not later than the Target Completion Date, unless such date is extended in terms of this Agreement.

Upon the Construction Contractor giving notice to the Terminal Operator in terms of the relevant Construction Agreement of the anticipated date of completion of the Construction Works, the Terminal Operator shall promptly and, in any event within 7 (seven) Days after receipt of such notice, notify TNPA and the Independent Certifier of such anticipated date, provided that such notice shall be given not less than 14 (fourteen) Days before such anticipated date.

TNPA and the Independent Certifier shall inspect the Construction Works on such anticipated date of Construction Completion or as soon as reasonably practicable thereafter, but in any event within 7 (seven) Days after such anticipated date.

If the Independent Certifier is reasonably of the opinion that completion of the Construction Works has taken place, the Independent Certifier shall forthwith issue the Completion Certificate.

If the Independent Certifier is not satisfied that completion as set out in clause 28.4.4 has occurred, the Independent Certifier shall notify the Terminal Operator and TNPA of such failure to attain completion of the Construction Works within 5 (five) Business Days after the inspection referred to in clause 28.4.3 specifying those elements of the Terminal or other conditions that remain to be satisfied by the Terminal Operator.

The issuing of a Completion Certificate shall not be withheld or delayed notwithstanding that minor items have yet to be completed and/or attended to and such outstanding items shall be reflected in a Snagging List (as defined in clause 28.4.8).

The Independent Certifier shall issue a Completion Certificate within 5 (five) Business Days after the completion, to the Independent Certifier’s satisfaction, of the Construction Works specified in the notice contemplated in clause 28.4.5 and the satisfaction of any other conditions specified.

The Independent Certifier shall identify in a list ("Snagging List") appended to the Completion Certificate any unfulfilled obligations of the Terminal Operator ("Unfulfilled Obligations"), which the Terminal Operator has undertaken to complete in respect of the Construction Works and the time within such Unfulfilled Obligations are to be completed or certify that there are no Unfulfilled Obligations in respect of the Construction Works. The Terminal Operator shall attend to such Unfulfilled Obligations within the time specified in the Snagging List.

If the Terminal Operator has suffered delay in the execution of its rights or obligations in terms of this Agreement as a result of the Independent Certifier’s failure to act in accordance with this clause 28.4 (Completion of Construction Works), such event shall constitute a Relief Event and shall be governed by the provisions of clause 39 (Consequences of a Relief Event).

Archaeological matters

All fossils, coins, articles of value or antiquity, structures and other remains or things of geological or archaeological interest or burial sites discovered on the Site ("Archaeological Articles") shall (as between the Parties) be the property of TNPA. The Terminal Operator shall take all reasonable precautions to prevent its agents, representatives and employees, labour or other persons from removing or damaging any such Archaeological Articles. The Terminal Operator shall, immediately upon discovery of such Archaeological Articles, advise TNPA, who shall issue instructions for dealing with it, accordingly.

If the Terminal Operator has suffered delay in the execution of its rights or obligations in terms of this Agreement as a result of having followed TNPA’s instructions as contemplated in clause 28.5.1 or any obtaining the Consents required in respect of such Archaeological Articles and their removal or preservation, such event shall constitute a Relief Event and shall be dealt with in accordance with clause 39 (Consequences of a Relief Event).

Utilities and Utility wayleaves

TNPA shall arrange for Utilities between the port boundary and the Project Site provided that, for the avoidance of doubt, TNPA shall not be liable or responsible for any Utilities at the Terminal, including the removal and disposal of waste.

TNPA shall have the right to approve the establishment on or over and/or relocation from the Project Site, at the request of any public or private Utility, of Utility wayleaves including, but not limited to, power pylons or lines, water or gas pipes and telecommunication lines or pylons.

If such establishment and/or relocation has delayed the Construction Works or the Scheduled Operations Commencement Date or adversely affected the normal course of Operation and Maintenance, such event shall constitute a Relief Event and shall be dealt with in accordance with clause 39 (Consequences of a Relief Event).

Information relating to the Project and the Construction Works

The Terminal Operator shall furnish to TNPA, or any of its duly authorised representatives, all such reports and other such information in relation to the Project and the Construction Works as TNPA may reasonably request from time to time.

The Terminal Operator shall cause the Construction Contractor to provide directly to TNPA copies of the reports of the Construction Contractor as set forth in this Agreement and the relevant Construction Agreement.

Upon completion of any part of the Construction Works, the Terminal Operator shall supply TNPA with the Construction Documents, copies of all "as-built" drawings and such other technical and design information and completion records relating to the finished Construction Works as TNPA may reasonably request.

Disruption to Port and Port Users

The Terminal Operator shall ensure that none of the Construction Works cause any disruption to existing Port Users nor to activities on adjoining land except to the extent that such disruption cannot reasonably be avoided as a result of any Construction Works being carried out. Where disruption cannot reasonably be avoided, the Terminal Operator shall ensure that appropriate traffic and other appropriate management measures are implemented to minimise the effect of any such disruption on Port Users.

- Operations Commencement for the Project

The Terminal Operator shall with effect from the Operations Commencement Date, perform or procure the performance of Operation and Maintenance of the Terminal in accordance with the Operational Plan.

Within 30 (thirty) Days after the Operations Commencement Date, TNPA shall announce the Terminal open.

The Terminal Operator shall not operate the Terminal, provide services or charge or collect fees in respect of the services until the Independent Certifier has issued the Completion Certificate.

Approval to commence operations

TNPA shall, subject to any IMDG Code related permissions being obtained, authorise the commencement of operations and in accordance with the provisions of the Act, grant approval to the Terminal Operator to commence operations at the Terminal and shall at the same time announce the Terminal open and that the Terminal Operator is authorised to charge and collect fees in respect of the services, with effect from the date that the Independent Certifier issues the Operations Certificate. The date specified by TNPA in the relevant notice issued in respect of such approval, as the date upon which the aforesaid approval and authorisation comes into operation or takes effect shall be the Actual Operations Commencement Date.

Notwithstanding but without prejudice to the provisions of clause 29.2, the Terminal Operator shall not operate the Terminal or charge or collect fees in respect of the Service until the Independent Certifier has issued the Operations Certificate in terms of clause 28.4.

- Operation and Maintenance

Obligation to Operate and Maintain

During the Operations Period, the Terminal Operator shall be obliged to undertake Operation and Maintenance activities of the Terminal subject to, and in accordance with the terms of the Operational Plan and this Agreement.

Standards of Operation and Maintenance

Generally, the Operation and Maintenance of the Terminal shall be carried out in accordance with the Law and in conformity with the standard of care and workmanship prescribed in the Operational Plan, original equipment manufacture’s standard and TNPA’s Asset Maintenance Manual to the extent applicable to the Terminal, using equipment and materials which are of suitable quality for the purposes and uses intended and free of defects and deficiencies, and in accordance with the specifications of such equipment.

The Terminal Operator shall submit an annual maintenance programme for the Terminal in respect of Terminal Infrastructure and Terminal Equipment in accordance with the Schedule 22 (Annual Reporting).

Any changes to the annual maintenance programme, after such programme has been submitted to TNPA as contemplated in clause 30.2.2. shall require the prior approval of TNPA, which approval shall not be unreasonably withheld.

Management

The Terminal Operator shall ensure that, subject to the other provisions of this Agreement, the Terminal is open to operate the Terminal and that the use of the Terminal and operation of the Terminal are convenient and safe at all times and (for the avoidance of doubt) 24 (twenty-four) hours of each Day.

The Terminal Operator shall take all reasonable steps in the performance of its obligations hereunder in such a way so as to prevent the occurrence of any environmental or health and safety hazards.

The Terminal Operator shall otherwise manage the Terminal and all vessels using the Terminal in accordance with the Act, the Port Rules, the Operation and Maintenance Manuals and the Operational Plan.

The Terminal Operator shall at all times exercise  its rights strictly in compliance with the provisions of this Agreement and applicable Law.

Marketing

The Terminal Operator shall actively market the Terminal and the services of the Terminal Operator internationally. In the event that the marketing materials contains information of the Port, which is not in the public domain, the Terminal Operator shall submit all information, materials, documents and any other data that it intends to use in respect of its marketing campaign in respect of the marketing of the Terminal and the services of the Terminal Operator to TNPA for approval prior to its use thereof.

Within 30 (thirty) Days of the receipt by TNPA of the information, materials, documents and other data detailed in clause 30.4.1, TNPA shall either grant or withhold its consent in respect of the use thereof in the marketing of the Terminal and the services of the Terminal Operator, provided that TNPA shall not unreasonably withhold its consent.  If TNPA withholds its consent, it will provide its written reasons for such withholding at the time that it notifies the Terminal Operator that it is withholding its consent. If TNPA has withheld its consent in respect of any such information, materials, documents or other data, the Terminal Operator shall not be entitled to use it in the marketing of the Terminal and the services of the Terminal Operator.

Terminal Operator Performance and Penalties

The Terminal Operator shall use its best efforts to promote and develop the Terminal and the services of the Terminal Operator, in order to achieve optimum utilisation of the Terminal and Port Infrastructure and in a manner, which is consistent with sound business practices, the Business Case and International Best Practice.

Without limiting the generality of clause 30.5.1, but subject to clause 30.5.7, the Terminal Operator shall meet the Terminal Operator Performance Standards with the effect from the commencement of the Operations Period.

At the end of each period of 5 (five) Contract Years during the Operations Period the Parties shall meet to review and where necessary adjust the Terminal Operator Performance Standards.

The actual performance of the Terminal Operator will be reviewed quarterly by TNPA against the Terminal Operator Performance Standards. TNPA will provide the Terminal Operator with a list of all of the information which it reasonably requires the Terminal Operator to provide for each Quarter no later than 10 (ten) Business Days before the beginning of that Quarter.

In order to conduct the Quarterly review, the Terminal Operator shall provide TNPA, within 10 (ten) Business Days after the end of each Quarter, with all information that TNPA requires to assess the Terminal Operator's performance in that Quarter.

TNPA shall communicate its initial comments and any requests for additional information within 10 (ten) Business Days after the information has been supplied by the Terminal Operator in terms of clause 30.5.5, and will take into consideration any response by the Terminal Operator to these initial comments, provided that this response is submitted within 10 (ten) Business Days of the initial comments. Where TNPA makes a negative finding regarding any aspect of the performance of the Terminal Operator, it shall give reasonable notice to that effect to the Terminal Operator and representatives of TNPA and the Terminal Operator shall meet to discuss and develop a performance improvement plan or a performance remediation strategy, in terms of which:

a plan of action with appropriate timelines shall be implemented by the Terminal Operator without delay; and

the results thereof be submitted within the set timelines to TNPA for review and final decision and/or outcome.

When, in the opinion of the Terminal Operator, circumstances occur which may impact negatively on its achievement of its Terminal Operator Performance Standards, the Terminal Operator shall notify TNPA in writing within 10 (ten) Business Days of the occurrence and both the Terminal Operator and TNPA shall document the details of the occurrence.  The Terminal Operator Performance Standards may be relaxed in accordance with such terms as the Parties may agree, should the Terminal Operator be prevented or delayed in performing its obligations by reason of a Force Majeure event. The Terminal Operator Performance Standards may be reviewed and amended, by agreement between the Parties, in the case of any other event or circumstance demonstrably beyond the control of the Terminal Operator, which had a material, negative impact on the achievement of the targets by the Terminal Operator.

Subject to the rights of TNPA to terminate this Agreement under clause 48 (Termination for Terminal Operator Default), if the Terminal Operator fails to achieve the minimum performance standards set out under this clause 30.5 and Schedule 16C (Key Performance Areas) at the conclusion of the year under assessment (the “Assessment Period”), and such failure is not attributable to any action, inaction or breach by TNPA of its obligations under this Agreement ("Failure"), TNPA will notify the Terminal Operator of such Failure and the manner in which the Penalty, as shall be determined in accordance with the cascade formula in Schedule 17E (Penalty and Incentive Cascade Formula), shall be imposed.

If Terminal Operator achieves minimum performance standards set out under this clause 30.5 and Schedule 16C (Key Performance Areas) and does so better than in the previous Assessment Period, TNPA will notify the Terminal Operator of their entitlement to an Incentive applicable to it, as shall be determined in accordance with the cascade formula contained in Schedule 17E (Penalty and Incentive Cascade Formula).

The penalties payable in terms of clause 30.5.11 shall be in addition to any other amounts payable in respect of the Penalty Period. TNPA shall not be entitled to seek damages for any failure of the Terminal Operator to comply with the Terminal Operator Performance Standards and in respect of which there is a specified penalty in Schedule 11 (Penalties) or elsewhere in this Agreement. The provisions of this clause 30.5 (Terminal Operator Performance and Penalties) are, however, without prejudice to TNPA's rights to claim damages for any other breach or default, not related to Performance, of this Agreement or to exercise any other rights available to it at Law or under this Agreement arising as a result of any failure of the Terminal Operator as referred to in clause 30.5.8 or any other cause whatsoever.

Any monies due to TNPA or due by TNPA pursuant to the provisions of this clause 30.5 shall be payable within 30 (thirty) Days after certification by the TNPA (as the case may be) that the Terminal Operator is liable or is entitled (as the case may be) to such payment.

TNPA shall be entitled to set-off any amounts payable as aforesaid against any monies due or which may become due to the Terminal Operator under this Agreement or against any Performance Guarantee provided that, should the Terminal Operator notify TNPA with appropriate supporting information that the Terminal Operator has not committed the breach complained of and that no such right to set-off or deduct penalties has arisen. In the instance that a dispute arises under this clause, either Party shall approach an “Independent Expert” (a person with appropriate expertise in respect to) to determine whether TNPA shall be entitled to the aforesaid penalties, the costs of whom shall be borne by the Party that refers the dispute and who’s determination shall be final and binding. The payment or set-off of such penalties shall not relieve the Terminal Operator from any liability or from any of its obligations under this Agreement The payment, set-off of or claim in respect of such penalties shall not relieve the Terminal Operator from any liability or from any of its obligations under this Agreement. For the avoidance of doubt, the Operating Performance Guarantee shall also be given in respect of and cover the Terminal Operator's obligations in terms of this clause 30.5 (Terminal Operator Performance) as well as Schedule 17 (Terminal Operator Performance Standards) and Schedule 11 (Penalties).

In relation to any Penalty Period in respect of which a Failure occurs the Terminal Operator shall as part of the Annual Report envisaged in clause 31,  submit a written remedial plan to TNPA, which shall detail the remedial steps that the Terminal Operator will take during the Penalty Period immediately following the Penalty Period in respect of which such Failure arose, in order to remedy the Failure and to achieve compliance with the relevant Performance Standards.

If the Terminal Operator: (i) incurs a Failure and associated penalties in respect of any Penalty; and/or (ii) fails to submit a remedial plan in terms of clause 30.5.13; and/or (iii) fails to comply with a remedial plan submitted by it in terms of clause 30.5.13, TNPA shall be entitled to exercise its rights in accordance with the provisions of clause 43 (Terminal Operator Default).

The Parties agree that in the event that any penalties  incurred in terms of this clause 30.5 (Terminal Operator Performance and Penalties) are determined to be a penalty in terms of the Conventional Penalties Act, 1962, TNPA shall be entitled to claim liquidated damages from the Terminal Operator in lieu of the relevant penalty, in an amount equal to such penalty.

- Reporting Requirements

The Terminal Operator shall, annually, within 1 (one) Month after the approval of its Annual Report by its Relevant Authority, submit to TNPA such annual report (the "Annual Report") which shall set out a detailed written account of the following matters:

the Operation and Maintenance of the Terminal in respect of the relevant Review Year including the Terminal Operator’s compliance with the Operational Plan, the maintenance plan envisaged in clause 30.2.2 and the Performance Standards;

the extent to which the Terminal Operator’s undertakings contained in clause 13 (Empowerment Obligations) have been met, as well as documenting any other achievements in promoting empowerment initiatives;

the quality and level of the services provided by the Terminal Operator at the Terminal during the relevant Review Year;

the Terminal Operator’s compliance with the terms of this Agreement, the Act and the Regulations;

the Terminal Operator’s compliance in respect of any Occupational, Health and Safety legislation;

steps taken by the Terminal Operator to eliminate anti-competitive and discriminatory practices; and

the quality and level of performance with regard to such environmental criteria and social responsibility requirements as may have been set by TNPA during or prior to the relevant Review Year or required by other national legislation.

The Annual Report shall be provided in the format set out in Schedule [        ] (Annual Reporting), and shall address the matters set out above and shall also include detailed information in respect of the following:

such statistical information relating to its operations as may reasonably be required by TNPA; statistics on the number, type and size of vessels serviced at the Project Site; and statistics on the number of trucks handled at the Project Site interface with land transport and cargo dwell time statistics;

its Cargo forecast for the remainder of the Concession Period, or  such shorter period as may be specified, in a form determined by TNPA from time to time; and

future development and acquisition plans, including any required or proposed new Terminal Equipment, relating to the Terminal or any Service provided at the Terminal.

The Terminal Operator shall, if requested by TNPA in writing, submit to TNPA an executive summary of the Annual Report, excluding any Confidential Information and/or any information not required to be provided by the Terminal Operator, which summary may be disclosed to members of the public.

TNPA may require the Terminal Operator, at the Terminal Operator’s cost, to submit such additional information as may be reasonably necessary to explain or amplify any Annual Report or other report or information submitted by the Terminal Operator in terms of clause 31.1 above.

The Terminal Operator must, within 24 (twenty-four) hours of its occurrence or discovery, inform TNPA of:

any industrial dispute between the Terminal Operator and its employees;

any industrial accident or disaster involving any employee or agent of the Terminal Operator or any injury on duty or fatality;

any occurrence of fire within the Project Site;

any theft or pilferage within the Project Site or any theft or pilferage involving any Cargo in the Terminal Operator’s possession or control;

any proceedings or claim instituted or made against the Terminal Operator which could materially affect its ability to perform any obligation or to comply with any term or condition of this Agreement; and

any spillage or pollution that may have an impact on the Environment.

- Financial Accounts, Reports, inspection and reporting of changes

Financial accounts and auditors

The Terminal Operator shall arrange at its own expense and cost for an accounting and cost control system consistent with Generally Accepted Accounting Principles and for the appointment as auditors of a firm of independent accountants, for the Terminal.

The Terminal Operator shall keep all its financial books and records, for the Terminal at all times within South Africa. The accounts of the Terminal Operator will be kept in Rand. Such accounts and the reports of such accountants shall be provided to TNPA.

TNPA may meet with the Terminal Operator's auditors regarding the Terminal Operator's accounts and operations, for the Terminal twice in a Contract Year.  TNPA may also, at its own cost, require that officers of TNPA or a firm of independent accountants conduct additional audits of the Terminal Operator after 10 (ten) Days prior notice to the Terminal Operator in respect of the Terminal.

Right of Inspection

In accordance with the provision of Section 63 of the Act, the Terminal Operator shall furnish to TNPA any information that TNPA may reasonably request and shall permit representatives of TNPA to visit the Construction Works, the Terminal and the Project Site and Terminal, and any of the other offices where the business of the Terminal Operator is conducted, and to have access to the Terminal Operator's books of accounts and records, designs, drawings and generally to all information that is customarily available to any shareholder of the Terminal Operator and in connection with the Project, and shall make such information, books of accounts and records, drawings and other data relating to Operation and Maintenance in respect of the Terminal, available to TNPA. The Terminal Operator shall provide TNPA with full read only access to the Terminal Operator's computer for the review and monitoring of revenue collection at the Terminal.

Periodic Reports

Together with the Annual Report the Terminal Operator shall furnish TNPA with:

3 (three) copies of the Terminal Operator’s complete audited financial statements in respect of the preceding Contract Year  (which are consistent with the books of accounts and prepared in accordance with International Financial Reporting Standards), together with an audit report thereon, all in accordance with the requirements of the Laws and regulations pertaining to accounting;

a copy of any management letter or other communication sent by the auditors to the Terminal Operator or to its management in relation to the Terminal Operator’s financial, accounting and other systems, management and accounts.

The Terminal Operator shall furnish TNPA, as soon as practicable but in any event no later than 45 (forty-five) Days after the end of each Quarterly period of each Contract Year (except for the last Quarterly period of each financial year), with:

3 (three) copies of the Terminal Operator’s complete financial statements for such Quarterly period (which are consistent with its books of account and prepared in accordance with International Financial Reporting Standards, including in each such report a balance sheet, a statement of income and a statement of cash flows as of the end of and for such period, and for the period from the beginning of such year to the close of such Quarterly period, certified by an officer of the Terminal Operator, all in accordance with the requirements of the Laws and regulations pertaining to accounting;

a report on any factors materially and adversely affecting or which might materially and adversely affect the Terminal Operator’s business and operation or its financial condition;

a list of creditors that individually and when aggregated make up in excess of 10% of the total value of liabilities i.e. all individual creditors that makes up more than 10 % of total liabilities (financial obligations;

a statement describing in detail any Related Party Transaction during the respective period;

a report on the implementation and progress of the Project, containing such information as TNPA may reasonably require and disclosing any factors of which the Terminal Operator is aware materially and adversely affecting or which would be otherwise likely, materially and adversely to affect, the carrying out of the Project; and

a statement identifying separately the capital costs, construction costs and Operation and Maintenance costs, during the respective period, for the Terminal and the operation of the Terminal separately.

The Terminal Operator shall furnish to TNPA as soon as practicable, but in any event no later than 35 (thirty-five) Days prior to the end of each Contract Year, the projected profit and loss account and the budget for the following Contract Year, together with an analysis thereof.

The Terminal Operator shall furnish to TNPA as soon as practicable, but in any event no later than the end of each Quarterly period of each Contract Year, projected cash flow for the following Quarterly period, together with an analysis thereof.

The Terminal Operator shall immediately report to TNPA details of the following events:

any charge, lien or attachment imposed on the Terminal Infrastructure, the Terminal Equipment and/or any of the Terminal Operator’s property and any seizure thereof which charge, lien, attachment or seizure will have a material adverse effect on the ability of the Terminal Operator to Operate and Maintain the Terminal and/or to perform its obligations under this Agreement;

any transaction in respect of the shares of the Terminal Operator of which the Terminal Operator is aware;

any default under any Financing Agreement, the circumstances thereof and possible results as viewed by the Terminal Operator; and

any matter the Terminal Operator is aware of, which might influence the validity of this Agreement or any matter that constitutes a material breach, including without limitation, any possible Termination Event, the circumstances thereof, and possible results as viewed by the Terminal Operator.

The Terminal Operator shall provide a monthly written report to TNPA with respect to the matters specified in the Detailed Design, D & C Specifications and Operational Plan to be reported relating to provision of the Operation and Maintenance of the Terminal.

Delivery of records

For a period of not more than 12 (twelve) months following the termination of this Agreement for whatever reason, the Terminal Operator shall retain in safe custody and storage all such records as are referred to in clause 32.3 (Periodic Reports) which were in existence at the date of termination. Upon expiry of such period or such earlier date as may be agreed by TNPA and the Terminal Operator, the Terminal Operator shall deliver all such records (or where such records are required by legislation to remain with the Terminal Operator or the Terminal Operator’s shareholders, copies thereof) to TNPA or to its duly authorised representative, in such manner and at such location as TNPA shall determine. TNPA shall make such records available for inspection by the Terminal Operator at any reasonable time.

Reporting of changes

The Terminal Operator shall notify TNPA in the event that it:

makes or allows any change in or to its corporate structure, the Constitutional Documents or its financial year end;

makes or allows any material change in the Terminal Operator’s organisational structure, or any other material change which might materially adversely affect the performance of the Terminal Operator’s obligations under this Agreement;

save for the Associated Agreements, enter into any agreement or series of agreements in respect of the Terminal, which contemplates or could involve revenue or contractual obligation that is in excess of 10 % of the asset base and/or annual turnover and/or annual Operating expenditure;

enter into any Related Party Transaction;

enter into any agreement or incur any liability which is not in the ordinary course of business of the Terminal Operator; or

make any change in the insurance policies contemplated in clause 16 (Project Insurance).

The Terminal Operator shall notify TNPA of any claim brought or threatened which is reasonably likely to have a material effect on the Terminal Operator or on its ability to perform its obligations under this Agreement.

- Rights of Access

Subject to the reasonable safety requirements of the Terminal Operator, TNPA, and/or their representatives may, at their own risk, enter upon the Terminal (or any other site or property used by the Terminal Operator for the purposes of the Project) to inspect the Construction Works, the Terminal and Operation and Maintenance, and to monitor compliance by the Terminal Operator with its obligations under this Agreement.

TNPA and/or their representatives may at all times, but subject to the reasonable security and safety requirements of the Terminal Operator, enter upon any property used by the Terminal Operator as training or workshop facilities and places where work is being prepared or materials being obtained for the Project.

The Terminal Operator shall procure that adequate facilities are made available to TNPA, and/or their representatives and that reasonable assistance is given for the purposes of clauses 33.1 and 33.2, subject to the Terminal Operator’s construction or operational requirements not being adversely affected and to reimbursement of any reasonable costs or expenses of the Terminal Operator.

- Authority Changes

TNPA shall have the right to require changes to be made to the D&C Specifications and the Operational Plan in accordance with this clause ("Authority Changes"), in which event TNPA shall serve notice thereof ("Authority Notice of Change") on the Terminal Operator.  Such Authority Changes shall always provide for any variation of the Terminal Operator’s obligations under this Agreement and the Associated Agreements and be technically feasible.

The Authority Notice of Change shall:

set out the Authority Change required in sufficient detail to enable the Terminal Operator to calculate and provide the estimated revised costs of the Project in accordance with clause 34.3 ("Estimate");

require the Terminal Operator to provide TNPA, within such period as determined by TNPA, (which period shall not be less than 28 (twenty-eight) Days after receipt by the Terminal Operator of the Authority Notice of Change), with the Estimate.

As soon as practicable and in any event within the period specified in the Authority Notice of Change, the Terminal Operator shall deliver the Estimate to TNPA. The Estimate shall include the opinion of the Terminal Operator on:

any impact on completion of the Construction Works;

any impact on the performance of the Terminal Operator’s rights or obligations under this Agreement and any impact on the Terminal Operator’s obligations to third parties;

any amendment required to this Agreement and/or any Associated Agreement as a result of the Authority Change;

any estimated revised Project costs that result from the Authority Change;

any capital expenditure that is required or no longer required as a result of the Authority Change; and

the proposed method of certification of any construction or operational aspects of the Terminal Operator’s obligations under this Agreement required by the Authority Change if not covered by the procedures set forth in the D&C Specifications, and Operation and Maintenance.

As soon as practicable after TNPA receives the Estimate. TNPA shall assess the Estimate and where necessary the Parties shall discuss and agree the issues set out in the Estimate. In such discussions TNPA may modify the Authority Notice of Change, in which case the Terminal Operator shall, as soon as practicable and in any event within such period as determined by TNPA (which period shall not be less than 28 (twenty-eight) Days after receipt by the Terminal Operator of such modification), notify TNPA of any consequential changes to the Estimate.

As soon as practicable after the contents of the Estimate have been agreed, TNPA shall:

confirm the Estimate (as modified); or

withdraw the Authority Notice of Change.

If TNPA does not confirm the Estimate (as modified) within 30 (thirty) Days after the contents of the Estimate having been notified to it in accordance with clause 34.4 or determined pursuant to clause 34.5, then the Authority Notice of Change shall be deemed to have been withdrawn.

If the Estimate (as modified) involves estimated capital expenditure, then the Terminal Operator shall use its reasonable endeavours to obtain funding for the whole of the estimated capital expenditure, on terms satisfactory to the Terminal Operator.

If the Terminal Operator has used its reasonable endeavours to obtain funding for the whole of the estimated capital expenditure but has been unable to do so within 60 (sixty) Days after the date that TNPA confirmed the Estimate, then the Terminal Operator shall have no obligation to carry out the Authority Change, unless TNPA agrees to pay the cost involved.

TNPA may, at any time following the date on which the Estimate is confirmed, agree to meet all or, to the extent the Terminal Operator has obtained funding for part of the capital expenditure, the remaining part of the estimated capital expenditure.

If the Estimate has been confirmed by TNPA and TNPA has agreed to meet all or part of the capital expenditure pursuant to clause 34.9, then the Terminal Operator shall be entitled to compensation as set forth in clause 39 (Consequences of a Relief Event).

If the Authority Notice of Change is deemed to be withdrawn in terms of clause 34.6 or if TNPA has confirmed the Estimate and has agreed to meet all or part of the capital expenditure as envisaged in clause 34.10, but TNPA thereafter withdraws the Authority Notice of Change, TNPA shall pay to the Terminal Operator the reasonable costs of providing the Estimate.

# PART IV – FINANCIAL PROVISIONS

- Fees in respect of services

The Terminal Operator shall have the exclusive right and obligation for its benefit and risk to levy and collect tariffs in respect of the services of the Terminal Operator, with effect from the Operations Commencement Date.

Neither  TNPA or any other Relevant Authority shall incur or assume any liability for or in connection with the tariffs charged in respect of the services of the Terminal Operator, any system used in respect of such fees or any defect or deficiency therein.

No later than 3 (three) months before the Scheduled Operations Commencement Date, the Terminal Operator shall submit to TNPA the initial tariff rates which it intends to charge in respect of the services of the Terminal Operator with effect from the Operations Commencement Date.

The Terminal Operator must submit to TNPA annually from the Operations Commencement Date, any adjustments to tariff rates which the Terminal Operator intends on implementing and that are in accordance with the necessary statutory and regulatory approvals.

All costs and expenses related to and arising from the charging and collection of tariffs shall be borne by the Terminal Operator.

Tariffs shall be charged and collected in Rands.

- Refinancing

The Terminal Operator shall promptly notify TNPA in writing prior to taking any steps to implement any proposed Refinancing. Such notice shall include:

full details of any proposed amendments to be made to or waivers granted under any of the Project Documents to give effect to such Refinancing;

a copy of the proposed financial model relating to such Refinancing (if any) and the basis for the assumptions used in that financial model;

the reasons for such Refinancing; and

any other information that may be reasonably necessary to enable TNPA to assess such Refinancing having regard to the provisions of this clause 36  (Refinancing).

- Foreign exchange risk

To the extent that the Terminal Operator at any time enters into any agreement in any currency whereby the risk of currency fluctuations is hedged, TNPA shall not in any circumstances be liable for such hedging arrangements and the Terminal Operator shall not enter into  any such arrangements whereby TNPA is or may become so liable. The costs and Losses arising out of such hedging arrangements shall not be included in or form part of any amounts payable by TNPA to the Terminal Operator on the Termination of this Agreement.

- Default Interest

Interests shall accrue on all overdue amounts payable in terms of this Agreement at the prime overdraft interest rate charged by First National Bank, a division of First Rand Bank Limited (or should First National Bank or First Rand Bank Limited cease to exist, any other major commercial bank in South Africa) plus 2% (two percent).

# PART V – RELIEF, AND FORCE MAJEURE EVENTS, CHANGE OF LAW

- Consequences of a Relief Event

If and to the extent that a Relief Event:

directly causes a delay in the Operations Commencement Date; and/or

materially adversely affects the ability of the Terminal Operator to perform any of its obligations under this Agreement, then the Terminal Operator shall be entitled to apply for relief from any rights of TNPA arising under clause 43 (Terminal Operator Default) and from its obligations under this Agreement.

To obtain relief, the Terminal Operator must:

as soon as practicable, and in any event within 14 (fourteen) Days after it became aware that the Relief Event has caused or is likely to cause delay and/or materially adversely affect the ability of the Terminal Operator to perform its other obligations, give to TNPA a notice of its claim for relief from its obligations under the Agreement, including full details of the nature of the Relief Event, the date of occurrence and its likely duration;

within 10 (ten) Days of receipt by TNPA of the notice referred to in clause 39.2.1 above, give full details of the relief claimed; and

demonstrate to the reasonable satisfaction of TNPA that:

the Terminal Operator and its Subcontractors could not have avoided such occurrence or consequences by steps which they might reasonably be expected to have taken, without incurring material expenditure;

the Relief Event directly caused the delay to the Target Completion Date or the Scheduled Operations Commencement Date or the need for relief from other obligations under the Agreement;

the time lost and/or relief from the obligations under the Agreement claimed could not reasonably be expected to be mitigated or recovered by the Terminal Operator acting in accordance with International Best Practice, without incurring material expenditure; and

the Terminal Operator is using reasonable endeavors to perform its obligations under the Agreement;

If the Terminal Operator has complied with its obligations under clause 39.2.3 above, then:

the Target Completion Date and/or the Scheduled Operations Commencement Date shall be postponed by such time as shall be reasonable for such a Relief Event, taking into account the likely effect of delay; and/or

TNPA shall not be entitled to exercise its rights to terminate the Agreement under clause 43 (Terminal Operator Default) and, subject to clause 39.3 below, shall give such other relief as may be deemed reasonable for the Relief Event.

If the information required by clause 39.2 above is provided after the dates referred to in that clause, then the Terminal Operator shall not be entitled to any relief during the period for which the information is delayed.

The Terminal Operator shall notify TNPA if at any time it receives or becomes aware of any further information relating to the Relief Event, giving details of that information to the extent that such information is new or renders information previously submitted materially inaccurate or misleading.

If a Relief Event continues for a period in excess of 180 (one hundred and eighty) Days, the Parties shall meet in order to find a mutually satisfactory solution for dealing with such prolonged Relief Event.

If the Parties cannot agree the extent of the relief required, or TNPA disagrees that a Relief Event has occurred or that the Terminal Operator is entitled to any extension of the Target Completion Date and/or the Scheduled Operations Commencement Date and/or relief from other obligations under this Agreement, the Parties shall resolve the matter in accordance with clause 57.7 (fast-track dispute resolution).

- Force Majeure

For the purposes of this Agreement, "Force Majeure" means any of the following events or circumstances to the extent that they are uninsurable:

war, civil war, armed conflicts, or terrorism; or

nuclear contamination unless the Terminal Operator and/or any Subcontractor is the source or cause of the contamination; or

chemical or biological contamination of the Construction Works and/or the Facilities and/or the Project Site from any of the events referred to in clause 41.1.1 above; or

the outbreak of communicable diseases classified and declared as a pandemic by the World Health Organisation,  which directly causes either Party to be unable to comply with all or a material   part of its obligations under this Agreement.

Subject to clause 41.3, the Party claiming relief shall be relieved from liability under this Agreement to the extent that, by reason of the Force Majeure Event, it is not able to perform all or a material part of its obligations under this Agreement.

Where a Party is (or claims to be) affected by an event of Force Majeure:

it shall take all reasonable steps to mitigate the consequences of such an event upon the performance of its obligations under this Agreement, resume performance of its obligations affected by the event of Force Majeure as soon as practicable and use all reasonable endeavors to remedy its failure to perform; and

it shall not be relieved from liability under this Agreement to the extent that it is not able to perform, or has not in fact performed, its obligations under this Agreement due to its failure to comply with its obligations under clause 41.3.1.

The Party claiming relief shall serve written notice on the other Party within 5 (five) Business Days of it becoming aware of the relevant Force Majeure Event. Such initial notice shall give sufficient details to identify the particular event claimed to be an event of Force Majeure.

A subsequent written notice shall be served by the Party claiming relief on the other Party within a further 10 (ten) Business Days, which notice shall contain such relevant information relating to the failure to perform (or delay in performing) as is available, including (without limitation) the effect of the Force Majeure Event on the ability of the Party to perform, the action being taken in accordance with clause 41.3, the date of the occurrence of the Force Majeure Event and an estimate of the period of time required to overcome it and/or its effects.

The Party claiming relief shall notify the other as soon as the consequences of the Force Majeure Event have ceased and when performance of its affected obligations can be resumed.

If, following the issue of any notice referred to in clause 41.5, the Party claiming relief receives or becomes aware of any further information relating to the Force Majeure Event and/or any failure to perform, it shall submit such further information to the other Party as soon as reasonably possible.

The Parties shall endeavor to agree any modifications to this Agreement which may be equitable having regard to the nature of an event or events of Force Majeure.  Clause 57 (Dispute Resolution) shall not apply to a failure of TNPA and the Terminal Operator to reach agreement pursuant to this clause 41.8, and this Agreement shall terminate in terms of clause 45.4 (Termination for Force Majeure) if no such agreement is reached.

- Unforeseeable Conduct

Should any Unforeseeable Conduct occur which materially and adversely affects the general economic position of the Terminal Operator, the Terminal Operator shall be entitled to such relief from TNPA as shall place the Terminal Operator in the same overall economic position as the Terminal Operator would have been in but for such Unforeseeable Conduct.

The Terminal Operator claiming the occurrence of the Unforeseeable Conduct shall give written notice to TNPA or the Relevant Authority containing reasonable particulars of such conduct and its likely economic consequences to the Terminal Operator.

The TNPA or the Relevant Authority shall have 60 (sixty) Days from the date of receipt of such notice to effect a remedy for the Unforeseeable Conduct which restores the general economic position of the Terminal Operator to that which it would have been in if such Unforeseeable Conduct had not occurred. If the TNPA or the Receiving Authority does not, effect such a remedy within such period, the Parties shall consult within 10 (ten) Business Days after the expiration of such period with a view to reaching a mutually satisfactory resolution of the situation.  If a mutually satisfactory resolution has not been reached within such 10 (ten) Business Day consultation period, the matter shall be dealt with in accordance with clause 57 (Dispute Resolution).

The Terminal Operator shall use all reasonable endeavours to minimise and mitigate the effects of any Unforeseeable Conduct.

# PART VI – TERMINATION

- Terminal Operator Default

Definition

"Terminal Operator Default" means any of the following events or circumstances:

any arrangement, composition or compromise with or for the benefit of creditors (including any voluntary arrangement as defined in the Insolvency Act, 1936 or the Companies Act) being entered into by or in relation to the Terminal Operator;

a liquidator, business rescue practitioner or the like taking possession of or being appointed over, or any business rescue, winding-up, execution or other process being levied or enforced (and not being discharged within 20 (twenty) Business Days) upon, the whole or any material part of the assets of the Terminal Operator (in any of these cases, where applicable, whether provisional or final, and whether voluntary or compulsory);

the Terminal Operator ceasing to carry on business;

a resolution being passed, or an order being made for the administration or the commencement of business rescue proceedings, winding-up, liquidation or dissolution of the Terminal Operator (in any of these cases, where applicable, whether provisional or final and whether voluntary or compulsory);

the Terminal Operator fails to complete the Construction Works on or before the Target Completion Date;

the Terminal Operator fails to commence operations at the Terminal on or before the Scheduled Operations Commencement Date;

the Terminal Operator commits a breach of any of its material obligations under this Agreement;

the Terminal Operator abandons the Construction Works (other than as a consequence of a breach by TNPA of its obligations under this Agreement);

the Terminal Operator, in operating the Terminal, ceases to provide all or a substantial part of the services in accordance with this Agreement (other than as a consequence of a breach by TNPA of its obligations under this Agreement);

the Terminal Operator failing to achieve the specific and quantifiable targets detailed in Schedule [           ] (Penalties) for 3 (three) consecutive years;

the Terminal Operator failing to comply with any provision of clause 18 (Changes in the Terminal Operator);

the Terminal Operator fails to pay any sum or sums due to TNPA under this Agreement (which sums are not bona fide in dispute) which, either individually or in aggregate, exceeds R 10 000 000.00 (ten million rand) over a period of 12 months and such failure continues for 20 (twenty) Business Days from receipt by the Terminal Operator of a notice of non-payment from TNPA;

the Terminal Operator failing to maintain any required insurance in terms of Clause 16 (Project Insurance) and failing to remedy such breach within 14 (fourteen) Days of receiving a written notice from TNPA requiring it to do so or such time reasonably required to reinstate the insurance;

any breach of any provision of this Agreement, other than a breach of any material obligation as envisaged in Clause 43.1.7 has occurred more than once and:

TNPA has given an initial warning notice to the Terminal Operator describing that breach in reasonable detail and stating that if that breach persists or recurs then TNPA may take further steps to terminate the Agreement; and

TNPA has issued a second and final warning notice following the persistence or re-occurrence of that breach in the period of 90 (ninety) Days after the initial warning notice, stating that if that breach persists or re-occurs within the period of 90 (ninety) Days after the final warning notice then TNPA may terminate the Agreement on 30 (thirty) Days’ notice to the Terminal Operator; and

such breach re-occurs within the said 90 (ninety) Day period referred to in clause 43.1.14.2.

- Notification

The Terminal Operator shall notify TNPA of the occurrence, and provide details, of any Terminal Operator Default and of any event or circumstance which is likely, with the passage of time or otherwise, to constitute or give rise to a Terminal Operator Default, in either case promptly upon the Terminal Operator becoming aware of its occurrence.

TNPA ’s options

On the occurrence of a Terminal Operator Default, or within a reasonable time after TNPA becomes aware of the same, TNPA may, subject to the provisions of Clause 57 (Dispute Resolution):

in the case of the Terminal Operator Default referred to in clauses 43.1.1, 43.1.2, 43.1.3, 43.1.4, 43.1.5, 43.1.7, 43.1.8, 43.1.9, 43.1.10, 43.1.12, 43.1.13 and 43.1.14, terminate this Agreement in its entirety by notice in writing having immediate effect; and

while the same is subsisting, in the case of any other Terminal Operator Default referred in clauses 43.1.6 and 43.1.14, serve notice of default on the Terminal Operator requiring the Terminal Operator at the Terminal Operator’s option either:

to remedy the Terminal Operator Default referred to in such notice of default (if the same is continuing) within 30 (thirty) Business Days of such notice of default; or

to put forward within 20 (twenty) Business Days of such notice of default a reasonable programme for remedying the Terminal Operator Default. The programme shall specify in reasonable detail the manner in, and the latest date by, which such Terminal Operator Default is proposed to be remedied. The Terminal Operator shall only have the option of putting forward a programme in accordance with this clause if it first notifies TNPA within 15 (fifteen) Business Days of such notice of default that it proposes to do so.

Remedy Provisions

Where the Terminal Operator puts forward a programme TNPA shall have 30 (thirty) Business Days from receipt of the same within which to notify the Terminal Operator that it does not accept the programme, failing which TNPA shall be deemed to have accepted the programme. TNPA shall act reasonably in rejecting the programme.  Where TNPA notifies the Terminal Operator that it does not accept the programme, the Parties shall endeavour within the following 20 (twenty) Business Days to agree on any necessary amendments to the programme put forward. If, following the necessary discussions and amendments, the programme is still not acceptable to TNPA then either party may refer the programme for resolution in accordance with clause 57.7 (fast-track dispute resolution).

If:

the Terminal Operator Default notified in a notice of default is not remedied before the expiry of the period referred to in the notice; or

where the Terminal Operator puts forward a programme which has been accepted by TNPA or has been determined to be reasonable and the Terminal Operator fails to achieve any element of the programme or to complete the programme by the specified end date for the programme (as the case may be); or

if any programme put forward by the Terminal Operator is rejected by TNPA  as not being reasonable, and the dispute resolution procedure does not find against that rejection, then TNPA may terminate this Agreement in its entirety by written notice to the Terminal Operator with immediate effect, provided that if the Terminal Operator’s execution of the programme is adversely affected by the occurrence of a Force Majeure Event or a Relief Event then, subject to the Terminal Operator complying with the mitigation and other requirements in this Agreement concerning Force Majeure Events or Relief Events (as the case may be), the time for execution of the programme or any relevant element of it shall be deemed to be extended by a period equal to the delay caused by the Force Majeure Event or Relief Event (as the case may be) which is agreed by the Parties or determined in accordance with clause 57.7 (fast-track dispute resolution).

TNPA’s Costs

The Terminal Operator shall reimburse TNPA with all costs incurred by TNPA in exercising any of its rights in terms of Clause 43 (Terminal Operator Default) (including, without limitation, any relevant increased administrative expenses).

TNPA shall not exercise, or purport to exercise, any right to terminate this Agreement except as expressly set out in this Agreement. The rights of TNPA (to terminate or otherwise) under this clause are in addition (and without prejudice) to any other right which TNPA  may have in law to claim the amount of loss or damages suffered by TNPA  on account of the acts or omissions of the Terminal Operator (or to take any action other than termination of this Agreement).

- TNPA Default

Definition "TNPA Default" means any one of the following events:

an expropriation or requisition of a material part of the Terminal and/or shares of the Terminal Operator, or a material part of the Terminal being removed from the possession of the Terminal Operator by TNPA, other than in terms of this Agreement;

a failure by TNPA to make payment of any amount or amounts that are due and payable by TNPA under this Agreement (which amounts are not bona fide in dispute) which, either singly or in aggregate exceeds the sum of R10, 000, 000 (ten  million rand) over a period of 12 months and such failure continued for 20 (twenty) Business Days from receipt by TNPA  of a notice of non-payment from the Terminal Operator; and

a breach by TNPA of its obligations under this Agreement which substantially frustrates or renders it impossible for the Terminal Operator to perform its obligations under this Agreement for a continuous period of 90 (ninety) Days.

For the avoidance of doubt, nothing in clause 45.1 shall preclude, prohibit or hamper the Government from undertaking any restructuring or reorganisation of the affairs, rights, obligations, assets or liabilities of TNPA.

Termination for TNPA Default

On the occurrence of TNPA Default, or within 60 (sixty) Days after the Terminal Operator becomes aware of same, the Terminal Operator may serve notice on TNPA of the occurrence (and specifying details) of such TNPA Default. If the relevant matter or circumstance has not been remedied or rectified within 30 (thirty) Business Days of such notice, the Terminal Operator may serve a further notice on TNPA terminating this Agreement with immediate effect.

The Terminal Operator shall not exercise or purport to exercise any rights to terminate this Agreement (or accept any repudiation of this Agreement) except as expressly provided for herein.

Termination for Force Majeure

If, in the circumstances referred to in clause 41 (Force Majeure), the Parties have failed to reach agreement on any modification to this Agreement pursuant to that Clause within 180 (one hundred and eighty) Days of the date on which the Party affected serves notice on the other Party in accordance with that clause, either Party may at any time afterwards terminate this Agreement by written notice to the other Party having immediate effect, provided always that the effects of the relevant events of Force Majeure continue to prevent either Party from performing any material obligation under this Agreement.

- Invalidation in terms of Section 67 of the Act

In the event that it is necessary to change the use to which the Terminal is put in order to improve the safety, security, efficiency and effectiveness of the operations of the Port in accordance with section 67(1)(a) and section 67(1)(b) of the Act, and the new use is incompatible with this Agreement, TNPA  may issue a directive, subject to the provisions of section 67(2) (b) of the Act, stipulating that this Terminal Operator Agreement is invalid from the date stipulated in that directive.

- Effects of Termination

Notice of Termination

Notwithstanding any provision of this Agreement, on service of a notice of termination, this Agreement shall only terminate in accordance with the provisions of this clause 47 (Effects of Termination).

Continued effect - no waiver

Notwithstanding any breach of this Agreement by either Party, and without prejudice to any other rights which the other Party may have in relation to it, the other Party may elect to continue to treat this Agreement as being in full force and effect and to enforce its rights under this Agreement. The failure of either Party to exercise any right under this Agreement, including any right to terminate this Agreement and any right to claim damages, shall not be deemed a waiver of such right for any continuing or subsequent breach.

Continued performance

Subject to any exercise by TNPA of its rights to perform, or to procure a third party to perform, the obligations of the Terminal  Operator, the Parties shall continue to perform their obligations under this Agreement, notwithstanding the giving of any notice of default or notice of termination, until the termination of the Agreement becomes effective in accordance with the provisions of this clause 47 (Effects of Termination).

Transfer to TNPA of the Terminal, Associated Agreements and other assets.

On the expiry or termination of this Agreement or, where applicable, the service of a notice of termination in accordance with this Agreement for any reason:

if that occurs prior to the Target Completion Date, in so far as any transfer shall be necessary fully and effectively to transfer property to TNPA , the Terminal Operator shall transfer to, and there shall vest in, TNPA  such part of the Construction Works and/or the Facilities as shall have been constructed and such items of the plant and equipment as shall have been procured by the Terminal Operator, and if TNPA  so elects:

all plant and all materials on or near to the Project Site shall remain available to TNPA for the purposes of completing the Construction Works;

the construction plant shall remain available to TNPA for the purposes of completing the Construction Works, subject to payment of the Terminal Operator's reasonable costs; and

if TNPA so elects, the Terminal Operator shall procure that any of the Associated Agreements specified by TNPA  are assigned to TNPA  or any third party nominated by it, provided that where termination occurs under clause 45 (TNPA Default), the consent of the relevant Subcontractors shall be required. Where TNPA does not so elect, or any Subcontractor whose consent is required refuses that consent, the Terminal Operator shall procure that all relevant Associated Agreements automatically terminate when this Agreement terminates.

If it occurs after the Completion Date, on service of a notice of termination in accordance with this Agreement for any reason, the Terminal Operator shall:

engage TNPA with the view to facilitating the “hand over and use” of the Terminal, Terminal Infrastructure and Terminal Equipment for the TNPA to fulfill its statutory obligations as an operator of last resort, on such further terms and conditions as may be agreed to in writing between the Parties, failing which the Terminal Operator shall “hand over” the Terminal to TNPA on payment of appropriate Compensation as provided for in Part VII of this Agreement;

where possible, procure that any Subcontractor shall (as the case may be), transfer to TNPA, free from any security interest full and unencumbered title in and to all or any part of the Terminal required by TNPA in connection with the Project;

procure that any Intellectual Property Rights shall be provided to TNPA and TNPA shall be granted a perpetual non-exclusive, royalty-free license to use such Intellectual Property Rights;

deliver to TNPA (as far as not already delivered to TNPA) one complete set of:

"as built drawings" showing all alterations made to the Facilities since the commencement of operation of the Terminal;

Maintenance, Operation and training manuals for the Terminal; and

the historical operating data and plans of the Terminal, its furniture, fittings and Equipment in a format acceptable to TNPA;

use all reasonable endeavours to procure that the benefit of all manufacturer's warranties in respect of mechanical and electrical plant and equipment used or made available by Terminal Operator under this Agreement and included in the Terminal are assigned, or otherwise transferred, to TNPA;

deliver to TNPA the information referred to in clause 32 (Financial Accounts, Reports, inspection and reporting of changes), except where such documents are required by Law to be retained by the Terminal Operator or any Subcontractor concerned, in which case complete copies shall be delivered to TNPA ; and

ensure that provision is made in all contracts relating to the Operation and Maintenance of the Terminal, excluding commercial contracts concluded between the Terminal Operator and its customers that TNPA will be in a position to exercise its rights, and the Terminal Operator will be in a position to comply with its obligations, under this clause 47.4.1.3.

Termination

On completion of the transfer required by clause 47.4 (transfer to TNPA  of Terminal, Associated Agreements and other assets) (except in so far as any of the requirements of that clause may be waived by TNPA ), this Agreement shall terminate and, save as provided in clause 47.7 (Continuing Obligations), all rights and obligations of TNPA and the Terminal Operator under this Agreement shall cease and be of no further force and effect.

Transitional arrangements

On the termination of this Agreement for any reason, for a period of 3 (three) months both before and after that expiry or any earlier termination, Terminal Operator shall have the following duties:

the Terminal Operator shall co-operate fully with TNPA and any Person who is providing services in the nature of any of the services of the Terminal Operator or any part of thereof , in order to achieve a smooth transfer of the manner in which TNPA  obtains services in the nature of the services of the Terminal Operator and to avoid or mitigate in so far as reasonably practicable any inconvenience or any risk to the health and safety of the employees of TNPA, the Port Users and members of the public;

the Terminal Operator shall as soon as practicable remove from the Project Site all property not required by TNPA  pursuant to clause 47.4 (transfer to TNPA  of the Terminal, Associated Agreements and other assets) and if it has not done so within 20 (twenty) Business Days after any notice from TNPA  requiring it to do so, TNPA  may (without being responsible for any loss, damage, costs or expenses) remove and sell any such property and shall hold any proceeds less all costs incurred for the credit of the Terminal Operator;

the Terminal Operator shall, by no later than the expiry or the date of any earlier termination of this Agreement becoming effective, deliver to TNPA:

any keys, remote access apparatus and computer access cards to the Terminal;

without prejudice to Clause 14 (Access to documents, copyright and related matters), any copyright licenses for any computer programmes (or licenses to use the same) necessary for the operation of the Terminal (but excluding computer programmes which have been developed or acquired by the Terminal Operator for its own use and not solely for the purposes of provision of any of the services at the Terminal or the assignment or transfer of which is otherwise restricted); and

the Terminal Operator shall as soon as practicable vacate the Project Site and (without prejudice to the rest of this Clause 47 (Effects of Termination)) shall leave the Project Site and the Terminal in a safe, clean and orderly condition;

If TNPA wishes to conduct a tender process with a view to entering into a contract for the provision of services provided by the Terminal Operator (which may or may not be the same as, or similar to, such services or any of them) following earlier termination of this Agreement, the Terminal Operator shall co-operate with TNPA fully in such tender process including (without limitation) by:

providing any information which TNPA may reasonably require to conduct such tender excluding any information which is commercially sensitive to the Terminal Operator (and, for the purpose of this sub-clause, commercially sensitive shall mean information which would if disclosed to a competitor of the Terminal Operator give that competitor a competitive advantage over the Terminal Operator and thereby prejudice the business of the Terminal Operator, but shall exclude any information dealing with employment matters); and

assisting TNPA, by providing all (or any) participants in such tender process with access to the Project Site and the Terminal.

Continuing Obligations

Save as otherwise expressly provided in this Agreement:

termination of this Agreement shall be without prejudice to any accrued rights and obligations under this Agreement as at the date of termination;

termination of this Agreement shall not affect the continuing rights and obligations of the Terminal Operator and TNPA under clauses 1 (Definitions and Interpretation), 7 (Indemnity), 8 (Terminal Operator's warranties and undertakings), 12 (Environmental Compliance), 14 (Access to documents, copyright and related matters), 15.1 (Delivery of Performance Guarantees), 19 (TNPA's Assistance and Rights and Limitations on Liability), 47.6 (Transitional Arrangements), 47.7 (Continuing Obligations), 55 (Corrupt gifts and fraud), 56 (Expert Determination), 57 (Dispute Resolution), and 58 (Information and Audit Access) or under any other provision of this Agreement which is expressed to survive termination or which is required to give effect to such termination or the consequences of such termination; and

The continuing obligations referred to in this clause 47.7 shall extinguish on the conclusion of the “hand over” of the Terminal to the satisfaction of both the Terminal Operator and TNPA.

- Termination Amount on Terminal Operator Default

Retendering Election

Upon the occurrence of a Terminal Operator Default and subject to clause 48.1.3, TNPA shall be entitled either to:

retender the operation of the Terminal in accordance with clause 48.2 (retendering procedure); or

exercise its rights as provided for in clause 47.4 and 47.6  request the Terminal Operator to vacate and hand back the Terminal and/or exercise its option to purchase the Terminal Equipment from the Terminal Operator in accordance with clause 48.1.3hereof below.

Subject to clause 48.1.3, TNPA shall notify the Terminal Operator of its election on or before the date falling 60 (sixty) Days after the Termination Date.

TNPA shall not be entitled to elect to retender the operation of the Terminal for the remaining portion of the Project Term if the Lenders have stepped-in and the Agent has demonstrated to TNPA that there are less than 3 (three) parties (each meeting the criteria in the definition of “Substitute Entity” in the FDA) who have pre-qualified pursuant to an RFQ issued by the Lenders for the operation of the Terminal for the remaining portion of the Project Term.

Retendering Procedure

If TNPA elects to retender the operation and maintenance of the Terminal under clause 48.1 (retendering election), the following provisions shall apply:

The Terminal Operator and/or its Members shall be precluded from participating, whether directly or indirectly in any manner, whatsoever in the retendering procedure.

The objective of the retendering procedure, among others, shall be to establish and (subject to clause 48.2.11) pay to the Terminal Operator and/or Lender, as the case may be the Highest Compliant Tender Price, as a result of the Tender Process.

TNPA shall (subject to any legal requirements preventing it from doing so) use its reasonable endeavours to complete the Tender Process as soon as practicable.

TNPA shall notify the Terminal Operator of the qualification criteria and the other requirements and terms of the Tender Process, including the timing of the Tender Process, and shall act reasonably in setting such requirements and terms.

The Terminal Operator authorises the release of any information that is reasonably required as part of the Tender Process by TNPA, which TNPA would otherwise be prevented from releasing under clause 14 (Access to documents, copyright and related matters).

The Terminal Operator may, at its own cost, appoint a Tender Process Monitor for the purposes of observing and reporting to the Terminal Operator on TNPA’s compliance with the Tender Process and making representations the TNPA in respect thereof. The Tender Process Monitor will not disclose any Confidential Information to the Terminal Operator, the Lenders or any other person (and shall provide an undertaking to TNPA to such effect as a condition of its appointment) but shall be entitled to advise the Terminal Operator and/or the Lenders as to whether it considers that TNPA has acted in accordance with the Tender Process.

The Tender Process Monitor shall be required to enter into a confidentiality agreement with TNPA in a form acceptable to TNPA and shall be entitled to attend all meetings relating to the Tender Process. In addition, the Tender Process Monitor shall be entitled to inspect copies of the tender documentation and bids and shall make written representations to TNPA regarding compliance with the Tender Process.  The Tender Process Monitor shall be required to make all representations in a timely manner as the Tender Process proceeds.  TNPA shall not be bound to consider or act upon such representations but acknowledges that such representations may be referred to by the Terminal Operator in the event that the Terminal Operator refers a dispute relating to the Tender Process  to dispute resolution in accordance with clause 57.7 (fast-track dispute resolution).

TNPA shall, with the express written consent of the Terminal Operator, require bidders to bid on either;

the acquisition of the Terminal Equipment and any other movable assets only, and/or

the acquisition of the entire business of the terminal as a going concern 	and, on the basis that they will receive the benefit of any insurance proceeds or outstanding claims under any, material damage insurance policies on the date the New Terminal Operator Agreement is entered into.

As soon as practicable after tenders have been received TNPA shall (acting reasonably) evaluate the Tenders and shall notify the Terminal Operator of the Highest Compliant Tender Price.

If the Terminal Operator refers a dispute relating to the Highest Compliant Tender Price to dispute resolution in accordance with clause 57 (Dispute Resolution), TNPA shall nevertheless be entitled to enter into a New Terminal Operator Agreement.

Upon receipt of the Highest Compliant Tender Price and within 180 (one hundred and eighty) Days after the Adjusted Highest Compliant Tender Price has been determined, TNPA shall pay to the Terminal Operator the Adjusted Highest Compliant Tender Price after TNPA has set off all amounts due and owing to it by the Terminal Operator.

The discharge by TNPA of its payment obligation in clause 48.2.11 above shall be in full and final settlement of any and all claims and rights of the Parties as against each other for breaches and/or termination of this Agreement and the Project Documents whether under contract, delict or otherwise.

If the Adjusted Highest Compliant Tender Price is not accepted by the Terminal Operator, TNPA shall have no obligation to make any payment to the Terminal Operator, in which event the Terminal Operator shall remain obliged to comply with the provisions of clause 47.4 and 47.6 above.  In these circumstances the TNPA shall be released from all liability to the Terminal Operator for breaches and/or termination of this Agreement and any other Project Document whether under contract, delict or otherwise.

TNPA may elect at any time prior to the receipt of a Tender to follow the no retendering procedure under Clause 48.3 (no retendering procedure) by notifying the Terminal Operator that this election has been made.

If TNPA receives a Tender but decides not to complete the Tender Process, it shall notify the Terminal Operator of this decision and exercise its rights as per the provisions of clause 47.3 and 47.4 and/or 47.5.

No Retendering Procedure

If either TNPA is not entitled to or elects not to retender pursuant to clause 48.1 (retendering election) then the following procedure shall apply:

The Terminal Operator shall afford the TNPA the first option, by way of written notice, to purchase the Equipment at a value and price determined by an Independent Expert, whose valuation shall be provided to the TNPA by written notice (‘Notice’).

The TNPA shall exercise its option to purchase the Equipment within 90 (ninety) days of receipt of the Notice referred to in 48.3.1.1, failing which the Terminal Operator shall be entitled to sell the Equipment to any third party and hand back the Terminal in accordance with 47.4 and 47.6.

In the event of TNPA electing not to purchase the Equipment, the Terminal Operator shall be obliged to remove such Equipment from Project Site within 90 (ninety) days of TNPA notifying the Terminal Operator of its election not to purchase the Equipment.

Save for payment to the Terminal Operator for the Terminal Equipment the, TNPA shall have no obligation to make any payment to the Terminal Operator and shall be released from all liability to the Terminal Operator for breaches and/or termination of this Agreement and any other Project Documents whether under contract, delict or otherwise.

- Termination Amount for TNPA Default

On termination of this Agreement as a result of a TNPA Default, the TNPA shall pay the Terminal Operator an amount equal to the direct actual costs incurred or sustained by the Terminal Operator as a consequence of the termination of the Agreement (such costs to be calculated by the Terminal Operator, and confirmed by the Payment Expert, and delivered by way of notice to the TNPA).  The direct actual costs will be limited to the following:

the value of the Terminal Infrastructure which compensation shall be determined with reference to:

the fair value of the Equity of the Terminal Operator; alternatively

the discounted cash flow (DCF) of all future proceeds in respect of the LNG Terminal for the remainder of the Operating Term,

- whichever is higher as at the date of termination; plus

the Debt; plus

the Subcontractors and Suppliers Costs; plus

an amount equal to the redundancy payments for employees of the Terminal Operator not transferring to the TNPA or its nominee that have been or will reasonably be incurred by the Terminal Operator as a direct result of the termination of this Agreement; plus

the transfer costs (being all costs incurred by the Terminal Operator in connection with the TNPA taking over the Construction Works (where applicable), the LNG Terminal, the Project Sites, the Consents / Approvals and the Project or to nominate a third party to do so),

provided that the Terminal Operator shall use reasonable endeavours to mitigate its liability in respect of all such amounts;

(such total amount payable by the TNPA to the Terminal Operator shall constitute the “Termination Amount”).

Payment Expert Calculations

If any calculation or valuation is required to be made for the purposes of determining an amount payable by the TNPA to the Terminal Operator pursuant to clause 49.1, the same shall be made by the Payment Expert.

The Terminal Operator and the TNPA shall ensure that the Payment Expert is appointed within fifteen (15) Business Days of delivery by the Terminal Operator of the notice in terms of clause 45.3.1 alternatively the notice in terms of clause 49.1.  The Payment Expert shall have fifteen (15) Business Days to calculate the amount payable by the TNPA to the Terminal Operator pursuant to this clause 49 (Compensation on Termination for TNPA Default).

Upon determination of the amount payable by the TNPA to the Terminal Operator pursuant to this clause 49 (Compensation on Termination for TNPA Default), the Terminal Operator shall be entitled to issue a written demand to the TNPA for payment of such amount (which amount shall be payable within 90 (ninety) days of demand).

In making any determination pursuant to this clause 49.2 (Payment Expert Calculations), the Payment Expert shall act as an expert and not an arbitrator.

- Termination Amount for Invalidation in terms of section 67 of the Act

- On termination of this Agreement in terms of section 67 of the Act, TNPA shall pay to the Terminal Operator the compensation as determined in accordance with the provisions of clause 49 (Termination Amount for TNPA Default).

- Termination Amount for termination for Force Majeure

- On termination of this Agreement in accordance with the provisions of clause 45.4 (Termination for Force Majeure), no payments and/or compensation will be payable by TNPA to the Terminal Operator and the Terminal Operator will have no claim against TNPA for any payments and/or compensation upon such termination.

- Termination Amount for corrupt gifts and fraud

  - On termination of this Agreement in accordance with clause 52 (Corrupt Acts and fraud), TNPA shall pay the Terminal Operator, an amount equal to the market value of any other assets and rights of the Terminal Operator (other than those transferred to TNPA pursuant to this Agreement) less the liabilities of the Terminal Operator properly incurred in connection with this Agreement, provided that no account shall be taken of any liabilities and obligations of the Terminal Operator out of:

agreements or arrangements entered into by the Terminal Operator to the extent that such agreements or arrangements were not entered into in connection with the Terminal Operator’s obligations in relation to the Project;

agreements or arrangements entered into by the Terminal Operator to the extent that such agreements or arrangements were not entered into in the ordinary course of business and on commercial arm’s length terms; and

less any amounts that TNPA is entitled to set off and deduct under clause 60.11 (set-off).

  - If the aggregate of the amounts referred to above is less than zero, then, for the purposes of the calculation in this clause 52 the aggregate shall be deemed to be zero.

  - If the termination is because of a Corrupt Act on the part of the Terminal Operator, then the amount payable to the Terminal Operator, inclusive of shares and the like, will be zero.

- Payment of Termination Amount

"Notice Date" means the date when the Termination Amount has been determined in accordance with clause 50 (Termination amount for invalidation in terms of Section 67 of the Act) or clause 52 (Termination Amount for corrupt gifts and fraud).

"Termination Amount" means any compensation payable by TNPA to the Terminal Operator on an early termination of the Agreement under clause 50 (Termination amount for invalidation in terms of Section 67 of the Act) and 52 (Termination Amount for corrupt gifts and fraud).

Method of payment

TNPA shall pay to the Terminal Operator the Termination Amount no later than 60 (sixty) Days after the Notice Date unless it elects to pay in accordance with clause 53.3.2 below.

TNPA may elect to pay the Termination Amount in not more than 3 instalments, on the dates (the "Instalment Dates") as the Parties may otherwise agree.

From the Notice Date until the date of payment, interest shall accrue on any unpaid element of the Termination Amount at the default rate detailed in clause 38 (Default Interest) and be payable on the next occurring Instalment Date.

If TNPA has elected to pay in accordance with clause 53.3.2 above, it may (on 30 (thirty) Days prior written notice to the Terminal Operator) elect to pay any outstanding element of the Termination Amount in full on any Instalment Date.

If TNPA fails to make a payment to the Terminal Operator in accordance with clause 53.3 (Method of Payment) or clauses 53.3.2 and 53.3.3 above, the Terminal Operator may issue a notice to TNPA declaring any unpaid and outstanding element of the Termination Amount to be immediately due and payable.

TNPA shall be entitled to set off against any Termination Amount, any monies owed and due to it by the Terminal Operator at the time for payment of the Termination Amount.

- Liability for Indirect and Consequential Losses and Damages

Notwithstanding any other provision of this Agreement, neither Party shall be liable to the other for any indirect, consequential or special damages, including loss of profit or anticipated savings, except as specifically set out in this Agreement.

# PART VIII – PROCEDURAL ISSUES

- Corrupt gifts and fraud

The Terminal Operator warrants that in entering into this Agreement it has not committed any Corrupt Act.

If the Terminal Operator, any Shareholder, any Subcontractor or any Affiliate of any of them (or anyone employed by or acting on behalf of any of them) commits or is reasonably suspected by TNPA of having committed any Corrupt Act, then TNPA shall be entitled to act in accordance with clauses 55.2.1 to 55.2.6 below:

if the Corrupt Act is committed by the Terminal Operator, any Shareholder, any director of the Terminal Operator, any director of any Shareholder, or any employee of the Terminal Operator or of any Shareholder acting under the authority of or with the knowledge of a director of the Terminal Operator or such Shareholder, as the case may be, then in any such case, TNPA may terminate this Agreement with immediate effect by giving written notice to the Terminal Operator;

if the Corrupt Act is committed by an employee of the Terminal Operator or of any Shareholder acting of his or her own accord, then in any such case, TNPA may give written notice to the Terminal Operator of termination and this Agreement will terminate, unless within 10 (ten) Business Days of the Terminal Operator’s receipt of such notice that employee’s involvement in the Project is terminated and (if necessary) the performance of any part of the Project Deliverables previously performed by him or her is performed by another Person;

if the Corrupt Act is committed by a Subcontractor, director of a Subcontractor or an employee of a Subcontractor acting under the authority or with the knowledge of a director of that Subcontractor, then in any such case, TNPA may give written notice to the Terminal Operator of termination and this Agreement will terminate, unless within 60 (sixty) Business Days of its receipt of such notice the Terminal Operator terminates the relevant Subcontract and procures the performance of the relevant part of the Project Deliverables by another Person, where relevant;

if the Corrupt Act is committed by an employee of a Subcontractor acting of his or her own accord, then TNPA may give notice to the Terminal Operator of termination and this Agreement will terminate, unless within 10 (ten) Business Days of its receipt of such notice the Terminal Operator procures the termination of that employee’s involvement in the Project and (if necessary) procures the performance of that part of the Project Deliverables previously performed by that employee to be performed by another Person;

if the Corrupt Act is committed by any other Person not specified in clauses 55.2.1 to 55.2.4 above but involved in the Project as a Subcontractor or supplier to any Subcontractor or to the Terminal Operator, then TNPA may give notice to the Terminal Operator of termination and this Agreement will terminate unless within 40 (forty) Business Days the Terminal Operator procures the termination of such Person’s involvement in the Project and (if necessary) procures the performance of the relevant part of the Project by another Person; and

any notice of termination under this clause 55.2 shall specify:

the nature of the Corrupt Act;

the identity of the party or parties who TNPA believes has committed the Corrupt Act; and

the date on which this Agreement will terminate in accordance with the applicable provisions of this clause.

Without prejudice to its other rights or remedies under this clause, TNPA shall be entitled to recover from the Terminal Operator, the greater of:

the amount or value of the gift, consideration or commission which is the subject of the Corrupt Act; and

any direct losses sustained by TNPA in consequence of any breach of this clause by the Terminal Operator.

Nothing contained in this clause shall prevent the Terminal Operator from paying any proper commission or bonus to its employees within the agreed terms of their employment.

The Terminal Operator shall notify TNPA of the occurrence (and details) of any Corrupt Act promptly on the Terminal Operator becoming aware of its occurrence.

- Expert Determination

Any dispute arising out of or in connection with this Agreement which is referred to resolution in terms of this clause 56 (Expert Determination) shall be determined in accordance with the provisions of this clause 56.1. The dispute resolution provisions contained in this clause 56.1 shall only be used in respect of matters specifically referred to dispute resolution in terms of this clause 56.1 by this Agreement, and all other disputes arising out of or in connection with this Agreement, or the subject matter of this Agreement shall not be referred to resolution in terms of this clause 56.1 but shall be dealt with in accordance with the Law applicable to such disputes and may be the subject of dispute resolution in terms of clause 56 (Dispute Resolution). Clause 56 (Expert Determination) shall be held in  Gqeberha  and the Parties shall endeavour to ensure that it is completed within 90 (ninety) Days after appointment of the Person designated in the clause of this Agreement that refers the relevant matter to determination under this clause 56.1 (such Person being the "Independent Expert" in this clause 56.1).

The Parties shall procure that the Independent Expert acts in accordance with the following criteria:

the Independent Expert shall have appropriate expertise in respect of the subject matter of the dispute to be referred to him; and

the Independent Expert shall be disinterested in the matter which is the subject of the dispute and shall have no interest in the outcome of the dispute.

The procedure to be followed in a dispute resolution shall be determined by the Independent Expert at the request of either Party, with due regard to the following principles:

the Independent Expert shall have full and unrestricted powers in relation to the dispute resolution. In particular, but without limitation, the Independent Expert shall have the power of a single arbitrator appointed in terms of the Arbitration Act, 1965 and need not strictly observe the rules of evidence;

the Independent Expert may not have regard to his personal knowledge of the facts, and any expert knowledge he may have, relating to the issues in dispute, but is to afford the Parties an opportunity of challenging the knowledge which he claims to have;

the Independent Expert may make such award, whether interim, provisional or final, as he considers appropriate, including without limitation ex parte awards, declaratory orders, interdicts and awards for specific performance, restitution, damages, penalties, security for costs or restitution;

the Independent Expert shall give his reasons for the award, if so, requested by either Party; and

subject to any relevant provisions of this Agreement, the Independent Expert shall make such award as to costs as he deems appropriate. If the Independent Expert's charges and any other costs have to be paid before the Independent Expert has made his award in respect of costs, the Parties shall pay the costs in equal amounts, and if a Party fails to pay its share, the Independent Expert may make his award in respect of the claim and costs in the absence of that Party. It is recorded that the Parties intend that the successful Party shall be awarded a full indemnity for all costs reasonably incurred by that Party and not merely the costs on the High Court or other scale.

The Parties shall use their best endeavours to procure that the Independent Expert complies with the provisions of clause 56.2 and that the procedures detailed in clause 56.3 above are followed.

Nothing in this clause 56 shall prevent a Party from seeking relief, in respect of matters referred to dispute resolution in terms of clause 56.1 of this Agreement, on an urgent or interlocutory basis with a court of appropriate jurisdiction.  Subject to the provisions of the clause of this Agreement that refers a dispute to determination in terms of this clause 56.1, if either Party is dissatisfied with or otherwise wishes to challenge the Expert's decision, recourse may be had to dispute resolution in terms of clause 57 (Dispute Resolution).

- Dispute Resolution

Referable disputes

The provisions of this clause 57 (Dispute Resolution) shall, save where expressly provided otherwise, apply to any dispute arising in relation to or in connection with any aspect of this Agreement between the Parties.

Internal referrals

If a dispute arises in relation to any aspect of this Agreement, the Parties shall attempt in good faith to come to an agreement in relation to the disputed matter, in accordance with the following informal process:

all disputes shall first be referred to a meeting of the liaison officers or other designated executives from each Party who are actively involved in the Project, and have sufficient authority to be able (if necessary, with consultation back to their respective organisations) to resolve it;

if the Parties have been unable to resolve the dispute within 15 (fifteen) Days of referral to the persons specified in clause 57.2.1.1, either Party may refer the dispute for a decision by the chief executive officer of TNPA and the chief executive officer or equivalent officer of the Terminal Operator;

if the chief executive officers are still unable to resolve the dispute, within 15 (fifteen) Days as specified in 57.2.1.2 either party may refer the dispute for a decision by the respective chairpersons of the board of directors of either party; and

In attempting to resolve the dispute in accordance with the provisions of this clause 57.2 (Internal Referral), the Parties shall (and shall procure that their employees and representatives shall) use reasonable endeavours to resolve such dispute without delay by negotiations or any other informal procedure which the relevant representatives may adopt. Those attempts shall be conducted in good faith in an effort to resolve the dispute without necessity for formal proceedings; and

Any dispute which has not been resolved by the representatives contemplated in clause 57.2.1 within 15 (fifteen) Days of the dispute being referred to them (or any longer period agreed between the Parties) shall be treated as a dispute in respect of which informal resolution has failed and shall be referred for determination in terms of clause 57.7 (Fast-track dispute resolution).

Performance to continue

No reference of any dispute to any resolution process in terms of this clause 57 (Dispute Resolution) shall relieve either Party from any liability for the due and punctual performance of its obligations under this Agreement.

Litigation

Save where any dispute has been expressly referred for determination in terms of clause 57.7 (fast-track dispute resolution), if informal resolution of any dispute has failed, then the dispute may be referred to litigation in the High Courts by either Party; and

Neither Party is limited in any proceedings before the High Court to the information, evidence or arguments used in the informal attempts to resolve the dispute.

Interlocutory proceedings

Notwithstanding the previous provisions of this clause either Party shall have the right to seek appropriate interdictory relief or an order of specific performance against the other in an appropriate court having jurisdiction in South Africa.

Suspension of prescription

The Parties agree that, for the purposes of the Prescription Act, 1969, time shall cease to run in respect of any dispute on the date of service of the relevant notice referring that dispute for mediation, and if any other subsequent proceedings are instituted in respect of that dispute, time shall continue to cease to run from the date of service of the relevant summons or notice of motion.

Fast-track dispute resolution

Disputes expressly referred for determination pursuant to this clause 57.7 (fast-track dispute resolution) shall be determined by the relevant Independent Expert;

Within 5 (five) Business Days after a dispute has been referred by Party to the appropriate Independent Expert, the Independent Expert shall require the Parties to submit in writing their respective arguments. The Independent Expert shall, in his or her absolute discretion, consider whether a hearing is necessary in order to resolve the dispute;

It shall be entirely within the power and competence of the Independent Expert to decide upon any matters related to the proper preparation of the dispute for hearing and in that regard the Independent Expert shall direct the Parties accordingly;

The Independent Expert shall set the date for the hearing, choose the venue (which must be a venue in South Africa) for the hearing and determine all matters regarding any aspect of the hearing.  Moreover, the Independent Expert can decide whether at the hearing the Parties are to give oral evidence or confine themselves to presenting their cases in writing or by some other appropriate procedure.  In this regard, the Independent Expert must be guided by considerations of fairness, the cost-effective resolution of the dispute, and the need to resolve the dispute quickly;

The Independent Expert shall provide both Parties with his or her written decision on the dispute, within 20 (twenty) Business Days of the referral (or such other period as the Parties may agree after the referral). The Independent Expert shall give his or her reasons for the award, if so, requested by either Party;

The Independent Expert's costs of any referral shall be borne as the Independent Expert shall specify or, if not specified, equally by the Parties. Each Party shall bear its own costs arising out of the referral, including its legal costs and the costs and expenses of any witnesses;

The Independent Expert shall act impartially and may take the initiative in ascertaining the facts and the Law. The Independent Expert need not strictly observe the principles of Law and may decide the matter submitted to him or her in accordance with what he or she considers equitable in the circumstances;

Subject to clause 57.5, should the need arise for either Party to seek interim or temporary relief before the adjudication is finalised, that Party may apply to the Independent Expert to grant such interlocutory order or give the required temporary relief and the Independent Expert shall have the same power to do so as if the matter were heard by a Judge in the High Court of South Africa, save that if by Law such power or order cannot be exercised or given by an Independent Expert then, and then only, should the Parties refer such matter to such High Court;

The proceedings shall be confidential, and all information, data or documentation disclosed or delivered by either Party to the Independent Expert in consequence of or in connection with his or her appointment as Independent Expert shall be treated as confidential.  Neither the Parties nor the Independent Expert shall, save as permitted by the confidentiality provisions of this Agreement, disclose to any Person any such information, data or documentation unless the Parties otherwise agree in writing, and all such information, data or documentation shall remain the property of the Party disclosing or delivering the same and all copies shall be returned to such Party on completion of the Independent Expert's work;

The Independent Expert is not liable for anything done or omitted in the discharge or purported discharge of his or her functions as Independent Expert, unless the act or omission is negligent or in bad faith.  Any employee or agent of the Independent Expert is similarly protected from liability;

Should any Party fail to co-operate with the Independent Expert with the result that in the view of the Independent Expert such default or omission prejudices the adjudication process, then the Independent Expert can either:

give that Party written notice that unless it remedies the default or omission within a given time, it will forfeit the right to continue to participate in the adjudication; or

warn the Party in writing that its default or omission may make it liable to a punitive order of costs irrespective of whether it succeeds in the adjudication or not and such punitive award of costs may include an order of attorney and client costs or attorney and own client costs as those expressions are understood in the Uniform Rules of Court; and

The Independent Expert shall be deemed not to be an arbitrator but shall render his or her decision as an expert and the provisions of the Arbitration Act, 1965 and any other law relating to arbitration shall not apply to the Independent Expert or his or her determination or the procedure by which he or she reaches his or her determination.  The Independent Expert's decision shall be final and binding on the Parties.

Survival of clause 57

The provisions of this clause 57 (Dispute Resolution):

constitute an irrevocable consent by the Parties to any proceedings in terms hereof and no Party shall be entitled to withdraw therefrom or claim at any such proceedings that it is not bound by such provisions; and

are severable from the rest of this Agreement and shall remain in effect despite the termination of or invalidity for any reason of this Agreement.

- Information and Audit Access

The Terminal Operator shall,  in respect of the Project provide to TNPA  all information, documents, records and the like in the possession of, or available to, the Terminal Operator (and to this end the Terminal Operator shall use all reasonable endeavors to ensure that all such information in the possession of any counter-party to any Project Document shall be available to it and the Terminal Operator has included, or shall include, relevant terms in all Project Documents to this effect) as may reasonably be requested by TNPA  for the purpose of complying with any of its statutory reporting obligations including where pursuant to the Public Finance Management Act, 1999 or the Auditor-General Act, 1995.

Without limiting the generality of the aforegoing, the Terminal Operator shall:

provide and shall procure that its Subcontractors shall provide all such information as TNPA may reasonably require from time to time to enable TNPA to provide reports and returns as required by any Relevant Authority, including reports and returns regarding the physical condition of any building occupied by TNPA, health and safety, national security, and environmental safety; and

note and facilitate TNPA’s compliance with the Promotion of Access to Information Act, 2000 if TNPA is required to provide information to any Person pursuant to that Act.

- Confidentiality and Non-Circumvention

The Parties undertake that during the operation of, and after the expiration, termination or cancellation of, this Agreement for any reason, they will keep confidential:

any information which a Party ("Disclosing Party") communicates to the other Party ("Recipient"), and which is stated to be or by its nature is intended to be confidential;

all other information of the same confidential nature concerning the business of the Disclosing Party which comes to the knowledge of the Recipient whilst it is engaged in negotiating the terms of this Agreement, the services Agreement or after conclusion thereof, including:

details of the Disclosing Party's financial structures and operating results;

details of the Disclosing Party's strategic objectives and planning;

- other than instances where any information is disclosed to equity funders and/or such other persons in the process of obtaining other forms of capital.

If the Recipient is uncertain as to whether any information is to be treated as confidential in terms of this clause 59 (Confidentiality), it shall be obliged to treat it as such until written clearance is obtained from the Disclosing Party.

Each Party undertakes, subject to clause 59.4, not to disclose any information which is to be kept confidential in terms of this clause 59 (Confidentiality), nor to use such information for its own or anyone else's benefit.

Notwithstanding the provisions of clause 59.3, the Recipient shall be entitled to disclose any information to be kept confidential if and to the extent only that the disclosure is bona fide and necessary for the purposes of carrying out its duties in terms of this Agreement.

The obligation of confidentiality placed on the Parties in terms of this clause 59 (Confidentiality) shall cease to apply to the Recipient in respect of any information which:

is or becomes generally available to the public other than by the negligence or default of the Recipient or by the breach of this Agreement by the Recipient;

the Disclosing Party confirms in writing is disclosed on a non-confidential basis;

has lawfully become known by or come into the possession of the Recipient on a non-confidential basis from a source other than the Disclosing Party having the legal right to disclose same, provided that such knowledge or possession is evidenced by the written records of the Recipient existing at the Signature Date; or

is disclosed pursuant to a requirement or request by operation of law, regulation or court order, to the extent of compliance with such requirement or request only and not for any other purpose, provided that:

the onus shall at all times rest on the Recipient to establish that information falls within the exclusions set out in clauses 59.5.1 to 59.5.4 (both inclusive);

information will not be deemed to be within the foregoing exclusions merely because such information is embraced by more general information in the public domain or in the Recipient's possession; and

any combination of features will not be deemed to be within the foregoing exclusions merely because individual features are in the public domain or in the Recipient's possession, but only if the combination itself and its principle of operation are in the public domain or in the Recipient's possession.

In the event that the Recipient is required to disclose confidential information of the Disclosing Party as contemplated in clause 59.5.4, the Recipient will:

advise the Disclosing Party thereof in writing prior to disclosure, if possible;

take such steps to limit the disclosure to the minimum extent required to satisfy such requirement and to the extent that it lawfully and reasonably can;

afford the Disclosing Party a reasonable opportunity, if possible, to intervene in the proceedings;

comply with the Disclosing Party's reasonable requests as to the manner and terms of any such disclosure; and

notify the Disclosing Party of the recipient of, and the form and extent of, any such disclosure or announcement immediately after it is made.

- Miscellaneous Matters

Addresses

The Parties choose the following addresses to which notices may be given, and at which documents in legal proceedings may be served (i.e., their domicilia citandi et executandi), in connection with this Agreement:

in the case of TNPA:

postal address	: P.O.Box 612054 Bluewater Bay, 6212.

physical address	:e-Mendi Building

N2 Neptune Road

Off Klub Road

Gqeberha

6001.

email address   :

attention	  :

in the case of the Terminal Operator:

postal address	:

physical address	:

email address    :

attention           :

(being "Party's addresses").

Notices given to the above addresses shall be delivered by hand or courier service and shall only be deemed received by the recipient Party once signed for on its behalf.

A Party may change that Party's addresses for this purpose, by notice in writing to the other Party, provided that the new addresses include a physical address in South Africa.

Certificate of indebtedness

A certificate signed by any officer, manager or employee of TNPA or {PREFERRED BIDDER}, the appointment of which officer or manager or employee need not be proved, reflecting:

any monies owing by the Terminal Operator to TNPA or vice versa under this Agreement;

any obligations owing by the Terminal Operator to TNPA or vice versa under this Agreement; and

the due date for payment of such monies or for performance of such obligations;

shall be prima facie proof thereof.

Entire Agreement

This Agreement contains all the express provisions agreed on by the Parties with regard to the subject matter of this Agreement and the Project, and the Parties waive the right to rely on any alleged express provision not contained in this Agreement;

If there is a conflict between the terms of this Agreement and those of any Schedule, the terms of this Agreement shall prevail; and

This Agreement, and the rights and obligations of the Parties (save for those subjects to suspensive conditions) shall take effect on the Signature Date.

Rights and remedies

The rights and remedies of the Parties under this Agreement are cumulative, may be exercised as often as the Parties require and are in addition to any other rights and remedies, which the Parties may have under the Law.

Further undertakings

TNPA and the Terminal Operator shall perform, or procure the performance, of all further things, and execute and deliver (or procure the execution and delivery) of all further documents, as may be required by the Law or as may be desirable or necessary to implement or give effect to the Project, this Agreement and the transactions contemplated therein.

No Representations

A Party may not rely on any representation which allegedly induced that Party to enter into this Agreement unless the representation is recorded in this Agreement.

Variation, Cancellation and Waiver

No contract varying, adding to, deleting from or cancelling this Agreement, and no waiver of any right under this Agreement, shall be effective unless reduced to writing and signed by or on behalf of the Parties; and

The termination of this Agreement shall not prejudice the rights of any Party in respect of any antecedent breach or non-performance of or in terms of this Agreement.

Indulgences

The grant of any indulgence by a Party under this Agreement shall not constitute a waiver of any right by the grantor or prevent or adversely affect the exercise by the grantor of any existing or future right of the grantor.

If any Party at any time breaches any of that Party's obligations under this Agreement, the other Party ("the Aggrieved Party"):

may, at any time after that breach, exercise any right that became exercisable directly or indirectly as a result of the breach, unless the Aggrieved Party has expressly elected in writing not to exercise the right.  If the Aggrieved Part is willing to relinquish that right the Aggrieved Party will on request do so in writing.  In particular, acceptance of late performance shall, for a reasonable period after performance, be provisional only, and the Aggrieved Party may still exercise that right during that period; and

shall not be estopped (i.e. prevented) from exercising the Aggrieved Party's rights arising out of that breach, despite the fact that the Aggrieved Party may have elected or agreed on one or more previous occasions not to exercise the rights arising out of any similar breach or breaches.

Invalidity and Severability

If any of the provisions of this Agreement becomes invalid, illegal or unenforceable for any reason, the validity, legality and enforceability of the remaining provisions of this Agreement shall not be impaired or affected in any way by such invalidity, illegality or unenforceability.

Cession

- The Terminal Operator shall not be permitted to cede, assign or delegate its rights and/or its obligations in terms of this Agreement without the prior written consent of TNPA. Any assignment, delegation or cession without such consent shall be of no force and effect. For the avoidance of doubt, the Terminal Operator shall not be entitled to cede or transfer any rights it has under this Agreement to any third party and/ or dilute any of its black shareholding and/or black ownership as defined in the B-BBEE Codes as amended from time.

Set-off

The Parties shall not be entitled to set-off, withhold or deduct any monies, which one Party owes to the other against any monies that are owed by one Party to the other in terms of this Agreement.

Applicable law

This Agreement is to be interpreted and implemented in accordance with the Law of South Africa.

Language

All notices or communications under or in connection with the Project shall be in English.

Jurisdiction of South African Courts

Subject to clause 56 (Expert Determination) and 57 (Dispute Resolution), the Parties consent to the exclusive jurisdiction of the Gqeberha High Court of South Africa, for any proceedings arising out of or in connection with the Project and this Agreement.

Costs

Each Party shall bear its own costs of negotiating and concluding this Agreement.

Counterparts

This Agreement may be executed in more than one counterpart, each of which together shall constitute one and the same instrument.

Signed at    __________________________ on  ______________________ 2024.

For:     Transnet National Port Authority

Signature:

Name     :

Chief Executive, duly authorised and warranting such authority

Date      :

Place     :

Witness :

Witness :

Signed at    __________________________  on  ______________________ 2024.

For:	Terminal Operator

Signature:

Name     :

duly authorised and warranting such authority

Date      :

Place     :

Witness :

Witness :

| SCHEDULES |  |
| --- | --- |
| Schedule | Appointment Letter |
| Schedule | Project Site |
| Schedule | Business Case |
| Schedule | Base Case Financial Model |
| Schedule | D & C Specifications |
| Schedule | Construction Agreement |
| Schedule | Terminal Operators Operational Plan |
| Schedule | Terminal Equipment |
| Schedule | Environmental Management Plan |
| Schedule | Terminal Operators B-BBEE’s Contributor Level Certificate |
| Schedule | Supplier Development Plan and Supplier Development Value Summary Worksheet |
| Schedule | Penalties |
| Schedule | B-BBEE Contributor Level Commitment |
| Schedule | Construction Performance Guarantee |
| Schedule | Operating Performance Guarantee |
| Schedule | Final Maintenance Guarantee |
| Schedule | Project Insurance |
| Schedule | Terminal Operator’s Operating Specifications |
| Schedule | Key Performance Areas |
| Schedule | Terminal Operator Performance Standards |
| Schedule | Penalty and Incentive Cascade Formula |
| Schedule | Liquid Bulk Terminal - Mandatory Requirements for SHE, Process Safety, Civil, Structural, Mechanical and Electrical |
| Schedule | Construction Programme |
| Schedule | Constitutional Documents |
| Schedule | TNPA Policies, Manuals and Operating Conditions |
| Schedule | Annual Reporting |
| Schedule | Independent Certifier Agreement |
| Schedule | Economic development guideline document |